## PO Format D 11C
Billing Schedule for Civil Engineering Works including all Supplies (Deposit 11C)
Revision - R3
Design, Engineering, Manufacture, Supply, Storage & handling at site, Construction including enabling work, Erection, Testing, Commissioning and Demonstration of Performance Guarantee of New Crushing Plant & Downhill Conveyor System of Deposit 14 and 11C at Bailadila Iron Ore Mines, NMDC, Kirandul Complex (Chhattisgarh) on Turnkey basis.
Contract Agreement no. HO(Contracts)/NCP&DHCS/DEP-14&11C/945/310/227 dated 28.03.2025
Header Line Item | Service Item | Description | Unit | Approx. Qty. | Basic Rate (Rs) | 77.5% of Basic Rate | 77.5% of Basic value | % Progress | Progress Amount (Rs) | GST 18% | 77.5% Gross Value (Rs)
Civil Engineering Work Clause no. 1 of Table 4A (Deposit - 11C ) of Price Schedule for Civil Engineering Works including all Supplies of Appendix -1 of Contract Voulme of Contract Agreement between SKSL & NMDC.
INDUSTRIAL BUILDINGS/ FACILITIES
140/300 |  | Civil Engineering Works 1 Dep -11C with ITC
| 1 | Excavation for industrial buildings/ facilities | Cum | 435125 | 800 | 620 | 269777500 | 1 | 269777500 | 48559950 | 318337450 | 348100000
| 2 | Slope Protection | Lump Sum | 1 | 15000000 | 11625000 | 11625000 | 1 | 11625000 | 2092500 | 13717500 | 15000000
| 3 | Back Filling | Cum | 117000 | 100 | 77.5 | 9067500 | 1 | 9067500 | 1632150 | 10699650 | 11700000
| 4 | PCC for industrial buildings/ facilities | Cum | 2830 | 15000 | 11625 | 32898750 | 1 | 32898750 | 5921775 | 38820525
| 5 | RCC for industrial buildings/ facilities | cum | 22960 | 27500 | 21312.5 | 489335000 | 1 | 489335000 | 88080300 | 577415300
|  | Total |  |  |  |  | 812703750 |  |  | 146286675 | 958990425
150/310 | 1 | Reinforcement Steel Works - On supply of reinforcement steel -For industrial buildings/ facilities | MT | 2686 | 90000 | 69750 | 187348500 | 0.75 | #REF! | 33722730 | 221071230
| 2 | Reinforcement Steel Works - On cutting, bending and fixing of reinforcement steel - For industrial buildings/ facilities | MT | 2686 | 30000 | 23250 | 62449500 | 0.2 | #REF! | 11240910 | 73690410
| 3 | Brickwork for industrial buildings/ facilities | Cum | 540 | 13000 | 10075 | 5440500 | 1 | 5440500 | 979290 | 6419790
| 4 | Door, Windows and Ventilators for industrial buildings/ facilities | Sqm | 330 | 10000 | 7750 | 2557500 | 1 | 2557500 | 460350 | 3017850
| 5 | Flooring Work for industrial buildings/ facilities | Sqm | 7375 | 2000 | 1550 | 11431250 | 1 | 11431250 | 2057625 | 13488875
| 6 | Plastering Work for industrial buildings/ facilities | Sqm | 9300 | 800 | 620 | 5766000 | 1 | 5766000 | 1037880 | 6803880
| 7 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for industrial buildings/ facilities - Substation (D11C-SS#1), | Lumpsum | 1 | 900000 | 697500 | 697500 | 1 | 697500 | 125550 | 823050
| 8 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for industrial buildings/ facilities - Substation (D11C-SS#2) | Lumpsum | 1 | 900000 | 697500 | 697500 | 1 | 697500 | 125550 | 823050
| 9 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for industrial buildings/ facilities - Reservoir | Lumpsum | 1 | 350000 | 271250 | 271250 | 1 | 271250 | 48825 | 320075
| 10 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for industrial buildings/ facilities - Pump House | Lumpsum | 1 | 500000 | 387500 | 387500 | 1 | 387500 | 69750 | 457250
|  | Total |  |  |  |  | 277047000 |  |  | 49868460 | 326915460
|  | TOTAL FOR INDUSTRIAL BUILDINGS |  |  |  |  | 1089750750 | 0 | 0 | 196155135 | 1285905885
ANCILLIARY FACILITIES
160/320 |  | Civil Engineering Works 3 Dep 11C without ITC
| 1 | Excavation for ancilliary facilities. | Cum | 11500 | 800 | 620 | 7130000 | 1 | 7130000 | 1283400 | 8413400
| 2 | PCC for ancilliary facilities. | Cum | 170 | 15000 | 11625 | 1976250 | 1 | 1976250 | 355725 | 2331975
| 3 | RCC for ancilliary facilities. | Cum | 1040 | 27500 | 21312.5 | 22165000 | 1 | 22165000 | 3989700 | 26154700
| 4 | Reinforcement Steel Works - On supply of Reinforcement Steel - For for ancilliary facilities. | MT | 114 | 90000 | 69750 | 7951500 | 0.75 | #REF! | 1431270 | 9382770 | 4185000 | 5400000 | 47368.4211
| 5 | Reinforcement Steel Works - On Cutting, Bending & Fixing of Reinforcement Steel - For for ancilliary facilities. | MT | 114 | 30000 | 23250 | 2650500 | 0.2 | #REF! | 477090 | 3127590 | 1116000 | 1440000 | 12631.5789
| 6 | Brickwork for ancilliary facilities. | Cum | 460 | 13000 | 10075 | 4634500 | 1 | 4634500 | 834210 | 5468710
| 7 | Doors, Windows and Ventilators- for ancilliary facilities. | Sqm | 310 | 10000 | 7750 | 2402500 | 1 | 2402500 | 432450 | 2834950
| 8 | Flooring work for ancilliary facilities. | Sqm | 625 | 2000 | 1550 | 968750 | 1 | 968750 | 174375 | 1143125
| 9 | Plastering Work for ancilliary facilities. | Sqm | 8950 | 800 | 620 | 5549000 | 1 | 5549000 | 998820 | 6547820
| 10 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for ancilliary facilities - Rest Shelter and office building | Lumpsum | 1 | 1200000 | 930000 | 930000 | 1 | 930000 | 167400 | 1097400
| 11 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for ancilliary facilities - Plant executive building | Lumpsum | 1 | 1000000 | 775000 | 775000 | 1 | 775000 | 139500 | 914500
| 12 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for ancilliary facilities - Toilet Block | Lumpsum | 1 | 150000 | 116250 | 116250 | 1 | 116250 | 20925 | 137175
| 13 | Road & Paved areas - Road - Earth work in formation | Sqm | 16500 | 1500 | 1162.5 | 19181250 | 0.25 | #REF! | 3452625 | 22633875 | 19181250 | 1162.5 | 1500
| 14 | Road & Paved areas - Road - Base | Sqm | 16500 | 1500 | 1162.5 | 19181250 | 0.25 | #REF! | 3452625 | 22633875 | 19181250 | 1162.5 | 1500
| 15 | Road & Paved areas - Road - Bitumen topping | Sqm | 16500 | 2100 | 1627.5 | 26853750 | 0.35 | #REF! | 4833675 | 31687425 | 26853750 | 1627.5 | 2100
| 16 | Road & Paved areas - Road - Toe/ Retaining wall | Sqm | 16500 | 900 | 697.5 | 11508750 | 0.15 | #REF! | 2071575 | 13580325 | 11508750 | 697.5 | 900
| 17 | Road & Paved areas - Drain - Excavation work | RMT | 3000 | 1750 | 1356.25 | 4068750 | 0.25 | #REF! | 732375 | 4801125 | 4068750 | 1356.25 | 1750
| 18 | Road & Paved areas - Drain - PCC work | RMT | 3000 | 700 | 542.5 | 1627500 | 0.1 | #REF! | 292950 | 1920450 | 1627500 | 542.5 | 700
| 19 | Road & Paved areas - Drain - RCC Work | RMT | 3000 | 3500 | 2712.5 | 8137500 | 0.5 | #REF! | 1464750 | 9602250 | 8137500 | 2712.5 | 3500
| 20 | Road & Paved areas - Drain - Culvert/Hume Pipe | RMT | 3000 | 1050 | 813.75 | 2441250 | 0.15 | #REF! | 439425 | 2880675 | 2441250 | 813.75 | 1050
| GRAND TOTAL | [5 empty] | 150249250 |  |  | 27044865 | 177294115
Note:
| A. | The figures are notional and for billing purposes only. The scope mentioned in the Agreement shall remain unchanged. GST shall be paid on corresponding invoice value i.e., 77.5%.
| B. | Payment for work partially completed during the period shall be made on a pro-rata basis.
| C. | If any items/work is not included in the Billing schedule but is required for completion of the project within Battery limit as per contract , the same shall be completed by contractor without any additional price claimed to NMDC.
| D | The Billing schedule shall be revised (maximum twice) during contractual period, if required keeping the total contract price unaltered.
| E | As per clause 4.2 ( Page no- 6 of 238 ) under Commercial Contract Agreement , if actual quantities/ weights differ from the indicated , neither the contractor shall be entitled to get any additional price from the Employer or the Employer entitled to deduct any amount from the contract price due to variation in physical quantities/weight.
| F | As desired by NMDC, the quantity and rate break-up has been indicated, which may vary during execution as per detailed engineering, while keeping the total amount shown against each item fixed.
| G | Industrial building and Ancilliary facilties have been divided as per the list provided by NMDC through e-mail dt. 13.10.25

## PO Format D 14
Billing Schedule for Civil Engineering Works including all Supplies (Deposit 14)
Revision - R3
Design, Engineering, Manufacture, Supply, Storage & handling at site, Construction including enabling work, Erection, Testing, Commissioning and Demonstration of Performance Guarantee of New Crushing Plant & Downhill Conveyor System of Deposit 14 and 11C at Bailadila Iron Ore Mines, NMDC, Kirandul Complex (Chhattisgarh) on Turnkey basis.
Contract Agreement no. HO(Contracts)/NCP&DHCS/DEP-14&11C/945/310/227 dated 28.03.2025
Header Line Item | Service Item | Description | Unit | Approx. Qty. | Basic Rate (Rs) | 77.5% of Basic Rate | 77.5% of Basic value | % Progress | Progress Amount (Rs) | GST 18% | 77.5% Gross Value (Rs)
Civil Engineering Work Clause no. 1 of Table 4A (Deposit - 14 ) of Price Schedule for Civil Engineering Works including all Supplies of Appendix -1 of Contract Voulme of Contract Agreement between SKSL & NMDC.
INDUSTRIAL BUILDINGS / FACILITIES
110/270 |  | Civil Engineering Works 1Dep-14 with ITC
| 1 | Excavation for industrial buildings/ facilities | Cum | 512950 | 800 | 620 | 318029000 | 100% | 318029000 | 57245220 | 375274220 |  | E/W | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 542800000 | 420670000
| 2 | Slope Protection | Sqm | 5250 | 4000 | 3100 | 16275000 | 100% | 16275000 | 2929500 | 19204500
| 3 | Back Filling | Cum | 140000 | 100 | 77.5 | 10850000 | 100% | 10850000 | 1953000 | 12803000
| 4 | PCC for industrial buildings/ facilities | Cum | 3330 | 15000 | 11625 | 38711250 | 100% | 38711250 | 6968025 | 45679275
| 5 | RCC for all industrial buildings / facilities | Cum | 23960 | 27500 | 21312.5 | 510647500 | 1 | 510647500 | 91916550 | 602564050
|  | Total |  |  |  |  | 894512750 |  |  | 161012295 | 1055525045
120/280 | 1 | Reinforcement steel work - On supply of reinforcement steel -For all industrial building and facilities | MT | 2886 | 90000 | 69750 | 201298500 | 1 | 201298500 | 36233730 | 237532230 |  |  | 14000000
| 2 | Reinforcement steel work - On cutting, bending and fixing of reinforcement steel -For all industrial building and facilities | MT | 2886 | 30000 | 23250 | 67099500 | 1 | 67099500 | 12077910 | 79177410 |  |  | 14000000 | 445360000
| 3 | Brick work for all industrial buildings / facilities | cum | 800 | 12500 | 9687.5 | 7750000 | 1 | 7750000 | 1395000 | 9145000
| 4 | Doors, windows and ventilators for all industrial buildings / facilities | sqm | 510 | 9000 | 6975 | 3557250 | 1 | 3557250 | 640305 | 4197555
| 5 | Flooring Work for all industrial buildings / facilities | Sqm | 9257.5 | 2000 | 1550 | 14349125 | 1 | 14349125 | 2582842.5 | 16931967.5
| 6 | Plastrering Work for all industrial buildings / facilities | Sqm | 13400 | 800 | 620 | 8308000 | 1 | 8308000 | 1495440 | 9803440
| 7 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for all industrial buildings / facilities - Substation (D14-SS#1), | Lumpsum | 1 | 900000 | 697500 | 697500 | 1 | 697500 | 125550 | 823050
| 8 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for all industrial buildings / facilities - Substation (D14-SS#2) | Lumpsum | 1 | 900000 | 697500 | 697500 | 1 | 697500 | 125550 | 823050
| 9 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for all industrial buildings / facilities - Substation (D14-SS#3) | Lumpsum | 1 | 900000 | 697500 | 697500 | 1 | 697500 | 125550 | 823050
| 10 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for all industrial buildings / facilities - Substation (D14-SS#4) | Lumpsum | 1 | 900000 | 697500 | 697500 | 1 | 697500 | 125550 | 823050
| 11 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for all industrial buildings / facilities - Pump House | Lumpsum | 1 | 500000 | 387500 | 387500 | 1 | 387500 | 69750 | 457250
| 12 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for all industrial buildings / facilities - Reservoir | Lumpsum | 1 | 300000 | 232500 | 232500 | 1 | 232500 | 41850 | 274350
|  | Total |  |  |  |  | 305772375 | 12 | 305772375 | 55039027.5 | 360811402.5
|  | TOTAL FOR INDUSTRIAL BUILDINGS |  |  |  |  | 1200285125 | 12 | 305772375 | 216051322.5 | 1416336447.5
ANCILLIARY FACILITIES
130/290 |  | Civil Engineering Works 3 Dep 14 without ITC
| 1 | Excavation for ancilliary facilities. | Cum | 18300 | 800 | 620 | 11346000 | 1 | 11346000 | 2042280 | 13388280
| 2 | PCC for for ancilliary facilities. | Cum | 170 | 15000 | 11625 | 1976250 | 1 | 1976250 | 355725 | 2331975
| 3 | RCC for for ancilliary facilities. | Cum | 1040 | 27500 | 21312.5 | 22165000 | 1 | 22165000 | 3989700 | 26154700
| 4 | Reinforcement Steel Works - On supply of Reinforcement Steel - For for ancilliary facilities. | MT | 114 | 90000 | 69750 | 7951500 | 1 | 7951500 | 1431270 | 9382770
| 5 | Reinforcement Steel Works - On Cutting, Bending & Fixing of Reinforcement Steel - For for ancilliary facilities. | MT | 114 | 30000 | 23250 | 2650500 | 1 | 2650500 | 477090 | 3127590
| 6 | Brickwork for ancilliary facilities. | Cum | 400 | 12500 | 9687.5 | 3875000 | 1 | 3875000 | 697500 | 4572500
| 7 | Doors, Windows & Ventilation for for ancilliary facilities. | Sqm | 190 | 9000 | 6975 | 1325250 | 1 | 1325250 | 238545 | 1563795
| 8 | Flooring Work for for ancilliary facilities. | Sqm | 742.5 | 2000 | 1550 | 1150875 | 1 | 1150875 | 207157.5 | 1358032.5
| 9 | Plastering for ancilliary facilities. | Sqm | 7850 | 800 | 620 | 4867000 | 1 | 4867000 | 876060 | 5743060
| 10 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for ancilliary facilities - Rest Shelter and office building | Lumpsum | 1 | 1200000 | 930000 | 930000 | 1 | 930000 | 167400 | 1097400
| 11 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for ancilliary facilities - Plant executive building | Lumpsum | 1 | 1000000 | 775000 | 775000 | 1 | 775000 | 139500 | 914500
| 12 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for ancilliary facilities - Toilet Block | Lumpsum | 1 | 100000 | 77500 | 77500 | 1 | 77500 | 13950 | 91450
| 13 | Road & Paved areas - Haul Road - Earth work in formation and consolidation after testing | Sqm | 5000 | 1800 | 1395 | 6975000 | 1 | 6975000 | 1255500 | 8230500 | #REF! | #REF!
| 14 | Road & Paved areas - Haul Road - Base | Sqm | 5000 | 1800 | 1395 | 6975000 | 1 | 6975000 | 1255500 | 8230500 | #REF! | #REF!
| 15 | Road & Paved areas - Haul Road - Crushed Stone | Sqm | 5000 | 2400 | 1860 | 9300000 | 1 | 9300000 | 1674000 | 10974000 | #REF! | #REF!
| 16 | Road & Paved areas - Road - Earth work in formation | Sqm | 20000 | 1250 | 968.75 | 19375000 | 1 | 19375000 | 3487500 | 22862500 | #REF! | #REF!
| 17 | Road & Paved areas - Road - Base | Sqm | 20000 | 1250 | 968.75 | 19375000 | 1 | 19375000 | 3487500 | 22862500 | #REF! | #REF!
| 18 | Road & Paved areas - Road - Bitumen topping | Sqm | 20000 | 1750 | 1356.25 | 27125000 | 1 | 27125000 | 4882500 | 32007500 | #REF! | #REF!
| 19 | Road & Paved areas - Road - Toe/ Retaining wall | Sqm | 20000 | 750 | 581.25 | 11625000 | 1 | 11625000 | 2092500 | 13717500 | #REF! | #REF!
| 20 | Road and Paved areas - Drain- Excavation work | RMT | 2500 | 2000 | 1550 | 3875000 | 1 | 3875000 | 697500 | 4572500 | 3875000 | 1550 | 2000
| 21 | Road and Paved areas - Drain- PCC work | RMT | 2500 | 800 | 620 | 1550000 | 1 | 1550000 | 279000 | 1829000 | 1550000 | 620 | 800
| 22 | Road and Paved areas - Drain- RCC Work | RMT | 2500 | 4000 | 3100 | 7750000 | 1 | 7750000 | 1395000 | 9145000 | 7750000 | 3100 | 4000
| 23 | Road and Paved areas - Drain- Culvert/Hume Pipe | RMT | 2500 | 1200 | 930 | 2325000 | 1 | 2325000 | 418500 | 2743500 | 2325000 | 930 | 1200
| TOTAL FOR ANCILLIARY BUILDINGS | [5 empty] | 175339875 | #REF! | #REF! | 31561177.5 | 206901052.5
Note:
| A. | The figures are notional and for billing purposes only. The scope mentioned in the Agreement shall remain unchanged. GST shall be paid on corresponding invoice value i.e., 77.5%. | [10 empty] | PO
| B. | Payment for work partially completed during the period shall be made on a pro-rata basis.
| C. | If any items/work is not included in the Billing schedule but is required for completion of the project within Battery limit as per contract , the same shall be completed by contractor without any additional price claimed to NMDC.
| D | The Billing schedule shall be revised (maximum twice) during contractual period, if required keeping the total contract price unaltered.
| E | As per clause 4.2 ( Page no- 6 of 238 ) under Commercial Contract Agreement , if actual quantities/ weights differ from the indicated , neither the contractor shall be entitled to get any additional price from the Employer or the Employer entitled to deduct any amount from the contract price due to variation in physical quantities/weight.
| F | The total amount shown against each items are fixed, however as desired by NMDC, the quantity and rate break-up has been indicated, which may vary during execution as per detailed engineering.
| G | Industrial building and Ancilliary facilties have been divided as per the list provided by NMDC through e-mail dt. 13.10.25

## Dep14
Billing Schedule for Civil Engineering Works including all Supplies (Deposit 14)
Revision - R3
Design, Engineering, Manufacture, Supply, Storage & handling at site, Construction including enabling work, Erection, Testing, Commissioning and Demonstration of Performance Guarantee of New Crushing Plant & Downhill Conveyor System of Deposit 14 and 11C at Bailadila Iron Ore Mines, NMDC, Kirandul Complex (Chhattisgarh) on Turnkey basis.
Contract Agreement no. HO(Contracts)/NCP&DHCS/DEP-14&11C/945/310/227 dated 28.03.2025
Sl. No. | Description | Unit | Approx. Qty. | Basic Rate (Rs) | 77.5% of Basic Rate | 77.5% of Basic value | % Progress | Progress Amount (Rs) | GST 18% | 77.5% Gross Value (Rs)
1 | 2 | 3 | 4 | 5 | 6=(5 x 77.5%) | 7 = (4 x 6) | 8 | 9=7 x 8 | 8= (7 x 18%) | 9 =(8+7)
Civil Engineering Work Clause no. 1 of Table 4A (Deposit - 14 ) of Price Schedule for Civil Engineering Works including all Supplies of Appendix -1 of Contract Voulme of Contract Agreement between SKSL & NMDC.
INDUSTRIAL BUILDINGS / FACILITIES
C.1 | Excavation | [11 empty] | I/B |  | A/B |  | Total
C.1.2 | Excavation for industrial buildings/ facilities | Cum | 512950 | 800 | 620 | 318029000 | 100% | 318029000 | 57245220 | 375274220 |  | E/W | 0 | 407281720 | #REF! | #REF! | #REF! | #REF! | 542800000 | 420670000
C.1.24 | Slope Protection | Sqm | 5250 | 4000 | 3100 | 16275000 | 100% | 16275000 | 2929500 | 19204500
C.1.25 | Back Filling | Cum | 140000 | 100 | 77.5 | 10850000 | 100% | 10850000 | 1953000 | 12803000
Sub Total | [5 empty] | 345154000 |  | 345154000 | 62127720 | 407281720 |  | 407281720
C.2 | Plain Cemenrt Concrete
C.2.1 | PCC for industrial buildings/ facilities | Cum | 3330 | 15000 | 11625 | 38711250 | 100% | 38711250 | 6968025 | 45679275
C.3 | Reinforced Cement Concrete
C.3.1 | RCC for all industrial buildings / facilities | Cum | 23960 | 27500 | 21312.5 | 510647500 | 1 | 510647500 | 91916550 | 602564050
410360000
C.4 | Reinforcement Steel Works | [11 empty] | 21000000
C.4.1 | On supply of reinforcement steel -For all industrial building and facilities | MT | 2886 | 90000 | 69750 | 201298500 | 1 | 201298500 | 36233730 | 237532230 |  |  | 14000000
C.4.1.1 | On cutting, bending and fixing of reinforcement steel -For all industrial building and facilities | MT | 2886 | 30000 | 23250 | 67099500 | 1 | 67099500 | 12077910 | 79177410 |  |  | 445360000 | 445360000
Sub Total | [5 empty] | 268398000 |  | 268398000 | 48311640 | 316709640 |  |  |  | 0
[12 empty] | 21000000 |  | 0
C.5 | Brickwork | [10 empty] | 5250
C.5.1 | Brick work for all industrial buildings / facilities | cum | 800 | 12500 | 9687.5 | 7750000 | 1 | 7750000 | 1395000 | 9145000
C.6 | Doors, Windows & Ventilation
C.6.1 | Doors, windows and ventilators for all industrial buildings / facilities | sqm | 510 | 9000 | 6975 | 3557250 | 1 | 3557250 | 640305 | 4197555
C.7 | Flooring Work
C.7.1 | Flooring Work for all industrial buildings / facilities | Sqm | 9257.5 | 2000 | 1550 | 14349125 | 1 | 14349125 | 2582842.5 | 16931967.5
C.8 | Plastering
C.8.1.1 | Plastrering Work for all industrial buildings / facilities | Sqm | 13400 | 800 | 620 | 8308000 | 1 | 8308000 | 1495440 | 9803440
C.9 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for all industrial buildings / facilities
C.9.1.1 | Substation (D14-SS#1), | Lumpsum | 1 | 900000 | 697500 | 697500 | 1 | 697500 | 125550 | 823050
C.9.1.2 | Substation (D14-SS#2) | Lumpsum | 1 | 900000 | 697500 | 697500 | 1 | 697500 | 125550 | 823050
C.9.1.3 | Substation (D14-SS#3) | Lumpsum | 1 | 900000 | 697500 | 697500 | 1 | 697500 | 125550 | 823050
C.9.1.4 | Substation (D14-SS#4) | Lumpsum | 1 | 900000 | 697500 | 697500 | 1 | 697500 | 125550 | 823050
C.19.2 | Pump House | Lumpsum | 1 | 500000 | 387500 | 387500 | 1 | 387500 | 69750 | 457250
C.19.3 | Reservoir | Lumpsum | 1 | 300000 | 232500 | 232500 | 1 | 232500 | 41850 | 274350
Sub Total | [5 empty] | 3410000 |  | 3410000 | 613800 | 4023800
TOTAL FOR INDUSTRIAL BUILDINGS | [5 empty] | 1200285125 | 6 | 1200285125 | 216051322.5 | 1416336447.5
ANCILLIARY FACILITIES
C.10 | Excavation
C.10.1 | Excavation for ancilliary facilities. | Cum | 18300 | 800 | 620 | 11346000 | 100% | 11346000 | 2042280 | 13388280
C.11 | Plain Cemenrt Concrete
C.11.1 | PCC for for ancilliary facilities. | Cum | 170 | 15000 | 11625 | 1976250 | 100% | 1976250 | 355725 | 2331975
C.12 | Reinforced Cement Concrete
C.12.1 | RCC for for ancilliary facilities. | Cum | 1040 | 27500 | 21312.5 | 22165000 | 100% | 22165000 | 3989700 | 26154700
C.13 | Reinforcement Steel Works
C.13.1.1 | On supply of Reinforcement Steel - For for ancilliary facilities. | MT | 114 | 90000 | 69750 | 7951500 | 100% | 7951500 | 1431270 | 9382770 | 4185000 | #REF! | #REF!
C.13.1.3 | On Cutting, Bending & Fixing of Reinforcement Steel - For for ancilliary facilities. | MT | 114 | 30000 | 23250 | 2650500 | 100% | 2650500 | 477090 | 3127590 | 1116000 | #REF! | #REF!
Sub Total | [5 empty] | 10602000 |  | 10602000 | 1908360 | 12510360
C.14 | Brickwork | [10 empty] | #REF!
C.14.1 | Brickwork for ancilliary facilities. | Cum | 400 | 12500 | 9687.5 | 3875000 | 100% | 3875000 | 697500 | 4572500
C.15 | Doors, Windows & Ventilation
C.15.1 | Doors, Windows & Ventilation for for ancilliary facilities. | Sqm | 190 | 9000 | 6975 | 1325250 | 100% | 1325250 | 238545 | 1563795
C.16 | Flooring Work
C.16.1 | Flooring Work for for ancilliary facilities. | Sqm | 742.5 | 2000 | 1550 | 1150875 | 100% | 1150875 | 207157.5 | 1358032.5
C.17 | Plastering
C.17.1 | Plastering for ancilliary facilities. | Sqm | 7850 | 800 | 620 | 4867000 | 100% | 4867000 | 876060 | 5743060
C.18 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for ancilliary facilities
C.18.1 | Rest Shelter and office building | Lumpsum | 1 | 1200000 | 930000 | 930000 | 100% | 930000 | 167400 | 1097400
C.18.2 | Plant executive building | Lumpsum | 1 | 1000000 | 775000 | 775000 | 100% | 775000 | 139500 | 914500
C.18.3 | Toilet Block | Lumpsum | 1 | 100000 | 77500 | 77500 | 100% | 77500 | 13950 | 91450
Sub Total | [5 empty] | 1782500 |  | 1782500 | 320850 | 2103350
C.19 | Road & Paved areas
C.19.1 | Haul Road | Sqm | 5000 |  | 0 | 0
C.19.1.1 | Earth work in formation and consolidation after testing | Sqm | 5000 | 1800 | 1395 | 6975000 | 100% | 6975000 | 1255500 | 8230500 | 1395 | 1800
C.19.1.2 | Base | Sqm | 5000 | 1800 | 1395 | 6975000 | 100% | 6975000 | 1255500 | 8230500 | 1395 | 1800
C.19.1.3 | Crushed Stone | Sqm | 5000 | 2400 | 1860 | 9300000 | 100% | 9300000 | 1674000 | 10974000 | 1860 | 2400
C.19.2 | Road | Sqm | 20000 |  | 0 | 0 |  |  | 0 | 0
C.19.2.1 | Earth work in formation | Sqm | 20000 | 1250 | 968.75 | 19375000 | 100% | 19375000 | 3487500 | 22862500 | 968.75 | 1250
C.19.2.2 | Base | Sqm | 20000 | 1250 | 968.75 | 19375000 | 100% | 19375000 | 3487500 | 22862500 | 968.75 | 1250
C.19.2.3 | Bitumen topping | Sqm | 20000 | 1750 | 1356.25 | 27125000 | 100% | 27125000 | 4882500 | 32007500 | 1356.25 | 1750
C.19.2.4 | Toe/ Retaining wall | Sqm | 20000 | 750 | 581.25 | 11625000 | 100% | 11625000 | 2092500 | 13717500 | 581.25 | 750
C.19.3 | Drain | RMT | 2500 | [5 empty] | 0 | 0
C.19.3.1 | Excavation work | RMT | 2500 | 2000 | 1550 | 3875000 | 100% | 3875000 | 697500 | 4572500 | 3875000 | 1550 | 2000
C.19.3.2 | PCC work | RMT | 2500 | 800 | 620 | 1550000 | 100% | 1550000 | 279000 | 1829000 | 1550000 | 620 | 800
C.19.3.3 | RCC Work | RMT | 2500 | 4000 | 3100 | 7750000 | 100% | 7750000 | 1395000 | 9145000 | 7750000 | 3100 | 4000
C.19.3.4 | Culvert/Hume Pipe | RMT | 2500 | 1200 | 930 | 2325000 | 100% | 2325000 | 418500 | 2743500 | 2325000 | 930 | 1200
TOTAL FOR ANCILLIARY BUILDINGS | [5 empty] | 175339875 | 18 | 175339875 | 31561177.5 | 206901052.5
GRAND TOTAL | [5 empty] | 1375625000 |  | 1375625000 | 247612500 | 1623237500
Note:
A. | The figures are notional and for billing purposes only. The scope mentioned in the Agreement shall remain unchanged. GST shall be paid on corresponding invoice value i.e., 77.5%.
B. | Payment for work partially completed during the period shall be made on a pro-rata basis.
C. | If any items/work is not included in the Billing schedule but is required for completion of the project within Battery limit as per contract , the same shall be completed by contractor without any additional price claimed to NMDC.
D | The Billing schedule shall be revised (maximum twice) during contractual period, if required keeping the total contract price unaltered.
E | As per clause 4.2 ( Page no- 6 of 238 ) under Commercial Contract Agreement , if actual quantities/ weights differ from the indicated , neither the contractor shall be entitled to get any additional price from the Employer or the Employer entitled to deduct any amount from the contract price due to variation in physical quantities/weight.
F | The total amount shown against each items are fixed, however as desired by NMDC, the quantity and rate break-up has been indicated, which may vary during execution as per detailed engineering.
G | Industrial building and Ancilliary facilties have been divided as per the list provided by NMDC through e-mail dt. 13.10.25

## Dep11C
Billing Schedule for Civil Engineering Works including all Supplies (Deposit 11C)
Revision - R3
Design, Engineering, Manufacture, Supply, Storage & handling at site, Construction including enabling work, Erection, Testing, Commissioning and Demonstration of Performance Guarantee of New Crushing Plant & Downhill Conveyor System of Deposit 14 and 11C at Bailadila Iron Ore Mines, NMDC, Kirandul Complex (Chhattisgarh) on Turnkey basis.
Contract Agreement no. HO(Contracts)/NCP&DHCS/DEP-14&11C/945/310/227 dated 28.03.2025
Sl. No. | Description | Unit | Approx. Qty. | Basic Rate (Rs) | 77.5% of Basic Rate | 77.5% of Basic value | % Progress | Progress Amount (Rs) | GST 18% | 77.5% Gross Value (Rs)
1 | 2 | 3 | 4 | 5 | 6=(5 x 77.5%) | 7 = (4 x 6) | 8 | 9=7 x 8 | 8= (7 x 18%) | 9 =(7+8)
Civil Engineering Work Clause no. 1 of Table 4A (Deposit - 11C ) of Price Schedule for Civil Engineering Works including all Supplies of Appendix -1 of Contract Voulme of Contract Agreement between SKSL & NMDC.
INDUSTRIAL BUILDINGS/ FACILITIES
D.1 | Excavation
D.1.1 | Excavation for industrial buildings/ facilities | Cum | 435125 | 800 | 620 | 269777500 | 1 | 269777500 | 48559950 | 318337450 | 348100000
D.1.18 | Slope Protection | Lump Sum | 1 | 15000000 | 11625000 | 11625000 | 1 | 11625000 | 2092500 | 13717500 | 15000000
D.1.19 | Back Filling | Cum | 117000 | 100 | 77.5 | 9067500 | 1 | 9067500 | 1632150 | 10699650 | 11700000
Sub total |  |  | 435125 |  |  | 290470000 |  | 290470000 | 52284600 | 342754600 | 374800000 | 374800000
0
D.2 | Plain Cemenrt Concrete | [10 empty] | 0
D.2.1 | PCC for industrial buildings/ facilities | Cum | 2830 | 15000 | 11625 | 32898750 | 1 | 32898750 | 5921775 | 38820525
D.3 | Reinforced Cement Concrete
D.3.1.1 | RCC for industrial buildings/ facilities | cum | 22960 | 27500 | 21312.5 | 489335000 | 1 | 489335000 | 88080300 | 577415300
D.4 | Reinforcement Steel Works
D.4.1.1 | On supply of reinforcement steel -For industrial buildings/ facilities | MT | 2686 | 90000 | 69750 | 187348500 | 0.75 | #REF! | 33722730 | 221071230
D.4.1.3 | On cutting, bending and fixing of reinforcement steel - For industrial buildings/ facilities | MT | 2686 | 30000 | 23250 | 62449500 | 0.2 | #REF! | 11240910 | 73690410
| Sub total |  |  |  |  | 249798000 | 0.95 |  | 44963640 | 294761640 | 0
D.5 | Brickwork
D.5.1 | Substations
D.5.1.1 | Brickwork for industrial buildings/ facilities | Cum | 540 | 13000 | 10075 | 5440500 | 1 | 5440500 | 979290 | 6419790
D.6 | Doors, Windows & Ventilation
D.6.1 | Substations
D.6.1.1 | Door, Windows and Ventilators for industrial buildings/ facilities | Sqm | 330 | 10000 | 7750 | 2557500 | 1 | 2557500 | 460350 | 3017850
D.7 | Flooring Work
D.7.1 | Flooring Work for industrial buildings/ facilities | Sqm | 7375 | 2000 | 1550 | 11431250 | 1 | 11431250 | 2057625 | 13488875
D.8 | Plastering
D.8.1.1 | Plastering Work for industrial buildings/ facilities | Sqm | 9300 | 800 | 620 | 5766000 | 1 | 5766000 | 1037880 | 6803880
C.9 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for industrial buildings/ facilities
C.9.1.1 | Substation (D11C-SS#1), | Lumpsum | 1 | 900000 | 697500 | 697500 | 1 | 697500 | 125550 | 823050
C.9.1.2 | Substation (D11C-SS#2) | Lumpsum | 1 | 900000 | 697500 | 697500 | 1 | 697500 | 125550 | 823050
C.9.2 | Reservoir | Lumpsum | 1 | 350000 | 271250 | 271250 | 1 | 271250 | 48825 | 320075
C.9.3 | Pump House | Lumpsum | 1 | 500000 | 387500 | 387500 | 1 | 387500 | 69750 | 457250
Sub total | [5 empty] | 2053750 |  | 2053750 | 369675 | 2423425
TOTAL FOR INDUSTRIAL BUILDINGS | [5 empty] | 1089750750 | 6.95 | 839952750 | 196155135 | 1285905885
ANCILLIARY FACILITIES
Excavation
D.10.1 | Excavation for ancilliary facilities. | Cum | 11500 | 800 | 620 | 7130000 | 1 | 7130000 | 1283400 | 8413400
Plain Cemenrt Concrete
D.11.1 | PCC for ancilliary facilities. | Cum | 170 | 15000 | 11625 | 1976250 | 1 | 1976250 | 355725 | 2331975
Reinforced Cement Concrete
D.12.1 | RCC for ancilliary facilities. | Cum | 1040 | 27500 | 21312.5 | 22165000 | 1 | 22165000 | 3989700 | 26154700
D.13 | Reinforcement Steel Works
D.13.1.1 | On supply of Reinforcement Steel - For for ancilliary facilities. | MT | 114 | 90000 | 69750 | 7951500 | 0.75 | #REF! | 1431270 | 9382770 | 4185000 |  | 5400000 | 47368.4211
D.13.1.3 | On Cutting, Bending & Fixing of Reinforcement Steel - For for ancilliary facilities. | MT | 114 | 30000 | 23250 | 2650500 | 0.2 | #REF! | 477090 | 3127590 | 1116000 |  | 1440000 | 12631.5789
Sub total |  |  | 228 |  |  | 10602000 |  | #REF! | 1908360 | 12510360
D.14 | Brickwork
D.14.1 | Brickwork for ancilliary facilities. | Cum | 460 | 13000 | 10075 | 4634500 | 1 | 4634500 | 834210 | 5468710
D.15 | Doors, Windows & Ventilation
D.15.1 | Doors, Windows and Ventilators- for ancilliary facilities. | Sqm | 310 | 10000 | 7750 | 2402500 | 1 | 2402500 | 432450 | 2834950
D.16 | Flooring Work
D.16.1 | Flooring work for ancilliary facilities. | Sqm | 625 | 2000 | 1550 | 968750 | 1 | 968750 | 174375 | 1143125
D.17 | Plastering
D.17.1 | Plastering Work for ancilliary facilities. | Sqm | 8950 | 800 | 620 | 5549000 | 1 | 5549000 | 998820 | 6547820
D.18 | Roof Treatment, Painting, Plumbing, Jigs & Fixtures including all finishing items for ancilliary facilities.
D.18.1 | Rest Shelter and office building | Lumpsum | 1 | 1200000 | 930000 | 930000 | 1 | 930000 | 167400 | 1097400
D.18.2 | Plant executive building | Lumpsum | 1 | 1000000 | 775000 | 775000 | 1 | 775000 | 139500 | 914500
D.18.3 | Toilet Block | Lumpsum | 1 | 150000 | 116250 | 116250 | 1 | 116250 | 20925 | 137175
Sub total | [5 empty] | 1821250 |  | 1821250 | 327825 | 2149075
D.19 | Road & Paved areas
D.19.1 | Road | Sqm | 16500 |  | 0 | 0
D.19.1.1 | Earth work in formation | Sqm | 16500 | 1500 | 1162.5 | 19181250 | 0.25 | 0 | 3452625 | 22633875 | 19181250 |  | 1162.5 | 1500
D.19.1.2 | Base | Sqm | 16500 | 1500 | 1162.5 | 19181250 | 0.25 | 0 | 3452625 | 22633875 | 19181250 |  | 1162.5 | 1500
D.19.1.3 | Bitumen topping | Sqm | 16500 | 2100 | 1627.5 | 26853750 | 0.35 | 0 | 4833675 | 31687425 | 26853750 |  | 1627.5 | 2100
D.19.1.4 | Toe/ Retaining wall | Sqm | 16500 | 900 | 697.5 | 11508750 | 0.15 | 0 | 2071575 | 13580325 | 11508750 |  | 697.5 | 900
D.19.2 | Drain | RMT | 3000 |  | 0 | 0 |  |  | 0 | 0
D.19.2.1 | Excavation work | RMT | 3000 | 1750 | 1356.25 | 4068750 | 0.25 | 0 | 732375 | 4801125 | 4068750 |  | 1356.25 | 1750
D.19.2.2 | PCC work | RMT | 3000 | 700 | 542.5 | 1627500 | 0.1 | 0 | 292950 | 1920450 | 1627500 |  | 542.5 | 700
D.19.2.3 | RCC Work | RMT | 3000 | 3500 | 2712.5 | 8137500 | 0.5 | 0 | 1464750 | 9602250 | 8137500 |  | 2712.5 | 3500
D.19.2.4 | Culvert/Hume Pipe | RMT | 3000 | 1050 | 813.75 | 2441250 | 0.15 | 0 | 439425 | 2880675 | 2441250 |  | 813.75 | 1050
Sub total | [5 empty] | 93000000 |  | 0 | 16740000 | 109740000
TOTAL FOR ANCILLIARY FACILITIES | [5 empty] | 150249250 | 7 | #REF! | 27044865 | 177294115
GRAND TOTAL | [5 empty] | 1240000000 |  | #REF! | 223200000 | 1463200000
Note:
A. | The figures are notional and for billing purposes only. The scope mentioned in the Agreement shall remain unchanged. GST shall be paid on corresponding invoice value i.e., 77.5%.
B. | Payment for work partially completed during the period shall be made on a pro-rata basis.
C. | If any items/work is not included in the Billing schedule but is required for completion of the project within Battery limit as per contract , the same shall be completed by contractor without any additional price claimed to NMDC.
D | The Billing schedule shall be revised (maximum twice) during contractual period, if required keeping the total contract price unaltered.
E | As per clause 4.2 ( Page no- 6 of 238 ) under Commercial Contract Agreement , if actual quantities/ weights differ from the indicated , neither the contractor shall be entitled to get any additional price from the Employer or the Employer entitled to deduct any amount from the contract price due to variation in physical quantities/weight.
F | As desired by NMDC, the quantity and rate break-up has been indicated, which may vary during execution as per detailed engineering, while keeping the total amount shown against each item fixed.
G | Industrial building and Ancilliary facilties have been divided as per the list provided by NMDC through e-mail dt. 13.10.25