## vwmasterrfi
projectcode | rfino | descriptionofwork | chainagefrom | chainageto | side | structure | componentname | striplayername | contractorcode | contractorname | ae_group | ae_name | posteddatetime | rficreator | inspectiondatetime | rfiinspector | inspecteddatetime | inspectioncomment | approveddatetime | rfiapprover | approved_comments | longitude | latitude | inspectionstatus | filterstatus | length | name_of_road
114:NSK-II (20A) | RFI/114:NSK-II (20A)/535 | Checking Shuttering and pouring concrete of PCC for Drain | 134600 | 134700 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-19 16:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-20 11:30 | Kishori Lal | 2025-05-21 17:34 | 134+635 to 134+700 RHS | 2025-05-21 18:27 | Brajesh Upadhyay | work has been done | 74.7578 | 20.4419 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/534 | Checking of Layout Marking & Excavation for Drain | 135235 | 135260 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-19 16:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-20 10:00 | Kishori Lal | 2025-05-21 17:05 | Work Done. | 2025-05-21 17:06 | Brajesh Upadhyay | Work has been done | 74.7595 | 20.4472 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/550 | Checking For Layout Marking ,Level & Excavation Of Drain | 135150 | 135200 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-25 18:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-26 09:30 | Saurabh SE | 2025-05-26 12:27 | Work done without level checking |  |  |  | 74.7592 | 20.4462 | Inspected | Inspected - Rejected - Work Not Done | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/506 | Checking Level and FDD test for Subgrade Top | 135230 | 135750 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 09:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-13 13:00 | Rushikesh Gunjal | 2025-05-21 12:21 | Checked and found ok | 2025-05-21 14:08 | Brajesh Upadhyay | work has been done | 74.7548 | 20.4148 | Inspected | RFI Approved | 520 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/509 | Checking Level and FDD test for GSB Top | 134500 | 135150 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 09:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-13 15:00 | Rushikesh Gunjal | 2025-05-21 11:51 | Ok | 2025-05-21 14:05 | Brajesh Upadhyay | work has been done | 74.7547 | 20.4143 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/487 | Checking Level and FDD test for GSB Top | 133500 | 134250 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 16:00 | Rushikesh Gunjal | 2025-05-21 12:10 | Checked and found ok | 2025-05-21 17:01 | Brajesh Upadhyay | Work has been done | 74.7545 | 20.4149 | Inspected | RFI Approved | 750 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/498 | Checking of Laying, Level and FDD of DLC top layer | 129770 | 130250 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 10:30 | Rushikesh Gunjal | 2025-05-23 16:14 | Checked and found ok | 2025-05-23 21:12 | Brajesh Upadhyay | work has been done | 74.7386 | 20.3913 | Inspected | RFI Approved | 480 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/481 | Checking Level and FDD test for GSB Top | 132950 | 133950 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 10:00 | Rushikesh Gunjal | 2025-05-21 11:54 | Checked and found ok | 2025-05-21 17:05 | Brajesh Upadhyay | Work has been done | 74.7547 | 20.4143 | Inspected | RFI Approved | 1000 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/538 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135260 | 135340 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-21 12:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-22 17:12 | Kishori Lal | 2025-05-21 17:09 | Not Ready. |  |  |  | 74.7594 | 20.447 | Inspected | Inspected - Rejected - Work Not Done | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/536 | Checking Reinforcement, shuttering and pouring concrete for Wall final lift of Retaining Wall | 132910 | 132960 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-21 11:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-22 | Kishori Lal | 2025-05-21 18:19 | Work done. | 2025-05-21 18:23 | Brajesh Upadhyay | work has been done | 74.7582 | 20.4264 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/537 | Checking For Shuttering & Concrete Pouring Of HPC Head Wall First Lift | 136078 | 136078 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-21 12:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-22 09:06 | Kishori Lal | 2025-05-21 18:41 | Work done. | 2025-05-21 18:49 | Brajesh Upadhyay | Work has been done | 74.7623 | 20.4538 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/398 | Checking Shuttering and pouring of PCC for Retaining Wall | 140450 | 141000 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 13:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 17:34 | Rushikesh Gunjal | 2025-05-21 10:49 | Ok | 2025-05-21 17:07 | Brajesh Upadhyay | Work has been done | 74.7813 | 20.4892 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/430 | Checking Reinforcement, shuttering and pouring concrete for Raft of Retaining Wall | 140450 | 141000 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 13:30 | Rushikesh Gunjal | 2025-05-21 15:07 | Work not done |  |  |  | 74.7811 | 20.4886 | Inspected | Inspected - Rejected - Work Not Done | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/531 | Checking Shuttering and laying of PCC for head wall & Below pipe PCC | 136078 | 136078 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-19 16:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-20 09:30 | Kishori Lal | 2025-05-21 16:47 | Work done. | 2025-05-21 17:00 | Brajesh Upadhyay | Work has been done | 74.7623 | 20.4539 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1665 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 120400 | 121020 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 17:35 | Rushikesh Gunjal | 2025-10-28 12:03 | Work already done | 2025-10-28 18:29 | Brajesh Upadhyay | work has been done | 74.6994 | 20.348 | Inspected | RFI Approved | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1684 | Checking Of Laying DLC Top | 123450 | 123700 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 16:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:52 | Rushikesh Gunjal | 2025-10-28 12:37 | Work was already done | 2025-10-28 18:31 | Brajesh Upadhyay | work has been done | 74.707 | 20.3607 | Inspected | RFI Approved | 250 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1683 | Checking Of Level & FDD Test For GSB Top | 123791 | 123870 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 16:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:51 | Rushikesh Gunjal | 2025-10-28 12:38 | Work was already done | 2025-10-28 18:31 | Brajesh Upadhyay | work has been done | 74.707 | 20.3607 | Inspected | RFI Approved | 79 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1672 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 129400 | 129693 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 12:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 12:46 | Rushikesh Gunjal | 2025-10-28 15:49 | Work already done | 2025-10-28 18:33 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 293 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1589 | Checking Of Laying DLC Top | 121010 | 121500 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:44 | Rushikesh Gunjal | 2025-10-28 11:54 | Work was already done | 2025-10-28 18:36 | Brajesh Upadhyay | work has been done | 74.6984 | 20.3413 | Inspected | RFI Approved | 490 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1578 | Checking Of Level & FDD Test For GSB Top | 122280 | 123140 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:23 | Rushikesh Gunjal | 2025-10-28 12:19 | Work was already done | 2025-10-28 18:37 | Brajesh Upadhyay | work has been done | 74.7026 | 20.3532 | Inspected | RFI Approved | 860 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1577 | Checking Of Level & FDD Test For GSB Top | 121510 | 122280 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:22 | Rushikesh Gunjal | 2025-10-28 12:05 | Work already done | 2025-10-28 18:37 | Brajesh Upadhyay | work has been done | 74.6994 | 20.348 | Inspected | RFI Approved | 770 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1542 | Checking Of Level & FDD Test For GSB Top | 127000 | 127850 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 14:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 14:15 | Rushikesh Gunjal | 2025-10-28 15:26 | Work was already done | 2025-10-28 18:39 | Brajesh Upadhyay | work has been done | 74.7327 | 20.3872 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1541 | Checking Of Level & FDD Test For GSB Top | 126600 | 127000 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 14:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 14:15 | Rushikesh Gunjal | 2025-10-28 15:25 | Work was already done | 2025-10-28 18:39 | Brajesh Upadhyay | work has been done | 74.7327 | 20.3872 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1540 | Checking Of Level & FDD Test For GSB Top | 126080 | 126600 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 14:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 14:13 | Rushikesh Gunjal | 2025-10-28 16:03 | Work was already done | 2025-10-28 18:40 | Brajesh Upadhyay | work has been done | 74.7248 | 20.3817 | Inspected | RFI Approved | 520 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1539 | Checking Of Level & FDD Test For GSB Top | 125500 | 126080 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 14:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 14:12 | Rushikesh Gunjal | 2025-10-28 16:03 | Work was already done | 2025-10-28 18:40 | Brajesh Upadhyay | work has been done | 74.7247 | 20.3817 | Inspected | RFI Approved | 580 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1535 | Checking Of Level & FDD Test For GSB Top | 122000 | 122500 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 13:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:59 | Rushikesh Gunjal | 2025-10-28 12:20 | Work was already done | 2025-10-28 18:40 | Brajesh Upadhyay | work has been done | 74.7026 | 20.3532 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1007 | Checking Of Utility Pipe Laying | 122320 | 122320 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-31 17:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-01 12:15 | Rushikesh Gunjal | 2025-08-01 16:02 | Check and found No GSB has been put down the pipe. Pipe joint not filled. |  |  |  | 74.7016 | 20.3512 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1473 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 126900 | 127300 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:33 | Rushikesh Gunjal | 2025-10-28 12:59 | Work was already done | 2025-10-28 18:47 | Brajesh Upadhyay | work has been done | 74.721 | 20.3767 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1442 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 123850 | 124700 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:01 | Rushikesh Gunjal | 2025-10-28 12:43 | Work was already done | 2025-10-28 18:55 | Brajesh Upadhyay | work has been done | 74.7071 | 20.3607 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1439 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 122800 | 123000 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 10:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 10:57 | Rushikesh Gunjal | 2025-10-28 12:29 | Work was already done | 2025-10-28 18:55 | Brajesh Upadhyay | work has been done | 74.7034 | 20.3548 | Inspected | RFI Approved | 200 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1437 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 121600 | 122000 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 10:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 10:55 | Rushikesh Gunjal | 2025-10-28 12:01 | Work was already done | 2025-10-28 18:55 | Brajesh Upadhyay | work has been done | 74.6994 | 20.348 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/539 | Checking For HPC Pipe Laying | 136078 | 136078 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-22 17:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-23 08:40 | Rushikesh Gunjal | 2025-05-23 17:36 | Checked and found no grouting on the inside |  |  |  | 74.7623 | 20.4539 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/540 | Checking For Shuttering & Concrete Pouring Of HPC Head Wall Second Lift | 136078 | 136078 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-22 17:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-23 17:00 | Rushikesh Gunjal | 2025-05-23 17:30 | Checked and found honeycombing |  |  |  | 74.7623 | 20.4539 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/541 | Checking For Reinforcement,Shuttering & Concrete Pouring Of Retaining Wall Raft | 140600 | 140650 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-22 17:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-23 16:00 | Rushikesh Gunjal | 2025-05-24 12:26 | Work not Done |  |  |  | 74.7812 | 20.4895 | Inspected | Inspected - Rejected - Work Not Done | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1632 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134650 | 134700 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 16:00 | Rushikesh Gunjal | 2025-10-27 16:04 | Work already done | 2025-10-28 08:16 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4423 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1631 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135100 | 135140 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:59 | Rushikesh Gunjal | 2025-10-27 16:03 | Work already done | 2025-10-28 08:24 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4425 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1630 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135090 | 135150 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:58 | Rushikesh Gunjal | 2025-10-27 16:02 | Work already done | 2025-10-28 08:24 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4425 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1617 | Checking Reinforcement, shuttering and pouring concrete for Final Lift Of Retaining Wall | 140800 | 140850 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:42 | Rushikesh Gunjal | 2025-10-27 15:13 | Work already done | 2025-10-28 08:25 | Brajesh Upadhyay | work has been done | 74.7812 | 20.489 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/548 | Checking Shuttering and pouring concrete of raft for Drain | 134635 | 134700 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-25 18:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-26 09:15 | Kishori Lal | 2025-05-26 12:31 | Work Execute without checking. |  |  |  | 74.7584 | 20.4416 | Inspected | Inspected - Rejected - Work Not Done | 65 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/551 | Checking pipe laying and joint filling & Checking shuttering and pouring concrete for Head Wall Final lif | 137018 | 137018 | RHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-25 18:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-26 10:30 | Kishori Lal | 2025-05-26 12:07 | Already work done without checking. |  |  |  | 74.766 | 20.4616 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/549 | Checking Shuttering and pouring concrete of PCC for Drain | 135235 | 135260 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-25 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-26 13:15 | Kishori Lal | 2025-05-26 12:18 | Work Execute without checking. |  |  |  | 74.7594 | 20.4468 | Inspected | Inspected - Rejected - Work Not Done | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/592 | Checking Pcc Below Pipe & Head Wall 1st Lift | 120723 | 120723 | LHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-31 19:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-01 11:00 | Kishori Lal | 2025-06-02 18:33 | Work done. | 2025-06-03 08:02 | Brajesh Upadhyay | work has been done | 74.6963 | 20.3388 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1006 | Checking Of Laying Of Utility Pipe | 121440 | 121440 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-31 17:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-01 10:00 | Rushikesh Gunjal | 2025-08-01 16:08 | Check and found No GSB has been put down the pipe. Pipe joint not filled.& open only in one side |  |  |  | 74.6989 | 20.3439 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/552 | Checking For Reinforcement ,Shuttering & Pouring Concrete Of Retaining Wall Raft | 140600 | 140640 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-26 18:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-28 12:15 | Rushikesh Gunjal | 2025-05-27 11:31 | Work not Done |  |  |  | 74.7813 | 20.4895 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/553 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135250 | 135340 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-27 08:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-27 11:30 | Rushikesh Gunjal | 2025-05-27 12:33 | Work not done Steel spacing is not maintained |  |  |  | 74.7594 | 20.4471 | Inspected | Inspected - Rejected - Work Not Done | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/554 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135230 | 135250 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-27 08:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-27 10:00 | Rushikesh Gunjal | 2025-05-27 12:27 | Work not completed |  |  |  | 74.7593 | 20.4468 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/555 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134720 | 134750 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-27 08:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-27 11:45 | Rushikesh Gunjal | 2025-05-27 12:40 | Steel alignment is not proper |  |  |  | 74.758 | 20.4424 | Inspected | Inspected - Fail | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/557 | Checking Layout Marking & Excavation For Drain | 134710 | 134730 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-27 08:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-27 11:35 | Rushikesh Gunjal | 2025-05-27 12:43 | Not done |  |  |  | 74.758 | 20.4424 | Inspected | Inspected - Fail | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/558 | Checking Layout Marking & Excavation For Drain | 134980 | 135080 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-27 09:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-27 11:10 | Rushikesh Gunjal | 2025-05-27 12:35 | Not Done |  |  |  | 74.7585 | 20.4446 | Inspected | Inspected - Rejected - Work Not Done | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1991 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120380 | 120400 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-26 15:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-27 10:00 | Rushikesh Gunjal | 2025-12-27 10:22 | Work not done |  |  |  | 74.6944 | 20.3357 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/556 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134730 | 134740 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-27 08:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-27 11:30 | Rushikesh Gunjal | 2025-05-27 12:45 | Already Work was done without inspected |  |  |  | 74.758 | 20.4422 | Inspected | Inspected - Fail | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/399 | Checking of Laying of PQC | 123150 | 123980 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 13:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 23:35 | Rushikesh Gunjal | 2025-05-23 12:38 | Checked and found ok | 2025-06-25 11:57 | Sanjay Sharma | work has been done | 74.7097 | 20.3668 | Inspected | RFI Approved | 830 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/594 | Checking of Layout Marking & Excavation for HPC | 133628 | 133628 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-31 21:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-01 10:15 | Saurabh SE | 2025-06-02 15:10 | Work done without level checking |  |  |  | 74.7585 | 20.4325 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/595 | Checking Shuttering and laying of PCC for head wall & Below pipe | 138728 | 138728 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-31 21:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-01 11:20 | Kishori Lal | 2025-06-02 12:31 | Not Done. |  |  |  | 74.7725 | 20.4757 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/559 | Checking Reinforcement, shuttering and pouring concrete for Retaing Wall Raft | 140640 | 140670 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-27 17:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-28 17:30 | Rushikesh Gunjal | 2025-05-29 10:14 | Not ok |  |  |  | 74.7814 | 20.4897 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/542 | Checking For Shuttering & Concrete Pouring Of HPC Head Wall Final Lift | 136078 | 136078 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-23 17:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-24 09:36 | Rushikesh Gunjal | 2025-05-24 13:06 | Ok | 2025-05-24 16:49 | Brajesh Upadhyay | done | 74.7623 | 20.4539 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/543 | Checking pipe laying and joint filling & Checking shuttering and pouring concrete for Head Wall second lift | 137018 | 137018 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-23 17:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-24 17:39 | Rushikesh Gunjal | 2025-05-24 12:48 | The pipe joint is not filled and the work is only done on the right side. |  |  |  | 74.7658 | 20.4616 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/544 | Checking Shuttering and laying of PCC for head wall & Below pipe | 138983 | 138983 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-23 17:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-24 17:00 | Rushikesh Gunjal | 2025-05-24 12:33 | Work not Completed |  |  |  | 74.7736 | 20.4777 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/545 | Checking Shuttering and pouring concrete of PCC for retaining wall | 140700 | 140800 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-23 17:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-24 15:30 | Rushikesh Gunjal | 2025-05-24 12:17 | Work not Done |  |  |  | 74.7816 | 20.4903 | Inspected | Inspected - Rejected - Work Not Done | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/546 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135260 | 135340 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-23 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-24 17:50 | Rushikesh Gunjal | 2025-05-24 13:15 | Checked and found ok | 2025-05-24 16:47 | Brajesh Upadhyay | work has been done | 74.7595 | 20.4472 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/547 | Checking Reinforcement,Shuttering and pouring concrete of Raft for Drain | 134600 | 134700 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-23 17:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-24 09:45 | Rushikesh Gunjal | 2025-05-24 13:22 | In Mention CH. 60% work has already been done and has not been inspected. In Mentioned CH. Total Work is not Done |  |  |  | 74.758 | 20.4422 | Inspected | Inspected - Fail | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/600 | Checking Reinforcement , Shuttering & Pouring Concrete For Drain Wall | 134710 | 134730 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-31 21:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-01 10:48 | Kishori Lal | 2025-06-02 14:45 | Not Ready. |  |  |  | 74.758 | 20.4423 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/511 | Checking of Laying, Level and FDD of DLC top layer | 130250 | 130870 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 09:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-13 12:18 | Rushikesh Gunjal | 2025-05-24 13:39 | Work not Done |  |  |  | 74.7501 | 20.4023 | Inspected | Inspected - Rejected - Work Not Done | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1996 | Checking Of Reinforcement , shuttering & Pouring Concrete For Toe Wall 1st Lift | 129620 | 129675 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-26 16:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-27 16:00 | Kishori Lal | 2025-12-29 11:35 | Work done. | 2026-01-01 14:09 | Brajesh Upadhyay | work has been done | 74.7481 | 20.3987 | Inspected | RFI Approved | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/560 | Checking Layout Marking & Excavation & Pcc For Drain | 135220 | 135260 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 08:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-29 11:00 | Rushikesh Gunjal | 2025-05-29 17:11 | Ok | 2025-05-30 07:53 | Brajesh Upadhyay | work done | 74.7594 | 20.4469 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/561 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134710 | 134720 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 08:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-29 11:55 | Rushikesh Gunjal | 2025-05-29 16:52 | Ok | 2025-05-30 07:55 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4423 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/562 | Checking Layout Marking & Excavation For Drain | 134520 | 134600 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 08:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-29 16:00 | Rushikesh Gunjal | 2025-05-29 16:22 | The excavation is not in line and level. |  |  |  | 74.758 | 20.4409 | Inspected | Inspected - Fail | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/564 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135230 | 135250 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 10:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-29 12:20 | Rushikesh Gunjal | 2025-05-30 11:47 | Not ok |  |  |  | 74.7592 | 20.4467 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/565 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134720 | 134750 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 10:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-29 12:30 | Rushikesh Gunjal | 2025-05-30 12:03 | Not completed |  |  |  | 74.7579 | 20.4425 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/566 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134730 | 134740 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 10:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-29 12:35 | Rushikesh Gunjal | 2025-05-30 12:05 | Not ok |  |  |  | 74.758 | 20.4424 | Inspected | Inspected - Rejected - Work Not Done | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/568 | Checking Shuttering and pouring concrete of PCC for Drain | 134980 | 135080 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 10:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-29 12:45 | Rushikesh Gunjal | 2025-05-30 11:49 | Work not done |  |  |  | 74.7585 | 20.4446 | Inspected | Inspected - Rejected - Work Not Done | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/569 | Checking Reinforcement,Shuttering and pouring concrete for Drain Slab | 134730 | 134740 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 10:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-29 15:45 | Rushikesh Gunjal | 2025-05-30 12:01 | Reinforcement is not in alignment |  |  |  | 74.7579 | 20.4425 | Inspected | Inspected - Fail | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/570 | Checking Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 134730 | 134750 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 10:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-29 17:50 | Rushikesh Gunjal | 2025-05-30 11:58 | Not completed |  |  |  | 74.758 | 20.4425 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/571 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134710 | 134720 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 10:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-29 17:00 | Rushikesh Gunjal | 2025-05-30 11:56 | Reinforcement is not in alignment |  |  |  | 74.758 | 20.4425 | Inspected | Inspected - Fail | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1036 | Checking Of Utility Pipe Laying | 134460 | 134460 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-18 17:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-19 09:30 | Saurabh SE | 2025-08-19 15:37 | Work done | 2025-08-19 20:57 | Brajesh Upadhyay | work has been done | 74.758 | 20.44 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/602 | Checking of Layout Marking , Excavation & pcc for Drain | 135090 | 135170 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-31 22:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-01 16:00 | Saurabh SE | 2025-06-02 12:47 | PCC is not done |  |  |  | 74.7588 | 20.4456 | Inspected | Inspected - Rejected - Work Not Done | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/601 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135170 | 135210 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-31 21:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-01 11:55 | Kishori Lal | 2025-06-02 13:29 | Not Ready. |  |  |  | 74.7592 | 20.4465 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/598 | Checking Shuttering and laying of PCC for Minor Bridge | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-31 21:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-02 12:35 | Kishori Lal | 2025-06-02 15:31 | Work done. | 2025-06-03 07:45 | Brajesh Upadhyay | work has been done | 74.7482 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/597 | Checking of Layout Marking & Excavation for HPC | 138780 | 138780 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-31 21:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-01 12:05 | Saurabh SE | 2025-06-02 12:24 | Without checking work is done |  |  |  | 74.7727 | 20.4762 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/593 | Checking Concrete Of Pcc Below Pipe & Head Wall 1st Lift | 120737 | 120737 | LHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-31 19:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-01 11:00 | Kishori Lal | 2025-06-02 18:21 | Not proper dimensions and alignment. |  |  |  | 74.6965 | 20.339 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/596 | Checking Shuttering & Pouring Concrete Of PCC For HPC Below Pipe | 138983 | 138983 | RHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-31 21:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-01 10:25 | Kishori Lal | 2025-06-02 12:14 | Work done. | 2025-06-03 07:40 | Brajesh Upadhyay | work has beeen done | 74.7737 | 20.4776 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/584 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134730 | 134740 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 21:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 12:30 | Kishori Lal | 2025-06-02 14:33 | Work done. | 2025-06-03 07:51 | Brajesh Upadhyay | work has been done | 74.7578 | 20.4419 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/639 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135190 | 135210 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 16:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 12:30 | Rushikesh Gunjal | 2025-06-07 11:45 | Ok | 2025-06-08 08:55 | Brajesh Upadhyay | work has been done | 74.7592 | 20.4464 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/640 | Checking Shuttering and pouring concrete of Head Wall Final Lift | 137018 | 137018 | LHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 16:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 14:30 | Kishori Lal | 2025-06-09 16:27 | Work done without checking. |  |  |  | 74.7656 | 20.4617 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/573 | Checking Reinforcement,Shuttering & Pouring Concrete For Drain Wall | 134710 | 134720 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 21:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 12:30 | Rushikesh Gunjal | 2025-05-30 11:54 | Repeat RFI |  |  |  | 74.758 | 20.4424 | Inspected | Inspected - Rejected - Work Not Done | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/572 | Checking Reinforcement, Shuttering & Pouring Concrete For Drain Raft | 135220 | 135260 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 21:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-30 11:15 | Rushikesh Gunjal | 2025-05-30 11:45 | Not ok |  |  |  | 74.7591 | 20.4467 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/642 | Checking Pipe Laying And Shuttering & Pouring Concrete Of Head Wall Second Lift for HPC | 138780 | 138780 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 16:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 16:50 | Kishori Lal | 2025-06-09 16:11 | Work Execute without checking. |  |  |  | 74.7727 | 20.4762 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/563 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135250 | 135340 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 10:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-29 12:15 | Rushikesh Gunjal | 2025-05-30 15:40 | Ok | 2025-05-30 18:31 | Brajesh Upadhyay | work has been done | 74.7594 | 20.4469 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/647 | Checking Reinforcement, shuttering and pouring concrete for Haunch Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 17:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 14:10 | Kishori Lal | 2025-06-09 17:50 | Not Ready. |  |  |  | 74.7483 | 20.3993 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1019 | Checking Of Utility Pipe Laying | 140520 | 140520 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-11 18:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-12 11:23 | Rushikesh Gunjal | 2025-08-12 17:20 | Ok | 2025-08-12 20:47 | Brajesh Upadhyay | work has been done | 74.7811 | 20.4887 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/567 | Checking Checking Shuttering and pouring concrete of PCC for Drain | 134710 | 134730 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-29 10:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-29 12:40 | Rushikesh Gunjal | 2025-05-30 12:02 | Ok | 2025-05-30 13:42 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4425 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1034 | Checking Of Layout Marking & Excavation & Laying PCC For Drain | 120170 | 120190 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-18 16:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-19 12:30 | Kishori Lal | 2025-08-20 16:58 | Work done. | 2025-08-20 17:28 | Brajesh Upadhyay | work has been done | 74.6928 | 20.3352 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1038 | Checking Of Utility Pipe Laying | 137560 | 137560 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-18 17:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-19 15:00 | Saurabh SE | 2025-08-19 14:52 | Work done | 2025-08-19 20:58 | Brajesh Upadhyay | work has been done | 74.7677 | 20.4666 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1040 | Checking Of Level & FDD Test & Filling Of Earthen Shoulder | 125000 | 125900 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-18 17:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-19 11:30 | Saurabh SE | 2025-08-19 17:14 | FDD found ok | 2025-08-19 20:59 | Brajesh Upadhyay | work has been done | 74.715 | 20.3724 | Inspected | RFI Approved | 900 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/574 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134710 | 134730 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 16:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 16:29 | Rushikesh Gunjal | 2025-06-02 16:05 | Reinforcement is not in alignment Work is already done without inspection |  |  |  | 74.7579 | 20.4423 | Inspected | Inspected - Fail | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1031 | Checking Of Layout Marking & Excavation & Laying PCC | 120190 | 120230 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-17 17:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-18 14:30 | Saurabh SE | 2025-08-18 15:30 | Work done | 2025-08-19 21:02 | Brajesh Upadhyay | work has been done | 74.6929 | 20.3353 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1032 | Checking Of Layout Marking & Excavation & Laying PCC For Drain | 120030 | 120050 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-17 17:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-18 14:00 | Saurabh SE | 2025-08-18 15:33 | Work done | 2025-08-19 21:02 | Brajesh Upadhyay | work has been done | 74.6918 | 20.3341 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/575 | Checking Shuttering and laying of PCC for head wall & Below pipe | 138983 | 138983 | RHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 18:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 09:10 | Rushikesh Gunjal | 2025-05-31 12:04 | PCC below head wall not done |  |  |  | 74.7738 | 20.4777 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1039 | Checking Of Utility Pipe Laying | 137730 | 137730 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-18 17:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-19 16:00 | Saurabh SE | 2025-08-19 14:47 | Not found in this chainge |  |  |  | 74.7682 | 20.4675 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/577 | Checking Shuttering and pouring concrete of PCC for retaining wall | 140700 | 140800 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 18:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 10:20 | Rushikesh Gunjal | 2025-05-31 11:48 | Dressing & compaction on bed not Done Work Not Done |  |  |  | 74.7817 | 20.4909 | Inspected | Inspected - Rejected - Work Not Done | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/576 | Checking Reinforcement, shuttering and pouring concrete for Retaing Wall Raft | 140640 | 140680 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 12:15 | Rushikesh Gunjal | 2025-05-31 12:32 | Work is already done before inspecting the RFI Date Used not approved steel - SRJ |  |  |  | 74.7813 | 20.4892 | Inspected | Inspected - Fail | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/578 | Checking Layout Marking & Excavation For HPC | 133628 | 133628 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 18:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 16:05 | Rushikesh Gunjal | 2025-05-31 13:12 | Not done |  |  |  | 74.7585 | 20.4326 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/579 | Checking pipe laying and joint filling & Checking shuttering and pouring concrete for Head Wall Final lift | 137018 | 137018 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 18:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 15:00 | Rushikesh Gunjal | 2025-06-02 16:15 | Pipe joint filling from inner side work not done |  |  |  | 74.7658 | 20.4616 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/586 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135230 | 135250 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 21:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 10:30 | Kishori Lal | 2025-06-02 13:23 | Work done | 2025-06-03 07:53 | Brajesh Upadhyay | work has been done | 74.7594 | 20.4468 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/433 | Checking of Laying of PQC | 125570 | 126510 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 19:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 05:33 | Rushikesh Gunjal | 2025-05-30 15:06 | Ok | 2025-05-30 19:25 | Brajesh Upadhyay | laying work has been done | 74.7224 | 20.3797 | Inspected | RFI Approved | 940 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/604 | Checking Of Shuttering & Concrete Pouring For Head Wall Second lift & Pipe Laying | 120723 | 120723 | LHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-01 17:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-02 16:10 | Kishori Lal | 2025-06-02 18:35 | Not Ready. |  |  |  | 74.6963 | 20.3388 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/603 | Checking Of Shuttering & Concrete Pouring For Head Wall Second lift & Pipe Laying | 120737 | 120737 | LHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-01 17:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-02 15:01 | Kishori Lal | 2025-06-02 18:23 | Not Done. |  |  |  | 74.6963 | 20.3388 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/643 | Checking Shuttering and pouring concrete For Head Wall First Lift Of HPC | 138983 | 138983 | LHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 16:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 15:55 | Kishori Lal | 2025-06-09 16:02 | Not Ready. |  |  |  | 74.7737 | 20.4778 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/400 | Checking of Laying of PQC | 123980 | 124920 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 13:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 07:52 | Rushikesh Gunjal | 2025-05-24 15:29 | Ok | 2025-06-25 11:57 | Sanjay Sharma | work has been done | 74.7121 | 20.3695 | Inspected | RFI Approved | 940 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/645 | Checking Shuttering & pouring Concrete For Encasing Of HPC | 120737 | 120737 | LHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 17:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 09:30 | Kishori Lal | 2025-06-09 18:57 | Repeat RFI. |  |  |  | 74.6966 | 20.3388 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/580 | Checking Reinforcement, Shuttering & Pouring Concrete For Drain Raft | 135220 | 135260 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 21:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 10:00 | Kishori Lal | 2025-06-02 12:53 | Not Ready. |  |  |  | 74.7592 | 20.4469 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/581 | Checking Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 134730 | 134750 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 21:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 11:15 | Kishori Lal | 2025-06-02 14:40 | Work done. | 2025-06-03 08:10 | Brajesh Upadhyay | work has been done | 74.7578 | 20.4421 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/582 | Checking of Layout Marking & Excavation for Drain | 134980 | 135080 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 21:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 09:15 | Saurabh SE | 2025-06-02 13:44 | Excavation not started |  |  |  | 74.7588 | 20.4452 | Inspected | Inspected - Rejected - Work Not Done | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/583 | Checking Reinforcement, Shuttering & Pouring PCC For Drain | 134980 | 135080 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 21:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 12:15 | Kishori Lal | 2025-06-02 13:37 | Not done. |  |  |  | 74.759 | 20.4461 | Inspected | Inspected - Rejected - Work Not Done | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/585 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134720 | 134750 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 21:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 11:30 | Kishori Lal | 2025-06-02 14:16 | Wrong Chainage. |  |  |  | 74.758 | 20.4424 | Inspected | Inspected - Fail | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/587 | Checking Shuttering and laying of PCC for Drain | 134520 | 134600 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 21:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 14:30 | Kishori Lal | 2025-06-02 14:55 | Not Ready. |  |  |  | 74.7579 | 20.4417 | Inspected | Inspected - Rejected - Work Not Done | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/588 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135220 | 135260 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 21:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 11:00 | Kishori Lal | 2025-06-02 13:07 | Not Ready. |  |  |  | 74.7593 | 20.4469 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/589 | Checking Layout Marking,Excavation & Laying Pcc For HPC | 120723 | 120723 | LHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 21:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 09:45 | Saurabh SE | 2025-06-02 18:09 | Work done | 2025-06-03 07:58 | Brajesh Upadhyay | work has been done | 74.6962 | 20.3387 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/590 | Checking Layout Marking,Excavation & Laying Pcc For HPC | 120737 | 120737 | LHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 21:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 10:40 | Saurabh SE | 2025-06-02 18:33 | Work done without level checking |  |  |  | 74.6964 | 20.3388 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/591 | Checking of Layout Marking & Excavation for Drain | 134570 | 134600 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-30 21:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-31 11:45 | Saurabh SE | 2025-06-02 14:56 | Work not done |  |  |  | 74.7578 | 20.4414 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/638 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135220 | 135235 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 16:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 11:30 | Rushikesh Gunjal | 2025-06-07 11:41 | Ok | 2025-06-08 08:55 | Brajesh Upadhyay | work has been done | 74.7592 | 20.4468 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/745 | Laying Of PQC Top | 132500 | 133850 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-24 18:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-25 18:00 | Rushikesh Gunjal | 2025-06-25 11:54 | Check and found Ok | 2025-06-25 13:09 | Sanjay Sharma | work has been done only 132500-132850 | 74.7583 | 20.4255 | Inspected | RFI Approved | 1350 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1030 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Final Lift | 140715 | 140735 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-17 17:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-18 14:30 | Saurabh SE | 2025-08-19 14:24 | Work completed | 2025-08-19 21:24 | Brajesh Upadhyay | work has been done | 74.7816 | 20.4902 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/698 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall First Lift & Encasing HPC | 120737 | 120737 | RHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-17 17:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-18 14:00 | Kishori Lal | 2025-06-18 15:16 | Alignment of HPC not as per design and drawing. |  |  |  | 74.6965 | 20.3387 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/599 | Checking Reinforcement,Shuttering & Pouring Concrete For Drain Slab | 134710 | 134720 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-31 21:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-01 11:40 | Kishori Lal | 2025-06-02 14:42 | Work done. | 2025-06-03 07:47 | Brajesh Upadhyay | work has been done | 74.7578 | 20.4419 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/699 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall First Lift & Encasing HPC | 120723 | 120723 | RHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-17 17:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-18 14:15 | Kishori Lal | 2025-06-18 15:14 | Work already completed without checking. |  |  |  | 74.6966 | 20.3387 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/461 | Checking of Laying of PQC | 126510 | 127330 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 09:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 18:06 | Rushikesh Gunjal | 2025-06-02 22:40 | Check and found ok | 2025-06-25 11:57 | Sanjay Sharma | work has been done | 74.7291 | 20.3844 | Inspected | RFI Approved | 820 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/701 | Checking Laying Of PCC for Drain | 135090 | 135130 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-17 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-18 23:15 | Rushikesh Gunjal | 2025-06-18 18:35 | Checked and ok | 2025-06-19 08:11 | Brajesh Upadhyay | work has been done | 74.7589 | 20.4459 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/702 | Checking Of Laying DLC Top | 130250 | 130870 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-17 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-18 10:06 | Rushikesh Gunjal | 2025-06-19 16:16 | Checked and ok | 2025-06-20 08:13 | Brajesh Upadhyay | work has been done | 74.754 | 20.412 | Inspected | RFI Approved | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/693 | Checking of Layout Marking , Excavation for Drain | 135090 | 135150 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-16 14:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-17 22:40 | Rushikesh Gunjal | 2025-06-18 18:30 | Excavation not done |  |  |  | 74.7589 | 20.4455 | Inspected | Inspected - Rejected - Work Not Done | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/692 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135190 | 135210 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-16 14:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-17 10:00 | Rushikesh Gunjal | 2025-06-18 18:47 | Ok | 2025-06-19 08:25 | Brajesh Upadhyay | work has been done | 74.7591 | 20.4463 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/694 | Checking of Laying pcc for Drain | 135130 | 135170 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-16 14:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-17 10:55 | Rushikesh Gunjal | 2025-06-18 18:37 | Ok | 2025-06-19 08:15 | Brajesh Upadhyay | work has been done | 74.7589 | 20.4459 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/695 | Checking Of Laying DLC Top | 132000 | 132900 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-17 17:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-18 14:30 | Rushikesh Gunjal | 2025-06-19 16:18 | Checked and ok | 2025-06-20 08:19 | Brajesh Upadhyay | work has been done | 74.754 | 20.412 | Inspected | RFI Approved | 900 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/747 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135110 | 135130 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-24 18:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-25 12:05 | Kishori Lal | 2025-06-25 15:03 | Not Ready. |  |  |  | 74.7589 | 20.4459 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/706 | Checking Shuttering & Pouring Concrete For Head Wall & Below Pipe PCC | 133023 | 133023 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-17 19:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-18 12:15 | Kishori Lal | 2025-06-18 13:00 | Work done without checking. |  |  |  | 74.7581 | 20.4273 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1590 | Checking Of Laying DLC Top | 121500 | 122280 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:47 | Rushikesh Gunjal | 2025-10-28 12:04 | Work was already done | 2025-10-28 18:36 | Brajesh Upadhyay | work has been done | 74.6994 | 20.348 | Inspected | RFI Approved | 780 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1025 | Checking Of Utility Pipe Laying | 121440 | 121440 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-17 17:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-18 10:30 | Saurabh SE | 2025-08-18 15:25 | Utility pipe work done | 2025-08-19 21:27 | Brajesh Upadhyay | work has been done | 74.6988 | 20.3444 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1132 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119830 | 120000 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-29 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-30 15:30 | Rushikesh Gunjal | 2025-08-30 15:32 | Work not done |  |  |  | 74.6911 | 20.333 | Inspected | Inspected - Rejected - Work Not Done | 170 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/637 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135242 | 135260 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 16:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 11:00 | Rushikesh Gunjal | 2025-06-07 11:39 | Ok | 2025-06-08 08:53 | Brajesh Upadhyay | work has been done | 74.7592 | 20.4468 | Inspected | RFI Approved | 18 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1026 | Checking Of Utility Pipe Laying | 122320 | 122320 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-17 17:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-18 12:30 | Saurabh SE | 2025-08-18 15:22 | Utility pipe work is done | 2025-08-19 21:27 | Brajesh Upadhyay | work has been done | 74.7016 | 20.3516 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1997 | Checking Of Reinforcement , shuttering & Pouring Concrete For Toe Wall Final Lift | 129620 | 129675 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-27 17:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-28 10:00 | Rushikesh Gunjal | 2025-12-29 16:31 | Work not done |  |  |  | 74.7481 | 20.3987 | Inspected | Inspected - Rejected - Work Not Done | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/605 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135170 | 135210 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 14:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 11:15 | Kishori Lal | 2025-06-04 14:40 | Not Ready. |  |  |  | 74.7591 | 20.4462 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/606 | Checking Layout Marking,Excavation & Laying Pcc For HPC | 120737 | 120737 | LHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 14:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 15:00 | Saurabh SE | 2025-06-05 15:38 | Work done | 2025-06-06 07:05 | Brajesh Upadhyay | work has been done | 74.6962 | 20.3386 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/607 | Checking Concrete Of Pcc Below Pipe & Head Wall 1st Lift | 120737 | 120737 | LHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 14:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 15:10 | Kishori Lal | 2025-06-04 17:43 | Work done. | 2025-06-04 20:28 | Brajesh Upadhyay | work has been done | 74.6965 | 20.3389 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/608 | Checking Of Pipe Laying For HPC | 120737 | 120737 | LHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 14:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 15:25 | Kishori Lal | 2025-06-04 17:46 | Work done. | 2025-06-04 20:21 | Brajesh Upadhyay | work has been done | 74.6965 | 20.3388 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/609 | Checking Shuttering and pouring concrete of Head Wall Second Lift | 120737 | 120737 | RHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 15:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 15:15 | Kishori Lal | 2025-06-04 17:55 | Work done LHS. | 2025-06-04 20:22 | Brajesh Upadhyay | work has been done | 74.6965 | 20.3389 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/610 | Checking Of Shuttering & Concrete Pouring For Head Wall Second lift & Pipe Laying | 120723 | 120723 | LHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 15:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 15:45 | Kishori Lal | 2025-06-04 18:03 | Shuttering cheking and found Satisfactory and allowing for concrete pouring M-20 Grade HPC Head wall 2nd lift. | 2025-06-04 20:23 | Brajesh Upadhyay | work has been done | 74.6962 | 20.3386 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/649 | Checking Shuttering and pouring concrete of Head Wall Final Lift | 138728 | 138728 | RHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-08 18:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-09 11:00 | Kishori Lal | 2025-06-09 16:20 | Work done. | 2025-06-10 07:57 | Brajesh Upadhyay | work has been done | 74.7725 | 20.4757 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/611 | Checking Reinforcement, shuttering and pouring concrete Of Raft for MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 16:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 10:30 | Kishori Lal | 2025-06-04 14:02 | Drawing not approved. |  |  |  | 74.7482 | 20.3993 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/614 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135220 | 135260 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 17:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 14:00 | Kishori Lal | 2025-06-04 14:58 | Wrong Chainage. |  |  |  | 74.7592 | 20.4469 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/613 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135220 | 135260 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 17:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 09:45 | Kishori Lal | 2025-06-04 14:56 | Wrong Chainage. |  |  |  | 74.7592 | 20.4468 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/612 | Checking Layout Marking & Excavation For Drain | 134570 | 134600 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 16:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 10:00 | Kishori Lal | 2025-06-04 14:20 | Work done. | 2025-06-04 20:24 | Brajesh Upadhyay | work has been done | 74.7577 | 20.4414 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/615 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134700 | 134723 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 17:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 14:15 | Kishori Lal | 2025-06-04 14:29 | Work done. | 2025-06-04 20:25 | Brajesh Upadhyay | work has been done | 74.7578 | 20.4424 | Inspected | RFI Approved | 23 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/616 | Checking Shuttering and pouring concrete for Head Wall Final Lift | 137018 | 137018 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 17:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 09:05 | Kishori Lal | 2025-06-04 15:18 | Work done only RHS. | 2025-06-04 20:25 | Brajesh Upadhyay | work has been done | 74.7658 | 20.4615 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/618 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135240 | 135340 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 17:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 10:05 | Kishori Lal | 2025-06-04 15:05 | Not Ready. |  |  |  | 74.7594 | 20.4469 | Inspected | Inspected - Rejected - Work Not Done | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/617 | Checking Shuttering and laying PCC for head wall & Below pipe | 138983 | 138983 | RHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 17:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 10:00 | Kishori Lal | 2025-06-04 16:22 | Work execute without checking. |  |  |  | 74.7741 | 20.4777 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/619 | Checking Shuttering and laying of PCC for head wall & Below pipe | 138780 | 138780 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 17:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 10:15 | Kishori Lal | 2025-06-04 16:08 | Work Done Below Pipe. | 2025-06-04 20:15 | Brajesh Upadhyay | work has been done | 74.7727 | 20.476 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/620 | Checking Shuttering and laying of PCC for head wall & Below pipe | 138728 | 138728 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 17:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 11:15 | Kishori Lal | 2025-06-04 15:36 | Work done. | 2025-06-04 20:17 | Brajesh Upadhyay | work has been done | 74.7723 | 20.4759 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1027 | Checking Of Utility Pipe Laying | 124880 | 124880 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-17 17:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-18 15:30 | Saurabh SE | 2025-08-18 15:14 | Utility pipe work done | 2025-08-19 21:28 | Brajesh Upadhyay | work has been done | 74.7137 | 20.3711 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/621 | Checking Excavation & Laying PCC For Head wall & Below Pipe | 133628 | 133628 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-03 17:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-04 15:00 | Rushikesh Gunjal | 2025-06-04 10:50 | Work is already done without inspection |  |  |  | 74.7587 | 20.4325 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/750 | Checking Reinforcement, shuttering and pouring concrete for A1,A2 & Intermediate Wall Second Lift Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-24 19:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-25 15:10 | Kishori Lal | 2025-06-25 18:02 | Not Ready. |  |  |  | 74.7469 | 20.3975 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/142 | Cheacking shuttering and pouring concrete for Head Wall first lift | 127930 | 127930 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-03 10:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-03 12:37 | Kishori Lal | 2025-04-03 13:39 | Work done. | 2025-04-04 10:11 | Brajesh Upadhyay | work has been done | 74.7354 | 20.389 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/644 | Checking Pipe Laying and Shuttering & Pouring Concrete For Head Wall Second Lift | 138983 | 138983 | RHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 17:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 15:45 | Kishori Lal | 2025-06-09 16:05 | Work execute without checking. |  |  |  | 74.7737 | 20.4777 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/641 | Checking Of Pipe Laying & Pouring Concrete Of Head Wall Second Lift & Encasing | 138728 | 138728 | RHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 16:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 16:40 | Kishori Lal | 2025-06-09 16:17 | Work done. | 2025-06-10 08:05 | Brajesh Upadhyay | work has been done | 74.7725 | 20.4757 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/622 | Checking Reinforcement, shuttering and pouring concrete Of Raft for MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-04 19:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-05 09:00 | Kishori Lal | 2025-06-05 20:00 | Work done. | 2025-06-06 06:53 | Brajesh Upadhyay | work has been done | 74.7483 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/749 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 120723 | 120723 | RHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-24 19:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-25 14:45 | Kishori Lal | 2025-06-25 18:44 | Already work done without checking. |  |  |  | 74.6963 | 20.3381 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/623 | Checking Shuttering & Pouring Concrete Of Encasing For HPC | 120723 | 120723 | LHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-04 19:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-05 14:00 | Kishori Lal | 2025-06-05 15:44 | Work Done. | 2025-06-06 06:54 | Brajesh Upadhyay | work has been done | 74.6963 | 20.3389 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/624 | Checking Shuttering & Pouring Concrete Of Encasing For HPC | 120737 | 120737 | LHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-04 20:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-05 14:30 | Kishori Lal | 2025-06-05 15:48 | Not Ready. |  |  |  | 74.6967 | 20.3388 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/625 | Checking shuttering and pouring concrete for Head Wall First lift Of HPC | 138983 | 138983 | RHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-04 20:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-05 09:30 | Kishori Lal | 2025-06-05 17:17 | Work done. | 2025-06-06 06:55 | Brajesh Upadhyay | work has been done | 74.7738 | 20.4777 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/626 | Checking Shuttering and laying PCC Head Wall & Below Pipe | 138983 | 138983 | LHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-04 20:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-05 09:30 | Kishori Lal | 2025-06-05 17:15 | Work done. | 2025-06-06 06:56 | Brajesh Upadhyay | work has been done | 74.7737 | 20.4778 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/627 | Checking Shuttering and Pouring Concrete Of head wall First Lift Of HPC | 138780 | 138780 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-04 20:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-05 10:15 | Kishori Lal | 2025-06-05 17:22 | Work done. | 2025-06-06 06:56 | Brajesh Upadhyay | work has been done | 74.7729 | 20.476 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/628 | Checking shuttering and pouring concrete for Head Wall First lift Of HPC | 138728 | 138728 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-04 20:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-05 10:30 | Kishori Lal | 2025-06-05 17:30 | Work in progress RHS. | 2025-06-06 06:57 | Brajesh Upadhyay | work has been done | 74.7724 | 20.4758 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1156 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Slab | 119805 | 119825 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-31 18:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-01 16:00 | Kishori Lal | 2025-09-01 12:40 | Work done. | 2025-09-01 20:48 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3324 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/629 | Checking Pipe Laying & Shuttering And Pouring Concrete For Head Wall Second Lift Of HPC | 137018 | 137018 | LHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-04 20:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-05 11:00 | Kishori Lal | 2025-06-05 17:36 | Work done. | 2025-06-06 06:50 | Brajesh Upadhyay | work has been done | 74.7656 | 20.4618 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/630 | Checking Layout Marking ,Excavation & Laying PCC For Head wall Of HPC | 133120 | 133120 | LHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-04 20:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-05 11:35 | Saurabh SE | 2025-06-05 17:06 | Excavation work is not done |  |  |  | 74.7582 | 20.428 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/631 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135190 | 135210 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-04 20:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-05 11:00 | Kishori Lal | 2025-06-05 17:56 | Not Ready. |  |  |  | 74.7592 | 20.4468 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/632 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135220 | 135235 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-04 20:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-05 10:45 | Kishori Lal | 2025-06-05 17:54 | Work done. | 2025-06-06 06:49 | Brajesh Upadhyay | work has been done | 74.7593 | 20.4469 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/633 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135242 | 135260 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-04 20:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-05 12:30 | Kishori Lal | 2025-06-05 17:52 | Work done. | 2025-06-06 06:48 | Brajesh Upadhyay | work has been done | 74.7593 | 20.4469 | Inspected | RFI Approved | 18 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/634 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135280 | 135340 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-04 20:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-05 14:10 | Kishori Lal | 2025-06-05 17:51 | Not Ready |  |  |  | 74.7591 | 20.4465 | Inspected | Inspected - Rejected - Work Not Done | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/748 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 120737 | 120737 | RHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-24 19:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-25 14:10 | Kishori Lal | 2025-06-25 18:43 | Already work done without checking. |  |  |  | 74.6965 | 20.3386 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1150 | Checking Of Level & FDD Test For Earthen Shoulder | 133850 | 134450 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-31 18:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-01 11:30 | Saurabh SE | 2025-09-01 16:57 | Work done | 2025-09-01 20:50 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4372 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/648 | Checking Excavation & Laying PCC For Head wall & Below Pipe | 133628 | 133628 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 17:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 12:10 | Kishori Lal | 2025-06-09 17:10 | Work already done without raising RFI |  |  |  | 74.7585 | 20.4326 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1151 | Checking Of Level & FDD Test For Earthen Shoulder | 134650 | 135400 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-31 18:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-01 15:30 | Saurabh SE | 2025-09-01 17:25 | Work done | 2025-09-01 20:50 | Brajesh Upadhyay | work has been done | 74.7592 | 20.4469 | Inspected | RFI Approved | 750 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1152 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall 1st Lift | 140590 | 140610 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-31 18:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-01 14:00 | Kishori Lal | 2025-09-01 17:21 | Work done. | 2025-09-01 20:51 | Brajesh Upadhyay | work has been done | 74.7814 | 20.4894 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1245 | Checking Reinforcement, shuttering and pouring concrete for retaining Wall Final Lift | 140515 | 140540 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-12 18:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-13 14:30 | Rushikesh Gunjal | 2025-09-13 11:48 | OK | 2025-09-14 10:40 | Brajesh Upadhyay | work has been done | 74.7812 | 20.4887 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1154 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 120060 | 120070 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-31 18:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-01 13:30 | Kishori Lal | 2025-09-01 12:29 | Work done. | 2025-09-01 20:51 | Brajesh Upadhyay | work has been done | 74.6922 | 20.3344 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1155 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Raft | 119830 | 119850 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-31 18:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-01 14:30 | Kishori Lal | 2025-09-01 12:36 | Work done. | 2025-09-01 20:52 | Brajesh Upadhyay | work has been done | 74.691 | 20.3327 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1011 | Checking Of Pipe Laying & Shuttering & Pouring Concrete Head Wall Second Lift | 120400 | 120400 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-01 18:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-02 15:30 | Rushikesh Gunjal | 2025-08-02 13:25 | Shuttering not in alignment & run away |  |  |  | 74.6942 | 20.3366 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1144 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 120080 | 120110 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-30 18:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-31 15:30 | Saurabh SE | 2025-09-01 12:02 | Work done | 2025-09-01 20:52 | Brajesh Upadhyay | work has been done | 74.6922 | 20.3344 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1005 | Checking Reinforcement, shuttering and pouring concrete for Wall First Lift Of Retaining Wall | 140800 | 140830 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-31 17:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-01 15:00 | Rushikesh Gunjal | 2025-08-01 17:42 | Check found OK | 2025-08-01 21:10 | Brajesh Upadhyay | work has been done | 74.7818 | 20.4911 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/497 | Checking of Laying of PQC | 127330 | 127670 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 06:30 | Rushikesh Gunjal | 2025-06-05 00:45 | Checked and found ok | 2025-06-06 07:24 | Brajesh Upadhyay | work has been done | 74.7339 | 20.3881 | Inspected | RFI Approved | 340 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/646 | Checking Shuttering and pouring concrete of Head Wall Final Lift Of HPC | 120723 | 120723 | LHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 17:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 10:00 | Kishori Lal | 2025-06-09 18:50 | Repeat RFI. |  |  |  | 74.6963 | 20.3387 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/635 | Checking Shuttering and laying Concrete Of Encasing For HPC | 120737 | 120737 | LHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 15:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 11:40 | Kishori Lal | 2025-06-09 18:56 | Cradle casting work done. | 2025-06-10 08:07 | Brajesh Upadhyay | work has bee done | 74.6966 | 20.3388 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/636 | Checking Shuttering and pouring concrete of Head Wall Final Lift for HPC | 120723 | 120723 | LHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-06 16:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-07 14:00 | Kishori Lal | 2025-06-09 18:46 | Work done. | 2025-06-10 08:08 | Brajesh Upadhyay | work has been done | 74.6963 | 20.3388 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1145 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120240 | 120250 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-30 18:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-31 16:05 | Kishori Lal | 2025-09-01 12:15 | Work done. | 2025-09-01 20:55 | Brajesh Upadhyay | work has been done | 74.6932 | 20.3357 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/961 | Checking Of Laying PQC Top | 133840 | 134530 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-24 17:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-25 08:00 | Rushikesh Gunjal | 2025-08-01 16:47 | Check found OK | 2025-08-01 21:22 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4364 | Inspected | RFI Approved | 690 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1138 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall Raft | 140590 | 140610 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-30 17:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-31 14:30 | Kishori Lal | 2025-09-01 17:19 | Work done. | 2025-09-01 20:56 | Brajesh Upadhyay | work has been done | 74.7817 | 20.489 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/081 | Checking Level and FDD test for GSB Top | 121500 | 122000 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 12:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 14:31 | Rushikesh Gunjal | 2025-03-11 16:40 | Checked and found ok | 2025-04-07 12:45 | Brajesh Upadhyay | Work done | 74.6984 | 20.3411 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1139 | Checking Of Layout Marking , Excavation & Laying PCC For Retaining Wall | 140650 | 140665 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-30 18:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-31 15:00 | Saurabh SE | 2025-09-01 17:52 | Work done | 2025-09-01 20:57 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4892 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1140 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119830 | 119850 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-30 18:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-31 09:30 | Saurabh SE | 2025-09-01 11:50 | Work done | 2025-09-01 20:57 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3325 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1141 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119970 | 120000 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-30 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-31 11:30 | Saurabh SE | 2025-09-01 11:58 | Work done | 2025-09-01 20:58 | Brajesh Upadhyay | work has been done | 74.6919 | 20.3341 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/653 | Checking Of Shuttering & Concrete Pouring For Head Wall Final lift | 138983 | 138983 | RHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-10 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 11:20 | Kishori Lal | 2025-06-11 17:10 | Work done without raising RFI. |  |  |  | 74.7737 | 20.4777 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/654 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift | 138780 | 138780 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-10 18:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 12:05 | Kishori Lal | 2025-06-11 17:01 | Not Ready. |  |  |  | 74.7723 | 20.4761 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/655 | Checking Reinforcement, shuttering and pouring concrete for Haunch MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-10 18:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 14:40 | Kishori Lal | 2025-06-11 15:24 | Reinforced and Formwork checked and found Satisfactory and allowing for concrete pouring for haunch. | 2025-06-12 12:06 | Brajesh Upadhyay | work has been done | 74.7488 | 20.3998 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/656 | Checking Shuttering and pouring concrete For Head Wall Final Lift | 120737 | 120737 | LHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-10 18:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 16:00 | Kishori Lal | 2025-06-11 12:21 | Work already done. | 2025-06-12 12:07 | Brajesh Upadhyay | work has been done | 74.6966 | 20.339 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/657 | Checking Of Layout Marking , Excavation & Laying Pcc For HPC | 120737 | 120737 | RHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-10 18:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 16:10 | Saurabh SE | 2025-06-11 12:16 | PCC not done |  |  |  | 74.6963 | 20.3387 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/658 | Checking Of Layout Marking , Excavation & Laying Pcc For HPC | 120723 | 120723 | RHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-10 18:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 16:30 | Saurabh SE | 2025-06-11 12:17 | PCC not done |  |  |  | 74.6965 | 20.3388 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/659 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Retaining Wall Raft | 140595 | 140634 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-10 18:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 10:30 | Rushikesh Gunjal | 2025-06-11 12:31 | Work done | 2025-06-12 10:49 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4896 | Inspected | RFI Approved | 39 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1142 | Checking Of Reinforcement ,Shuttering & Pouring Concrete For drain Slab | 120000 | 120020 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-30 18:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-31 15:50 | Kishori Lal | 2025-09-01 12:02 | Work done. | 2025-09-01 20:58 | Brajesh Upadhyay | work has been done | 74.6917 | 20.334 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/660 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall Raftl | 140643 | 140710 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-10 18:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 10:35 | Rushikesh Gunjal | 2025-06-11 12:26 | Checked and found ok | 2025-06-12 10:52 | Brajesh Upadhyay | work has been done | 74.7814 | 20.49 | Inspected | RFI Approved | 67 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/661 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135242 | 135260 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-10 18:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 11:45 | Rushikesh Gunjal | 2025-06-11 12:58 | Not done |  |  |  | 74.7591 | 20.4469 | Inspected | Inspected - Rejected - Work Not Done | 18 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1143 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120130 | 120150 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-30 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-31 15:00 | Kishori Lal | 2025-09-01 12:08 | Work done. | 2025-09-01 20:59 | Brajesh Upadhyay | work has been done | 74.6925 | 20.3348 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/651 | Checking Pipe Laying & Shuttering & Pouring Concrete for Head Wall Second Lift | 138728 | 138728 | LHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-10 18:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 11:00 | Kishori Lal | 2025-06-11 16:55 | Work done without raising RFI. |  |  |  | 74.7723 | 20.4758 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/652 | Checking Shuttering and Pouring Concrete For Head Wall First Lift | 133628 | 133628 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-10 18:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 14:00 | Kishori Lal | 2025-06-11 16:10 | Work already done without raising RFI & First 1st lift not done. |  |  |  | 74.7586 | 20.4325 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/752 | Checking Reinforcement, shuttering and pouring concrete for A1,A2 & Intermediate Wall Second Lift Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-25 18:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-26 15:00 | Kishori Lal | 2025-06-27 15:57 | Not Ready. |  |  |  | 74.7487 | 20.3995 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/756 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135024 | 135050 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-25 19:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-26 14:30 | Kishori Lal | 2025-06-27 16:30 | Reinforcement checking and found Satisfactory and allowing for concrete pouring M-25 Grade of concrete for Drain Raft. | 2025-06-27 22:55 | Sanjay Sharma | work has been done | 74.7586 | 20.4455 | Inspected | RFI Approved | 26 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/662 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135210 | 135235 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-10 18:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 11:50 | Rushikesh Gunjal | 2025-06-11 12:55 | Not done |  |  |  | 74.7592 | 20.4466 | Inspected | Inspected - Rejected - Work Not Done | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/663 | Checking Layout Marking & Excavation For Drain | 135210 | 135235 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-10 18:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 11:55 | Rushikesh Gunjal | 2025-06-11 13:02 | Work not done |  |  |  | 74.7592 | 20.4469 | Inspected | Inspected - Fail | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/753 | Laying Of DLC Top | 123840 | 124340 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-25 19:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-26 16:00 | Rushikesh Gunjal | 2025-06-26 15:31 | Checked and found ok | 2025-06-27 22:56 | Sanjay Sharma | work has been done | 74.7086 | 20.3654 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/700 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135170 | 135190 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-17 17:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-18 11:00 | Rushikesh Gunjal | 2025-06-18 18:51 | Ok | 2025-06-19 08:11 | Brajesh Upadhyay | work has been done | 74.7591 | 20.4463 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/708 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135150 | 135170 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-18 19:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-19 19:18 | Rushikesh Gunjal | 2025-06-19 14:28 | Check and found ok | 2025-06-20 08:06 | Brajesh Upadhyay | work done | 74.7591 | 20.4462 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/709 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135170 | 135210 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-18 19:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-19 19:19 | Rushikesh Gunjal | 2025-06-19 14:23 | Ok | 2025-06-20 07:57 | Brajesh Upadhyay | work has been done | 74.7592 | 20.4464 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1130 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Raft | 120130 | 120150 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-29 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-30 14:00 | Rushikesh Gunjal | 2025-09-01 13:22 | Ok | 2025-09-01 21:00 | Brajesh Upadhyay | work has been done | 74.6925 | 20.3348 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1312 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120360 | 120400 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-26 17:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-27 15:00 | Rushikesh Gunjal | 2025-09-27 15:39 | Check found OK | 2025-09-28 07:03 | Brajesh Upadhyay | work has been done | 74.6907 | 20.3322 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1305 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119740 | 119780 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-23 17:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-24 12:30 | Rushikesh Gunjal | 2025-09-25 11:07 | Check found OK | 2025-09-28 07:06 | Brajesh Upadhyay | work has been done | 74.6907 | 20.332 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/707 | Checking Laying Of PCC for Drain | 135024 | 135050 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-18 19:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-19 19:15 | Rushikesh Gunjal | 2025-06-19 14:40 | Ok | 2025-06-20 08:03 | Brajesh Upadhyay | work has been done | 74.7586 | 20.445 | Inspected | RFI Approved | 26 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/696 | Checking Of Laying PQC Top | 128500 | 129350 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-17 17:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-18 16:05 | Rushikesh Gunjal | 2025-06-18 18:06 | Ok | 2025-06-19 08:21 | Brajesh Upadhyay | work has been done | 74.7435 | 20.3951 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/697 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135242 | 135260 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-17 17:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-18 11:00 | Rushikesh Gunjal | 2025-06-18 18:59 | Check and found ok | 2025-06-19 08:23 | Brajesh Upadhyay | work has been done | 74.7593 | 20.4469 | Inspected | RFI Approved | 18 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/208 | Checking shuttering and pouring concrete for Head Wall second lift | 132669 | 132669 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-12 10:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-12 14:30 | Kishori Lal | 2025-04-12 12:09 | Work done. | 2025-04-12 18:38 | Brajesh Upadhyay | Work has been done | 74.7586 | 20.424 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/667 | Checking Of Layout Marking , Excavation & Laying PCC For HPC | 120723 | 120723 | RHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-11 14:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-12 14:30 | Saurabh SE | 2025-06-14 16:01 | Work done | 2025-06-15 09:51 | Brajesh Upadhyay | work has been done | 74.6964 | 20.3387 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/669 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall First Lift | 140595 | 140634 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-11 14:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-12 16:00 | Rushikesh Gunjal | 2025-06-12 15:03 | Reinforcement is not in alignment |  |  |  | 74.7813 | 20.4894 | Inspected | Inspected - Fail | 39 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/664 | Checking Layout Marking & Excavation For Drain | 135210 | 135235 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-11 14:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-12 10:30 | Rushikesh Gunjal | 2025-06-12 15:21 | Ok | 2025-06-13 11:00 | Brajesh Upadhyay | work has been done | 74.7593 | 20.4468 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/668 | Checking Of Layout Marking , Excavation & Laying PCC For HPC | 120737 | 120737 | RHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-11 14:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-12 14:50 | Saurabh SE | 2025-06-14 15:21 | Work done | 2025-06-15 09:52 | Brajesh Upadhyay | work has been done | 74.6965 | 20.3388 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/665 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135210 | 135235 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-11 14:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-12 10:45 | Rushikesh Gunjal | 2025-06-12 15:19 | Not ok |  |  |  | 74.7592 | 20.4468 | Inspected | Inspected - Rejected - Work Not Done | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/666 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135242 | 135260 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-11 14:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-12 10:55 | Rushikesh Gunjal | 2025-06-12 15:20 | Not ok |  |  |  | 74.7593 | 20.4469 | Inspected | Inspected - Rejected - Work Not Done | 18 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/671 | Checking Of Laying DLC Top | 130250 | 130870 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-11 14:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-11 16:00 | Rushikesh Gunjal | 2025-06-12 17:34 | No representative of the contractor was present for checking on site FDD not check ITF representative not present |  |  |  | 74.7497 | 20.4014 | Inspected | Inspected - Fail | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/673 | Checking Of Laying DLC Top | 130870 | 132000 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-11 14:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-12 15:00 | Rushikesh Gunjal | 2025-06-12 19:29 | No representative of the contractor was present for checking on site FDD not check ITF representative not present |  |  |  | 74.7539 | 20.4113 | Inspected | Inspected - Fail | 1130 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/674 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall First Lift | 140643 | 140710 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-11 14:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-12 16:15 | Rushikesh Gunjal | 2025-06-12 14:58 | Not ok |  |  |  | 74.7813 | 20.4896 | Inspected | Inspected - Rejected - Work Not Done | 67 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1193 | Checking Of Laying PQC Top | 140830 | 141400 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 17:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 18:30 | Rushikesh Gunjal | 2025-09-13 15:35 | Check found OK | 2025-09-14 11:04 | Brajesh Upadhyay | work has been done | 74.7819 | 20.4916 | Inspected | RFI Approved | 570 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1195 | Checking Of Laying PQC Top | 120400 | 121020 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 20:30 | Rushikesh Gunjal | 2025-09-13 16:30 | Check found OK | 2025-09-14 11:06 | Brajesh Upadhyay | work has been done | 74.6959 | 20.3382 | Inspected | RFI Approved | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/677 | Checking Reinforcement, shuttering and pouring concrete for A1 & Intermediate Wall First Lift Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-11 19:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-12 13:15 | Kishori Lal | 2025-06-14 18:27 | Work done. | 2025-06-15 09:49 | Brajesh Upadhyay | work has been done | 74.7486 | 20.3978 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1184 | Checking Of Laying PQC Top | 135550 | 136400 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 15:15 | Rushikesh Gunjal | 2025-09-09 16:01 | Check found OK | 2025-09-14 11:13 | Brajesh Upadhyay | work has been done | 74.762 | 20.4533 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/676 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift | 138780 | 138780 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-11 17:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-12 16:45 | Kishori Lal | 2025-06-14 19:40 | Not Ready. |  |  |  | 74.7727 | 20.476 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/675 | Checking Reinforcement, shuttering and pouring concrete for A2 First Lift Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-11 17:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-12 13:15 | Kishori Lal | 2025-06-14 18:25 | Work done. | 2025-06-15 09:47 | Brajesh Upadhyay | work has been done | 74.7481 | 20.3999 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/679 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall First Lift | 140595 | 140634 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-12 18:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-13 11:30 | Rushikesh Gunjal | 2025-06-13 17:19 | Checked and ok | 2025-06-13 17:46 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4894 | Inspected | RFI Approved | 39 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/678 | Checking Shuttering & Laying Of PCC | 135210 | 135235 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-12 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-13 12:30 | Rushikesh Gunjal | 2025-06-13 17:34 | Description is not clearly mentioned Wrong RFI |  |  |  | 74.7593 | 20.4466 | Inspected | Inspected - Rejected - Work Not Done | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/680 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall First Lift | 140643 | 140710 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-12 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-13 11:40 | Rushikesh Gunjal | 2025-06-13 17:16 | Checked and ok | 2025-06-13 17:45 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4894 | Inspected | RFI Approved | 67 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1187 | Checking Of Laying PQC Top | 138150 | 139060 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 17:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 16:30 | Rushikesh Gunjal | 2025-09-13 12:29 | Check found OK | 2025-09-14 11:38 | Brajesh Upadhyay | work has been done | 74.7659 | 20.4616 | Inspected | RFI Approved | 910 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2023 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Mid Wall First Lift Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-06 17:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-07 15:00 | Rushikesh Gunjal | 2026-01-08 10:40 | Work done | 2026-01-08 15:55 | Brajesh Upadhyay | work has been done | 74.7075 | 20.3637 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1188 | Checking Of Laying PQC Top | 139060 | 139900 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 17:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 17:30 | Rushikesh Gunjal | 2025-09-13 12:31 | Check found OK | 2025-09-14 11:40 | Brajesh Upadhyay | work has been done | 74.7659 | 20.4618 | Inspected | RFI Approved | 840 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2024 | Checking Of Layout Marking , Excavation & Laying PCC For Terminal Slab A1,A2 of BC | 140928 | 140928 | LHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-06 17:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-07 15:00 | Rushikesh Gunjal | 2026-01-07 15:57 | Work done | 2026-01-08 15:56 | Brajesh Upadhyay | work has been done | 74.7821 | 20.4923 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1173 | Checking Of Level & FDD test for GSB Top Layer | 129800 | 129810 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 15:00 | Rushikesh Gunjal | 2025-09-11 13:04 | Check and OK | 2025-09-14 11:55 | Brajesh Upadhyay | work has been done | 74.7748 | 20.4809 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/681 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135210 | 135235 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-14 09:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-15 09:30 | Rushikesh Gunjal | 2025-06-16 18:57 | Ok | 2025-06-17 18:48 | Brajesh Upadhyay | work has been done | 74.7592 | 20.4467 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/682 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135242 | 135260 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-14 09:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-15 09:40 | Rushikesh Gunjal | 2025-06-16 18:58 | Not ok |  |  |  | 74.7593 | 20.4469 | Inspected | Inspected - Fail | 18 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1174 | Checking Of Level & FDD test for GSB Top Layer | 140050 | 140260 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 16:30 | Rushikesh Gunjal | 2025-09-13 14:59 | Check found Ok | 2025-09-14 11:57 | Brajesh Upadhyay | work has been done | 74.7774 | 20.4862 | Inspected | RFI Approved | 210 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1179 | Checking Of Laying DLC Top | 120400 | 121010 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 15:30 | Rushikesh Gunjal | 2025-09-13 16:41 | Check found OK | 2025-09-14 11:59 | Brajesh Upadhyay | work has been done | 74.696 | 20.3381 | Inspected | RFI Approved | 610 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1129 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Slab | 120205 | 120225 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-29 18:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-30 11:30 | Rushikesh Gunjal | 2025-08-30 14:58 | Check and OK | 2025-09-01 09:09 | Brajesh Upadhyay | work has been done | 74.6931 | 20.336 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1131 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Wall | 120340 | 120360 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-29 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-30 15:00 | Rushikesh Gunjal | 2025-08-30 14:49 | Check and OK | 2025-09-01 09:11 | Brajesh Upadhyay | work has been done | 74.6939 | 20.3362 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1133 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Wall | 120040 | 120070 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-29 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-30 16:00 | Rushikesh Gunjal | 2025-08-30 15:25 | OK | 2025-09-01 09:12 | Brajesh Upadhyay | work has been done | 74.692 | 20.3343 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1128 | Checking Of Layout Marking , Excavation & Laying PCC For Retaining | 140590 | 140610 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-29 18:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-30 15:00 | Rushikesh Gunjal | 2025-08-30 10:07 | Check found OK | 2025-09-01 09:15 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4891 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2017 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Approach Slab A1,A2 Of MNB | 129698 | 129698 | LHS | Bridge | Minor Bridge Reconstruction | Approaches | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-03 17:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-04 12:00 | Rushikesh Gunjal | 2026-01-07 15:27 | Work done | 2026-01-08 16:02 | Brajesh Upadhyay | work has been done | 74.7483 | 20.3991 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1117 | Checking Of Level & FDD Test For Earthen Shoulder | 132850 | 133130 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-28 16:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-29 11:00 | Rushikesh Gunjal | 2025-08-30 12:14 | Check found OK | 2025-09-01 09:16 | Brajesh Upadhyay | work has been done | 74.7585 | 20.4239 | Inspected | RFI Approved | 280 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/687 | Checking Of Laying DLC Top | 130250 | 130870 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-16 09:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-16 13:45 | Rushikesh Gunjal | 2025-06-16 18:38 | Contractor s representative not available on site for checking ITF representative not present |  |  |  | 74.7521 | 20.4064 | Inspected | Inspected - Fail | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1118 | Checking Of Level & FDD Test For Earthen Shoulder | 133270 | 133850 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-28 16:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-29 16:00 | Rushikesh Gunjal | 2025-08-30 12:15 | Check found Satisfactory result | 2025-09-01 09:17 | Brajesh Upadhyay | work has been done | 74.7585 | 20.4239 | Inspected | RFI Approved | 580 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/688 | Checking Of Laying DLC Top | 130870 | 132000 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-16 09:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-17 09:40 | Rushikesh Gunjal | 2025-06-16 18:43 | Contractor s representative not available on site for checking ITF representative not present |  |  |  | 74.7542 | 20.4123 | Inspected | Inspected - Fail | 1130 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1171 | Checking Of Level & FDD test for GSB Top Layer | 120400 | 121030 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 10:30 | Rushikesh Gunjal | 2025-09-13 16:46 | Ok | 2025-09-14 12:02 | Brajesh Upadhyay | work has been done | 74.696 | 20.3382 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1162 | Checking Of Level & FDD Test For GSB Top | 139900 | 140260 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-01 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-02 15:45 | Rushikesh Gunjal | 2025-09-13 14:57 | Check found OK | 2025-09-14 12:04 | Brajesh Upadhyay | work has been done | 74.7774 | 20.4862 | Inspected | RFI Approved | 360 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/715 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall First Lift & Encasing HPC | 120737 | 120737 | RHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-19 19:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-20 12:10 | Kishori Lal | 2025-06-23 18:06 | Already Work done without checking and without raising RFI. | 2025-06-25 11:56 | Sanjay Sharma | work has been done | 74.6966 | 20.3389 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/714 | Checking Pipe Laying And Shuttering & Pouring Concrete Of Head Wall Second Lift for HPC | 138780 | 138780 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-19 19:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-20 14:10 | Kishori Lal | 2025-06-23 12:02 | Work execute without checking and without raising RFI. |  |  |  | 74.7729 | 20.4761 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/716 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall First Lift & Encasing HPC | 120723 | 120723 | RHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-19 19:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-20 12:30 | Kishori Lal | 2025-06-23 18:08 | Already work done without checking. |  |  |  | 74.6965 | 20.3389 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1097 | Checking Of Laying DLC Top | 133050 | 133210 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 17:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 10:30 | Rushikesh Gunjal | 2025-08-30 11:44 | Check found OK | 2025-09-01 09:25 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4369 | Inspected | RFI Approved | 160 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1098 | Checking Of Laying DLC Top | 133230 | 133850 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 17:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 12:30 | Rushikesh Gunjal | 2025-08-30 11:45 | Check found OK | 2025-09-01 09:26 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4369 | Inspected | RFI Approved | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1099 | Checking Of Laying DLC Top | 133850 | 134460 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 17:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 16:45 | Rushikesh Gunjal | 2025-08-30 11:47 | Check found Satisfactory result | 2025-09-01 09:27 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4369 | Inspected | RFI Approved | 610 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/799 | Checking Layout Marking & Excavation & Pcc For HPC | 120400 | 120400 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-03 18:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-04 16:30 | Rushikesh Gunjal | 2025-07-04 15:14 | Headwall Excavation is not done PCC not Done |  |  |  | 74.6942 | 20.3367 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/800 | Checking Layout Marking & Excavation & Pcc For Retaining Wall | 132910 | 132970 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-03 18:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-04 16:30 | Rushikesh Gunjal | 2025-07-04 17:39 | Check and OK | 2025-07-05 09:42 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4262 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1134 | Checking Of Laying DLC Top | 136400 | 137280 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-30 16:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-31 14:00 | Saurabh SE | 2025-09-05 17:33 | Work done | 2025-09-14 12:10 | Brajesh Upadhyay | work has been done | 74.764 | 20.4571 | Inspected | RFI Approved | 880 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/683 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall First Lift & Encasing HPC | 120737 | 120737 | RHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-14 20:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-15 11:30 | Kishori Lal | 2025-06-16 11:50 | Not Ready. |  |  |  | 74.6967 | 20.3388 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/684 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall First Lift & Encasing HPC | 120723 | 120723 | RHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-14 20:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-15 11:40 | Kishori Lal | 2025-06-16 11:51 | Not Ready. |  |  |  | 74.6965 | 20.3389 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/685 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall Raft | 140710 | 140725 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-14 20:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-15 10:00 | Rushikesh Gunjal | 2025-06-17 11:44 | Without inspection work completed |  |  |  | 74.7816 | 20.4905 | Inspected | Inspected - Fail | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2011 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Bottom Haunch Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-03 08:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-03 16:00 | Rushikesh Gunjal | 2026-01-07 11:09 | Work done | 2026-01-08 16:09 | Brajesh Upadhyay | work has been done | 74.7075 | 20.3636 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2010 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Toe Wall Final Lift | 129620 | 129675 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-03 08:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-03 11:00 | Rushikesh Gunjal | 2026-01-07 16:24 | Work done | 2026-01-08 16:09 | Brajesh Upadhyay | work has been done | 74.7483 | 20.3989 | Inspected | RFI Approved | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/703 | Checking Of Laying DLC Top | 130870 | 132000 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-17 18:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-18 15:30 | Rushikesh Gunjal | 2025-06-19 16:12 | Checked and ok | 2025-06-20 08:15 | Brajesh Upadhyay | work has been done | 74.754 | 20.4119 | Inspected | RFI Approved | 1130 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2012 | Checking Of Layout Marking , Excavation & Laying PCC For Approach Slab A1, A2 Of MNB | 129698 | 129698 | LHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-03 08:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-03 17:00 | Rushikesh Gunjal | 2026-01-07 15:23 | Work done | 2026-01-08 16:09 | Brajesh Upadhyay | work has been done | 74.7478 | 20.3987 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2013 | Checking Of Layout Marking , Excavation & Laying PCC For Cut Off Wall Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-03 09:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-03 15:00 | Rushikesh Gunjal | 2026-01-07 15:30 | Work already done | 2026-01-08 16:09 | Brajesh Upadhyay | work has been done | 74.7484 | 20.3991 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1082 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 133180 | 133250 | BHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 13:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-26 18:00 | Rushikesh Gunjal | 2025-08-30 12:03 | Oky | 2025-09-01 09:39 | Brajesh Upadhyay | work has been done | 74.7582 | 20.4285 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2014 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Midwall Bottom Haunch Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-03 17:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-04 14:30 | Rushikesh Gunjal | 2026-01-07 11:15 | Work done | 2026-01-08 16:09 | Brajesh Upadhyay | work has been done | 74.7074 | 20.3637 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2015 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Cut Off Wall Casting of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-03 17:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-04 10:00 | Rushikesh Gunjal | 2026-01-07 16:26 | Work already done | 2026-01-08 16:10 | Brajesh Upadhyay | work has been done | 74.7484 | 20.3991 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1084 | Checking Of Level & FDD test for GSB Top Layer | 133240 | 133860 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 14:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-27 08:30 | Rushikesh Gunjal | 2025-08-30 11:36 | Check found OK | 2025-09-01 09:40 | Brajesh Upadhyay | work has been done | 74.7587 | 20.437 | Inspected | RFI Approved | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/757 | Checking Of Laying PQC Top | 121020 | 121640 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-26 18:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-26 20:30 | Rushikesh Gunjal | 2025-06-30 13:26 | Check and found OK | 2025-06-30 21:43 | Sanjay Sharma | work has been done | 74.6988 | 20.3438 | Inspected | RFI Approved | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1085 | Checking Of Level & FDD test for GSB Top Layer | 133860 | 134500 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 14:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-27 11:30 | Rushikesh Gunjal | 2025-08-30 11:19 | Check found OK | 2025-09-01 09:40 | Brajesh Upadhyay | work has been done | 74.758 | 20.442 | Inspected | RFI Approved | 640 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1126 | Checking Of Level & FDD Test For GSB Top | 136400 | 137280 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-29 16:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-30 14:30 | Rushikesh Gunjal | 2025-09-05 11:37 | Check found OK | 2025-09-14 12:12 | Brajesh Upadhyay | work has been done | 74.7659 | 20.462 | Inspected | RFI Approved | 880 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/758 | Checking Of Laying DLC Top | 124340 | 125100 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-26 18:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-27 09:00 | Rushikesh Gunjal | 2025-06-27 15:50 | Check and found OK | 2025-06-27 22:54 | Sanjay Sharma | work has been done | 74.71 | 20.3669 | Inspected | RFI Approved | 760 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/759 | Checking Of Laying DLC Top | 125100 | 125890 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-26 18:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-27 17:10 | Rushikesh Gunjal | 2025-06-30 16:41 | Check and found satisfactory | 2025-06-30 21:43 | Sanjay Sharma | work has been done | 74.7211 | 20.3768 | Inspected | RFI Approved | 790 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/762 | Checking Of Level & FDD test for GSB Top Layer | 126500 | 127170 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-26 18:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-27 11:30 | Rushikesh Gunjal | 2025-06-27 16:30 | Check and ok | 2025-06-27 22:54 | Sanjay Sharma | work has been done | 74.7121 | 20.3693 | Inspected | RFI Approved | 670 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/760 | Checking Of Laying PQC Top | 121640 | 122200 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-26 18:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-27 17:00 | Rushikesh Gunjal | 2025-06-30 22:30 | Check and found OK | 2025-07-01 15:39 | Brajesh Upadhyay | work has been done | 74.6995 | 20.3478 | Inspected | RFI Approved | 560 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/761 | Checking Of Level & FDD test for GSB Top Layer | 125890 | 126500 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-26 18:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-27 07:30 | Rushikesh Gunjal | 2025-06-27 16:27 | Check and ok | 2025-06-27 22:54 | Sanjay Sharma | work has been done | 74.7121 | 20.3693 | Inspected | RFI Approved | 610 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/763 | Checking Of Level & FDD test for GSB Top Layer | 127170 | 127870 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-26 18:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-27 15:00 | Rushikesh Gunjal | 2025-07-01 15:30 | Check and found Satisfactory | 2025-07-01 15:40 | Brajesh Upadhyay | work has been done | 74.7283 | 20.3839 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/767 | Checking Layout Marking & Excavation & PCC For Retaining Wall | 140600 | 140750 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-26 19:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-27 15:00 | Saurabh SE | 2025-06-27 18:14 | PCC not done |  |  |  | 74.7814 | 20.4898 | Inspected | Inspected - Rejected - Work Not Done | 150 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/766 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall Raft | 140730 | 140850 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-26 19:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-27 15:50 | Rushikesh Gunjal | 2025-06-27 18:25 | Check and found Ok | 2025-06-27 22:53 | Sanjay Sharma | work has been done | 74.7816 | 20.4905 | Inspected | RFI Approved | 120 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/844 | Checking Reinforcement, shuttering and pouring concrete for Wall First Lift Of Retaining Wall | 132910 | 132940 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-09 19:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-10 14:00 | Rushikesh Gunjal | 2025-07-10 12:44 | Reinforcement is not in alignment |  |  |  | 74.7582 | 20.4262 | Inspected | Inspected - Fail | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/811 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall First lift | 140730 | 140850 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-05 18:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-06 11:30 | Rushikesh Gunjal | 2025-07-09 11:58 | Check and found OK | 2025-07-10 08:53 | Brajesh Upadhyay | work has beeen done | 74.7816 | 20.491 | Inspected | RFI Approved | 120 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/956 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall Raft | 140620 | 140630 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-24 17:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-25 15:30 | Rushikesh Gunjal | 2025-07-25 11:51 | Work done without inspection |  |  |  | 74.7814 | 20.4894 | Inspected | Inspected - Fail | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1127 | Checking Of Laying DLC Top | 135550 | 136400 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-29 16:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-30 16:50 | Rushikesh Gunjal | 2025-09-05 11:56 | Check found Satisfactory result | 2025-09-14 12:12 | Brajesh Upadhyay | work has been done | 74.7649 | 20.4586 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/727 | Checking Of PQC Cutting & Sealant Filling | 123900 | 124600 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-21 16:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-22 15:20 | Rushikesh Gunjal | 2025-06-23 16:42 | Checked and OK | 2025-06-24 10:24 | Sanjay Sharma | work has been done | 74.722 | 20.379 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/721 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135150 | 135170 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-20 18:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-21 18:29 | Rushikesh Gunjal | 2025-06-21 12:36 | Checked and found OK | 2025-06-24 10:25 | Sanjay Sharma | ok | 74.759 | 20.4461 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/720 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135024 | 135050 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-20 18:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-21 18:28 | Rushikesh Gunjal | 2025-06-21 12:52 | Work not done |  |  |  | 74.7587 | 20.4452 | Inspected | Inspected - Rejected - Work Not Done | 26 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/722 | Checking Laying Of PCC for Drain | 135090 | 135130 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-20 18:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-21 18:31 | Rushikesh Gunjal | 2025-06-21 12:46 | Ok | 2025-06-25 11:56 | Sanjay Sharma | work has been done | 74.7588 | 20.4456 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/795 | Checking Shuttering and pouring concrete for Drain PCC | 135024 | 135050 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-03 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-04 12:30 | Rushikesh Gunjal | 2025-07-04 17:58 | Check and found satisfactory | 2025-07-05 09:57 | Brajesh Upadhyay | work has been done | 74.7587 | 20.445 | Inspected | RFI Approved | 26 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/723 | Checking Of Laying PQC Top | 129800 | 130170 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-20 19:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-21 19:19 | Rushikesh Gunjal | 2025-06-21 13:37 | Ok | 2025-06-24 10:25 | Sanjay Sharma | work has been done | 74.7498 | 20.4018 | Inspected | RFI Approved | 370 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/724 | Checking Of Laying PQC Top | 130170 | 131120 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-20 19:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-21 19:19 | Rushikesh Gunjal | 2025-06-21 13:28 | Checked and found Ok | 2025-06-25 11:56 | Sanjay Sharma | work has been done | 74.7516 | 20.4053 | Inspected | RFI Approved | 950 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1116 | Checking Of Exiting BT Dismantling , Excavation Embankment Top, Level And FDD Test | 120400 | 121020 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-28 16:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-29 09:30 | Rushikesh Gunjal | 2025-09-13 17:01 | OK | 2025-09-14 12:15 | Brajesh Upadhyay | work has been done | 74.696 | 20.3381 | Inspected | RFI Approved | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1102 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 117000 | 117650 | BHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 17:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 16:30 | Rushikesh Gunjal | 2025-09-13 16:54 | OK | 2025-09-14 12:19 | Brajesh Upadhyay | work has been done | 74.696 | 20.3381 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/729 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135242 | 135340 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-21 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-22 14:05 | Kishori Lal | 2025-06-23 12:31 | Work already done without checking. |  |  |  | 74.7595 | 20.4469 | Inspected | Inspected - Rejected - Work Not Done | 98 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/730 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135110 | 135130 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-21 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-22 11:00 | Kishori Lal | 2025-06-23 12:53 | Work done. | 2025-06-25 11:36 | Sanjay Sharma | ok | 74.7591 | 20.4457 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/731 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135130 | 135150 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-21 18:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-22 11:30 | Kishori Lal | 2025-06-23 12:39 | Work done. | 2025-06-24 10:24 | Sanjay Sharma | work has been done | 74.759 | 20.4459 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/732 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135024 | 135050 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-21 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-22 10:15 | Kishori Lal | 2025-06-23 13:08 | Not Ready. |  |  |  | 74.7586 | 20.445 | Inspected | Inspected - Rejected - Work Not Done | 26 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/733 | Checking Reinforcement, shuttering and pouring concrete for A1,A2 & Intermediate Wall Second Lift Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-21 18:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-22 15:20 | Kishori Lal | 2025-06-23 17:18 | Not Ready. |  |  |  | 74.7483 | 20.3993 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/734 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall Final Lift HPC | 120737 | 120737 | RHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-21 18:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-22 12:15 | Kishori Lal | 2025-06-23 18:10 | Already work done. |  |  |  | 74.6966 | 20.3388 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/735 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall Final Lift HPC | 120723 | 120723 | RHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-21 18:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-22 12:30 | Kishori Lal | 2025-06-23 18:11 | Already work done. |  |  |  | 74.6965 | 20.3386 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/736 | Checking Shuttering & Pouring Concrete For Head Wall First Lift Of HPC | 133023 | 133023 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-21 18:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-22 14:10 | Kishori Lal | 2025-06-23 13:35 | HPC Head wall 1st Work done without checking & without raising RFI. |  |  |  | 74.7582 | 20.4273 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1028 | Checking Of Level & FDD Test & Filling Of Earthen Shoulder | 125200 | 125900 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-17 17:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-18 09:30 | Saurabh SE | 2025-08-19 17:25 | No filling of Earthen shoulder |  |  |  | 74.7218 | 20.3784 | Inspected | Inspected - Rejected - Work Not Done | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1989 | Checking Of Layout Marking , Excavation & Laying PCC For Toe Wall | 129620 | 129675 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-24 18:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-25 14:00 | Rushikesh Gunjal | 2025-12-25 16:27 | Work done | 2025-12-25 17:30 | Brajesh Upadhyay | work has been done | 74.7482 | 20.3989 | Inspected | RFI Approved | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1037 | Checking Of Utility Pipe Laying | 137200 | 137200 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-18 17:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-19 12:30 | Saurabh SE | 2025-08-19 14:57 | Not found in this chainge |  |  |  | 74.7665 | 20.4642 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/738 | Checking Shuttering & Pouring Concrete For Head Wall Second Lift Of HPC | 133023 | 133023 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-22 17:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-23 14:30 | Kishori Lal | 2025-06-23 13:37 | Already work done. |  |  |  | 74.7581 | 20.4274 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/739 | Laying Of PQC Top | 132050 | 132500 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-22 17:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-23 17:30 | Rushikesh Gunjal | 2025-06-24 21:02 | Check and found ok | 2025-06-25 11:36 | Sanjay Sharma | ok | 74.7585 | 20.4233 | Inspected | RFI Approved | 450 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/740 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135090 | 135130 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-22 18:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-23 14:30 | Kishori Lal | 2025-06-23 13:04 | Wrong Chainage. |  |  |  | 74.7587 | 20.4456 | Inspected | Inspected - Fail | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/843 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134700 | 134725 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-09 19:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-10 12:30 | Rushikesh Gunjal | 2025-07-10 12:26 | Work not done |  |  |  | 74.7579 | 20.4422 | Inspected | Inspected - Rejected - Work Not Done | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/768 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 133023 | 133023 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-27 17:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-28 11:00 | Rushikesh Gunjal | 2025-06-28 12:48 | RHS head wall final lift Alignment is not proper |  |  |  | 74.7582 | 20.4272 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/798 | Checking Layout Marking & Excavation & Pcc For HPC | 120895 | 120895 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-03 18:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-04 16:00 | Rushikesh Gunjal | 2025-07-04 16:02 | Check and found OK | 2025-07-05 09:49 | Brajesh Upadhyay | work has been done | 74.6977 | 20.3399 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/854 | Checking Reinforcement, shuttering and pouring concrete for A1 & A2 Wall First Lift Of Box Culvert | 133216 | 133216 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-11 19:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-12 15:00 | Rushikesh Gunjal | 2025-07-12 11:42 | Reinforcement & shuttering work is not Completed Clear cover not maintain Spacing is not maintained |  |  |  | 74.7582 | 20.4289 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/770 | Checking Of Laying PQC Top | 122200 | 122970 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-27 18:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-28 10:30 | Rushikesh Gunjal | 2025-07-03 20:33 | Check and found satisfactory | 2025-07-04 09:39 | Brajesh Upadhyay | work has been done | 74.7053 | 20.3581 | Inspected | RFI Approved | 770 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/773 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135024 | 135050 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-27 18:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-28 11:00 | Rushikesh Gunjal | 2025-06-28 12:27 | Check and found OK | 2025-06-28 16:31 | Sanjay Sharma | work has been done | 74.7586 | 20.4451 | Inspected | RFI Approved | 26 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/774 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135100 | 135110 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-27 18:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-28 11:20 | Rushikesh Gunjal | 2025-06-28 12:14 | Work not done |  |  |  | 74.7589 | 20.4457 | Inspected | Inspected - Rejected - Work Not Done | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/797 | Checking Layout Marking & Excavation For Drain | 135050 | 135090 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-03 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-04 11:30 | Rushikesh Gunjal | 2025-07-04 18:00 | Layout and excavation not ready |  |  |  | 74.7587 | 20.4451 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/794 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135000 | 135017 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-03 18:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-04 11:00 | Rushikesh Gunjal | 2025-07-04 18:04 | Reinforcement and shuttering work not ready |  |  |  | 74.7587 | 20.445 | Inspected | Inspected - Rejected - Work Not Done | 17 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/796 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135130 | 135170 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-03 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-04 12:45 | Rushikesh Gunjal | 2025-07-04 18:09 | Check and found Ok | 2025-07-05 09:58 | Brajesh Upadhyay | work has been done | 74.7589 | 20.4458 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/801 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall First lift | 140730 | 140850 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-03 18:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-04 15:00 | Rushikesh Gunjal | 2025-07-04 18:24 | Concrete poure without reinforcement Checking |  |  |  | 74.7816 | 20.4906 | Inspected | Inspected - Fail | 120 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/804 | Checking Reinforcement, shuttering and pouring concrete for Bottom Haunch box culvert | 133216 | 133216 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-04 18:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-05 14:30 | Saurabh SE | 2025-07-07 16:48 | Work not done properly |  |  |  | 74.7583 | 20.4289 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/805 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall First lift | 140730 | 140850 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-04 18:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-05 10:00 | Saurabh SE | 2025-07-05 11:51 | Work done without checking |  |  |  | 74.7816 | 20.4907 | Inspected | Inspected - Fail | 120 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/806 | Checking Reinforcement, Shuttering & Pouring Concrete For Raft Of Retaining Wall | 132910 | 132970 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-04 18:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-05 14:30 | Saurabh SE | 2025-07-07 16:39 | Work done | 2025-07-08 08:49 | Brajesh Upadhyay | work has been done | 74.7584 | 20.4261 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/410 | Checking of Laying of PQC | 124920 | 125570 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 18:30 | Rushikesh Gunjal | 2025-05-30 15:10 | Check found ok | 2025-05-30 19:31 | Brajesh Upadhyay | pqc laying work has been done | 74.7223 | 20.3797 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/808 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135090 | 135100 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-04 18:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-05 14:30 | Saurabh SE | 2025-07-07 17:21 | Work done | 2025-07-08 08:50 | Brajesh Upadhyay | work has been done | 74.7588 | 20.4451 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/775 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall First lift | 140730 | 140850 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-27 19:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-28 15:00 | Rushikesh Gunjal | 2025-06-28 11:23 | Shuttering work is not Done |  |  |  | 74.7817 | 20.4907 | Inspected | Inspected - Rejected - Work Not Done | 120 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/244 | Checking of Layout Marking & Excavation for Retaining Wall | 140450 | 141000 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 15:00 | Rushikesh Gunjal | 2025-04-28 16:52 | Checked and found OK | 2025-04-28 17:12 | Brajesh Upadhyay | work has been done | 74.7816 | 20.4901 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/741 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135090 | 135110 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-23 18:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-24 12:30 | Kishori Lal | 2025-06-25 14:57 | Work done. | 2025-06-26 10:16 | Sanjay Sharma | work has been done | 74.7588 | 20.4455 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/742 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135024 | 135050 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-23 18:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-24 12:45 | Kishori Lal | 2025-06-25 15:10 | Not Ready. |  |  |  | 74.7586 | 20.445 | Inspected | Inspected - Rejected - Work Not Done | 26 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/743 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135110 | 135130 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-23 18:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-24 13:00 | Kishori Lal | 2025-06-25 15:01 | Work done. | 2025-06-26 10:15 | Sanjay Sharma | work has been done | 74.759 | 20.4459 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/777 | Checking PCC Of Retaining Wall | 140600 | 140750 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-28 09:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-28 16:30 | Rushikesh Gunjal | 2025-06-28 11:25 | Work not completed |  |  |  | 74.7817 | 20.4905 | Inspected | Inspected - Rejected - Work Not Done | 150 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/803 | Checking Of Shuttering & Concrete Pouring For Head Wall First lift | 120895 | 120895 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-04 18:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-05 15:30 | Saurabh SE | 2025-07-05 18:08 | Work not done |  |  |  | 74.6975 | 20.3398 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/802 | Checking Layout Marking & Excavation & Pcc For HPC | 120400 | 120400 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-04 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-05 15:00 | Saurabh SE | 2025-07-05 18:02 | PCC not done | 2025-07-06 07:26 | Brajesh Upadhyay | work has been done | 74.6976 | 20.3398 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/845 | Checking Reinforcement, shuttering and pouring concrete for Wall Final Lift Of Retaining Wall | 140640 | 140680 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-09 19:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-10 15:00 | Rushikesh Gunjal | 2025-07-10 11:52 | Check and found OK | 2025-07-11 09:05 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4896 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/846 | Checking Of Level & FDD test for GSB Top Layer | 130890 | 131670 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-10 18:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-11 17:00 | Rushikesh Gunjal | 2025-07-11 17:03 | Check and found satisfactory result | 2025-07-12 08:06 | Brajesh Upadhyay | work has been done | 74.749 | 20.4003 | Inspected | RFI Approved | 780 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/771 | Checking Of Laying DLC Top | 126500 | 127170 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-27 18:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-28 18:00 | Rushikesh Gunjal | 2025-07-05 12:06 | Check and found OK | 2025-07-09 10:17 | Brajesh Upadhyay | work has been done | 74.7317 | 20.3864 | Inspected | RFI Approved | 670 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/764 | Checking Of Level & FDD test for GSB Top Layer | 127870 | 128720 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-26 18:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-27 17:00 | Rushikesh Gunjal | 2025-07-05 12:29 | Check and found satisfactory | 2025-07-18 09:20 | Brajesh Upadhyay | work has been done | 74.7343 | 20.3884 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/324 | Checking Shuttering and laying of PCC Below Pipe | 134083 | 134083 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 17:00 | Kishori Lal | 2025-05-05 12:34 | Work done. | 2025-05-05 17:51 | Brajesh Upadhyay | work done | 74.7588 | 20.4367 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/807 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135110 | 135130 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-04 18:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-05 11:30 | Saurabh SE | 2025-07-05 16:05 | Work done | 2025-07-06 07:29 | Brajesh Upadhyay | work has been done | 74.759 | 20.4459 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/429 | Checking Shuttering and laying of PCC for head wall & Below pipe | 138983 | 138983 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 12:42 | Kishori Lal | 2025-05-09 11:38 | Not Done. |  |  |  | 74.7739 | 20.4777 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/809 | Checking Of Shuttering & Concrete Pouring For Head Wall First lift of HPC | 120895 | 120895 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-05 18:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-06 15:30 | Rushikesh Gunjal | 2025-07-08 15:51 | Check and found The outside of the headwall is not in alignment & found honeycombs |  |  |  | 74.6975 | 20.3398 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/812 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134990 | 135017 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-05 19:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-06 11:30 | Rushikesh Gunjal | 2025-07-08 17:04 | check and found satisfactory | 2025-07-09 10:09 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4449 | Inspected | RFI Approved | 27 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/813 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135024 | 135050 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-05 19:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-06 19:00 | Rushikesh Gunjal | 2025-07-08 17:00 | Reinforcement & shuttering work not complete |  |  |  | 74.7587 | 20.4449 | Inspected | Inspected - Rejected - Work Not Done | 26 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/814 | Checking Of Layout Marking , Excavation & Laying Pcc For Drain | 120280 | 120380 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-05 19:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-06 14:05 | Rushikesh Gunjal | 2025-07-09 15:46 | Work not done |  |  |  | 74.6941 | 20.3363 | Inspected | Inspected - Rejected - Work Not Done | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/778 | Checking Of Laying PQC Top | 124470 | 125360 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-29 09:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-29 16:50 | Rushikesh Gunjal | 2025-07-08 16:22 | Check and found OK | 2025-07-09 10:16 | Brajesh Upadhyay | work has been done | 74.7133 | 20.3708 | Inspected | RFI Approved | 890 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2026 | Checking Of Layout Marking , Excavation & Laying PCC For Approach Slab A1,A2 Of MNB | 129698 | 129698 | RHS | Bridge | Minor Bridge Reconstruction | Approaches | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-07 18:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-08 14:00 | Rushikesh Gunjal | 2026-01-08 18:13 | Work done | 2026-01-09 09:24 | Brajesh Upadhyay | work has been done | 74.7483 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/816 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120350 | 120380 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-06 18:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-07 14:00 | Saurabh SE | 2025-07-07 14:17 | Work done | 2025-07-08 08:48 | Brajesh Upadhyay | work has been done | 74.694 | 20.3365 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/815 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134730 | 134820 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-06 18:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-07 10:00 | Saurabh SE | 2025-07-07 17:13 | Work done without checking |  |  |  | 74.758 | 20.4424 | Inspected | Inspected - Fail | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/817 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135170 | 135210 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-06 18:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-07 10:30 | Saurabh SE | 2025-07-07 17:24 | Work not completed |  |  |  | 74.7589 | 20.4462 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/779 | Checking Of Shuttering & Pouring PCC OF Retaining Wall | 140600 | 140750 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-29 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-30 14:05 | Rushikesh Gunjal | 2025-06-30 18:40 | Not done |  |  |  | 74.7815 | 20.4901 | Inspected | Inspected - Rejected - Work Not Done | 150 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/819 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall second Lift Of HPC | 120895 | 120895 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-06 19:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-07 14:30 | Saurabh SE | 2025-07-07 14:28 | Work not done |  |  |  | 74.6975 | 20.3397 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/818 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall Final Lift | 140600 | 140640 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-06 19:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-07 11:00 | Saurabh SE | 2025-07-07 17:44 | Work done without any checking |  |  |  | 74.7813 | 20.4893 | Inspected | Inspected - Fail | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/781 | Checking Reinforcement, shuttering and pouring concrete for A1,A2 & Intermediate Wall Second Lift Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-29 18:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-01 14:15 | Rushikesh Gunjal | 2025-06-30 17:14 | Work not Done |  |  |  | 74.7483 | 20.3992 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/785 | Checking Of Laying PQC Top | 126100 | 126980 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-29 18:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-30 11:15 | Rushikesh Gunjal | 2025-07-12 15:18 | Check and found satisfactory result | 2025-07-15 09:02 | Brajesh Upadhyay | work has been done | 74.7246 | 20.3817 | Inspected | RFI Approved | 880 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/783 | Checking Layout Marking & Excavation For Drain | 134980 | 135010 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-29 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-30 14:15 | Rushikesh Gunjal | 2025-06-30 18:19 | Check and found ok | 2025-06-30 21:42 | Sanjay Sharma | work has been done | 74.7587 | 20.4452 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/784 | Checking Layout Marking & Excavation For Drain | 135010 | 135030 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-29 18:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-30 11:19 | Saurabh SE | 2025-07-02 12:39 | Work done | 2025-07-03 10:08 | Brajesh Upadhyay | work has been done | 74.7586 | 20.445 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/786 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135024 | 135050 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-29 18:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-30 09:30 | Rushikesh Gunjal | 2025-06-30 18:22 | Ok | 2025-06-30 21:42 | Sanjay Sharma | work has been done | 74.7587 | 20.445 | Inspected | RFI Approved | 26 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/787 | Checking Layout Marking & Excavation & PCC For Drain | 135000 | 135050 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-29 18:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-30 11:25 | Saurabh SE | 2025-07-02 12:34 | PCC not done |  |  |  | 74.7587 | 20.445 | Inspected | Inspected - Rejected - Work Not Done | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1190 | Checking Of Laying DLC Top | 140840 | 141650 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 17:30 | Rushikesh Gunjal | 2025-09-13 15:40 | Work not done |  |  |  | 74.7819 | 20.4916 | Inspected | Inspected - Rejected - Work Not Done | 810 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/788 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135090 | 135110 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-29 18:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-30 14:05 | Rushikesh Gunjal | 2025-06-30 18:24 | Work not done |  |  |  | 74.7589 | 20.4457 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/780 | Checking Of Layout Marking , Excavation For Retaining Wall | 140750 | 140800 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-29 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-30 11:50 | Rushikesh Gunjal | 2025-06-30 18:41 | Ok | 2025-06-30 21:43 | Sanjay Sharma | work has been done | 74.7818 | 20.4908 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/510 | Checking of Laying of PQC | 127670 | 128500 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 09:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-13 17:00 | Rushikesh Gunjal | 2025-06-06 23:21 | Check and found ok | 2025-06-08 09:10 | Brajesh Upadhyay | work has been done | 74.7388 | 20.3916 | Inspected | RFI Approved | 830 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/791 | Checking Shuttering and laying of PCC for Drain | 134980 | 135010 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-30 20:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-01 11:25 | Rushikesh Gunjal | 2025-07-01 15:59 | OK | 2025-07-02 11:18 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4448 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/792 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135090 | 135110 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-30 20:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-01 11:55 | Rushikesh Gunjal | 2025-07-01 16:01 | Shuttering & Reinforcing work not complete |  |  |  | 74.7589 | 20.4455 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/793 | Checking of Laying of PQC | 128460 | 129360 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-30 20:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-01 17:30 | Rushikesh Gunjal | 2025-07-18 12:34 | Check and found OK | 2025-07-19 19:37 | Brajesh Upadhyay | work has been done | 74.743 | 20.3947 | Inspected | RFI Approved | 900 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1153 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 120250 | 120270 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-31 18:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-01 11:50 | Kishori Lal | 2025-09-01 12:18 | Not Ready. |  |  |  | 74.6931 | 20.336 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/769 | Checking Of Laying DLC Top | 125890 | 126500 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-27 18:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-28 08:15 | Rushikesh Gunjal | 2025-07-01 15:06 | Check and found OK | 2025-07-01 15:36 | Brajesh Upadhyay | work has been done | 74.7243 | 20.3815 | Inspected | RFI Approved | 610 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/824 | Checking Of Shuttering & Laying PCC For Retaining Wall | 132970 | 133000 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-07 18:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-08 12:15 | Rushikesh Gunjal | 2025-07-09 16:46 | Work not done |  |  |  | 74.7583 | 20.4267 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/820 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134780 | 134820 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-07 18:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-08 10:30 | Saurabh SE | 2025-07-08 12:35 | Work already done so many time before |  |  |  | 74.758 | 20.4429 | Inspected | Inspected - Fail | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/825 | Checking Reinforcement, shuttering and pouring concrete for Wall First Lift Of Retaining Wall | 140640 | 140730 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-07 18:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-08 15:00 | Rushikesh Gunjal | 2025-07-09 12:01 | Work done without inspection |  |  |  | 74.7815 | 20.4901 | Inspected | Inspected - Fail | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/826 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135170 | 135210 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-07 19:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-08 12:05 | Rushikesh Gunjal | 2025-07-09 16:55 | Ok | 2025-07-10 08:41 | Brajesh Upadhyay | work has been done | 74.7592 | 20.4463 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1149 | Checking Of Laying DLC Top | 137280 | 138150 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-31 18:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-01 17:30 | Saurabh SE | 2025-09-01 17:39 | Work not done |  |  |  | 74.7657 | 20.4618 | Inspected | Inspected - Rejected - Work Not Done | 870 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/821 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135024 | 135050 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-07 18:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-08 11:00 | Saurabh SE | 2025-07-08 12:07 | Work not done |  |  |  | 74.7586 | 20.4449 | Inspected | Inspected - Rejected - Work Not Done | 26 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/822 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135242 | 135340 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-07 18:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-08 11:30 | Saurabh SE | 2025-07-08 12:16 | Work already done so many time before |  |  |  | 74.7593 | 20.4468 | Inspected | Inspected - Fail | 98 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/810 | Checking Of Shuttering & Concrete Pouring For Head Wall First lift Of HPC | 120400 | 120400 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-05 18:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-06 15:50 | Rushikesh Gunjal | 2025-07-08 15:43 | Work not done |  |  |  | 74.6942 | 20.3367 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/823 | Checking Of Reinforcement, Shuttering & Pouring Concrete For A1,A2 Wall First Lift Of Box Culvert | 133216 | 133216 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-07 18:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-08 14:00 | Saurabh SE | 2025-07-08 16:54 | Work not done |  |  |  | 74.7583 | 20.4289 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/827 | Checking Of Level & FDD test for GSB Top Layer | 129580 | 129670 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-08 19:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-09 10:15 | Rushikesh Gunjal | 2025-07-09 16:29 | Check and found OK | 2025-07-10 08:45 | Brajesh Upadhyay | work has been done | 74.7414 | 20.3934 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/833 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134780 | 134820 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-08 19:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-09 11:30 | Rushikesh Gunjal | 2025-07-09 16:52 | Work not done |  |  |  | 74.758 | 20.4423 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/853 | Checking Reinforcement, shuttering and pouring concrete for Wall First Lift Of Retaining Wall | 132940 | 132978 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-11 19:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-12 14:30 | Rushikesh Gunjal | 2025-07-12 11:57 | Reinforcement alignment is not maintained |  |  |  | 74.7582 | 20.4266 | Inspected | Inspected - Fail | 38 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/852 | Checking Reinforcement, shuttering and pouring concrete for Wall Final Lift Of Retaining Wall | 132910 | 132940 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-11 19:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-12 14:00 | Rushikesh Gunjal | 2025-07-12 11:59 | Work done without inspection |  |  |  | 74.7582 | 20.4265 | Inspected | Inspected - Fail | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/772 | Checking Of Laying PQC Top | 122970 | 123700 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-27 18:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-28 18:30 | Rushikesh Gunjal | 2025-07-08 16:04 | Checked and found ok | 2025-07-09 10:18 | Brajesh Upadhyay | work has been done | 74.7073 | 20.3616 | Inspected | RFI Approved | 730 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/836 | Checking Of Laying DLC Top | 131660 | 132260 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-09 18:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-10 15:00 | Rushikesh Gunjal | 2025-07-10 17:03 | Work not done |  |  |  | 74.7533 | 20.4095 | Inspected | Inspected - Rejected - Work Not Done | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2064 | Checking Of Providing & Fixing of Metal Beam Crash Barrier | 118880 | 119170 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-05 17:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-06 14:00 | Rushikesh Gunjal | 2026-02-06 18:34 | W-Beam is not fixed |  |  |  | 74.69 | 20.3269 | Inspected | Inspected - Rejected - Work Not Done | 290 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/521 | Checking Level and FDD checking of GSB top layer | 136970 | 137990 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-14 12:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-14 17:07 | Rushikesh Gunjal | 2025-05-17 12:04 | Ok | 2025-05-17 17:57 | Brajesh Upadhyay | Work has been done | 74.7677 | 20.4666 | Inspected | RFI Approved | 1020 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/838 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134640 | 134670 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-09 18:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-10 10:00 | Rushikesh Gunjal | 2025-07-10 12:29 | Ok | 2025-07-11 09:06 | Brajesh Upadhyay | work has been done | 74.758 | 20.4422 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/841 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135000 | 135017 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-09 19:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-10 11:30 | Rushikesh Gunjal | 2025-07-10 12:22 | Reinforcement work & shuttering work not Ready |  |  |  | 74.7586 | 20.445 | Inspected | Inspected - Rejected - Work Not Done | 17 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/839 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134670 | 134710 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-09 18:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-10 10:45 | Rushikesh Gunjal | 2025-07-10 12:28 | Ok | 2025-07-11 09:07 | Brajesh Upadhyay | work has been done | 74.758 | 20.4422 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/840 | Checking Of Layout Marking , Excavation & Laying Pcc For Drain | 135050 | 135100 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-09 19:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-10 14:00 | Rushikesh Gunjal | 2025-07-10 12:16 | Excavation not completed Pcc not done |  |  |  | 74.7588 | 20.4452 | Inspected | Inspected - Rejected - Work Not Done | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/842 | Checking Reinforcement, shuttering and pouring concrete for Drain wall | 135024 | 135050 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-09 19:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-10 11:50 | Rushikesh Gunjal | 2025-07-10 12:20 | Check and found Ok | 2025-07-11 09:07 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4451 | Inspected | RFI Approved | 26 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1995 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 135130 | 135140 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-26 15:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-27 14:00 | Rushikesh Gunjal | 2025-12-27 11:21 | Work already done | 2025-12-28 09:28 | Brajesh Upadhyay | work has been done | 74.7591 | 20.4461 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1994 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 134722 | 134750 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-26 15:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-27 15:00 | Rushikesh Gunjal | 2025-12-27 11:27 | Wrong RFI mention Chainage HP culvert is exist CH. 135+723 |  |  |  | 74.758 | 20.4423 | Inspected | Inspected - Rejected - Work Not Done | 28 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1264 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 127176 | 127176 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-14 10:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 13:00 | Kishori Lal | 2025-09-14 15:32 | Work done. | 2025-09-14 18:54 | Brajesh Upadhyay | work has been done | 74.7297 | 20.3851 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2069 | Checking Of Reinforcement, Shuttering & Pouring Concrete For R.Wall A1,A2 2nd Lift Of MNB | 123800 | 123800 | LHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-07 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-08 11:00 | Kishori Lal | 2026-02-14 13:12 | Work done. | 2026-02-16 09:21 | Brajesh Upadhyay | work has been done | 74.7074 | 20.3637 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2068 | Checking Of Providing & Fixing of Metal Beam Crash Barrier | 140450 | 140580 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-07 17:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-07 18:30 | Rushikesh Gunjal | 2026-02-18 14:49 | Work done | 2026-02-19 10:02 | Brajesh Upadhyay | work has been done | 74.7804 | 20.4882 | Inspected | RFI Approved | 130 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2007 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134700 | 134715 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-30 18:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-31 11:00 | Rushikesh Gunjal | 2025-12-31 15:27 | Work already done | 2026-01-01 14:07 | Brajesh Upadhyay | work has been done | 74.758 | 20.4423 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1993 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 134700 | 134715 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-26 15:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-27 10:00 | Rushikesh Gunjal | 2025-12-27 11:28 | Work done | 2025-12-28 09:28 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4423 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/357 | Checking pipe laying and joint filling | 134083 | 134083 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 17:00 | Kishori Lal | 2025-05-06 12:11 | Not satisfactory. |  |  |  | 74.7581 | 20.4373 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/375 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 139350 | 139950 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 12:30 | Rushikesh Gunjal | 2025-05-17 12:26 | Ok | 2025-05-17 18:18 | Brajesh Upadhyay | Work has been done | 74.7744 | 20.4791 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/435 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 137900 | 138630 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 19:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 12:00 | Rushikesh Gunjal | 2025-05-17 12:30 | Ok | 2025-05-17 18:09 | Brajesh Upadhyay | Work has been done | 74.7713 | 20.4741 | Inspected | RFI Approved | 730 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/434 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 138630 | 139350 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 19:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 12:00 | Rushikesh Gunjal | 2025-05-17 12:31 | Checked and found ok | 2025-05-17 18:10 | Brajesh Upadhyay | Work has been done | 74.7706 | 20.4724 | Inspected | RFI Approved | 720 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/402 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 136360 | 137150 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 10:00 | Rushikesh Gunjal | 2025-05-17 12:35 | Ok | 2025-05-17 18:16 | Brajesh Upadhyay | Work has been done | 74.767 | 20.4653 | Inspected | RFI Approved | 790 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/374 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 135890 | 136360 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 13:00 | Rushikesh Gunjal | 2025-05-17 12:40 | Ok | 2025-05-17 18:18 | Brajesh Upadhyay | Work has been done | 74.7633 | 20.456 | Inspected | RFI Approved | 470 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/373 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 137150 | 137900 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 12:08 | Rushikesh Gunjal | 2025-05-17 12:41 | Checked and ok | 2025-05-17 18:19 | Brajesh Upadhyay | Work has been done | 74.7633 | 20.4559 | Inspected | RFI Approved | 750 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/380 | Checking Reinforcement, shuttering and pouring concrete for Wall final lift of Retaining Wall | 132910 | 132960 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 11:30 | Rushikesh Gunjal | 2025-05-17 12:56 | Not ok |  |  |  | 74.7582 | 20.4216 | Inspected | Inspected - Rejected - Work Not Done | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/528 | Checking Level & FDD test for GSB Top layer | 139040 | 139770 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-14 14:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-15 14:00 | Rushikesh Gunjal | 2025-05-17 12:18 | Checked and found ok | 2025-05-17 17:54 | Brajesh Upadhyay | Work has been done | 74.7745 | 20.4796 | Inspected | RFI Approved | 730 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/527 | Checking FDD and Level for GSB top Layer | 138580 | 139040 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-14 14:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-15 12:00 | Rushikesh Gunjal | 2025-05-17 12:20 | Ok | 2025-05-17 17:55 | Brajesh Upadhyay | Work has been done | 74.7744 | 20.4797 | Inspected | RFI Approved | 460 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/526 | Checking Level and FDD test for GSB Top | 137750 | 138580 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-14 14:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-14 18:00 | Rushikesh Gunjal | 2025-05-17 12:07 | Ok | 2025-05-17 17:56 | Brajesh Upadhyay | Work has been done | 74.7695 | 20.4701 | Inspected | RFI Approved | 830 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/520 | Checking Level and FDD checking of GSB top layer | 135980 | 136970 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-14 12:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-14 14:00 | Rushikesh Gunjal | 2025-05-17 11:54 | Checked and found ok | 2025-05-17 17:57 | Brajesh Upadhyay | Work has been done | 74.7601 | 20.4495 | Inspected | RFI Approved | 990 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/512 | Checking Level and FDD test for GSB Top | 135150 | 135980 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 11:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-13 17:30 | Rushikesh Gunjal | 2025-05-17 11:52 | Ok | 2025-05-17 17:58 | Brajesh Upadhyay | Work has been done | 74.7601 | 20.4495 | Inspected | RFI Approved | 830 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/406 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 136360 | 137150 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 14:00 | Rushikesh Gunjal | 2025-05-17 12:39 | Ok | 2025-05-17 18:12 | Brajesh Upadhyay | Work has been done | 74.7633 | 20.4559 | Inspected | RFI Approved | 790 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/405 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 134500 | 134960 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 13:00 | Rushikesh Gunjal | 2025-05-17 12:49 | Ok | 2025-05-17 18:13 | Brajesh Upadhyay | Work has been done | 74.7579 | 20.4412 | Inspected | RFI Approved | 460 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/404 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 138630 | 139350 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 12:00 | Rushikesh Gunjal | 2025-05-17 12:24 | Checked and found ok | 2025-05-17 18:14 | Brajesh Upadhyay | Work has been done | 74.7744 | 20.4791 | Inspected | RFI Approved | 720 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/369 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 134960 | 135890 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 12:46 | Rushikesh Gunjal | 2025-05-17 12:44 | Ok | 2025-05-17 18:22 | Brajesh Upadhyay | Work has been done | 74.7601 | 20.4496 | Inspected | RFI Approved | 930 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/532 | Checking Shuttering and pouring concrete of PCC for retaining wall | 140600 | 140700 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-19 16:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-20 16:30 | Kishori Lal | 2025-05-21 16:29 | Work done. | 2025-05-21 16:59 | Brajesh Upadhyay | Work has been done | 74.7812 | 20.4892 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/117 | Checking of Layout Marking & Excavation for HPC | 132669 | 132669 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-29 13:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-30 11:16 | Kishori Lal | 2025-04-01 15:48 | Excavation and layout of HPC not as per design and drawing. |  |  |  | 74.7591 | 20.4242 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/005 | Checking of Existing BT dismantling | 121440 | 121600 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-13 19:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-14 11:30 | Rushikesh Gunjal | 2025-02-14 15:24 | Complete | 2025-02-15 11:13 | Brajesh Upadhyay | work has been done | 74.6989 | 20.3452 | Inspected | RFI Approved | 160 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/006 | Checking excavation up to embankment top after checking excavation FDD test | 124900 | 125100 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-13 19:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-14 15:00 | Rushikesh Gunjal | 2025-02-14 17:13 | Completed | 2025-02-15 11:10 | Brajesh Upadhyay | RFI not approved Subject to P&P not approved | 74.7166 | 20.3734 | Inspected | RFI Not Approved | 200 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/004 | Checking of Existing BT dismantling | 123980 | 124400 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-13 19:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-14 11:00 | Rushikesh Gunjal | 2025-02-14 15:37 | Completed | 2025-02-15 11:15 | Brajesh Upadhyay | work has been done | 74.7096 | 20.3666 | Inspected | RFI Approved | 420 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/002 | Checking of Existing BT dismantling | 121200 | 121400 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-12 13:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-13 12:30 | Rushikesh Gunjal | 2025-02-13 16:31 | Completed | 2025-02-15 11:25 | Brajesh Upadhyay | BT Scarification work has been done | 74.6989 | 20.3435 | Inspected | RFI Approved | 200 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/003 | Checking of Existing BT dismantling | 124600 | 124900 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-13 18:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-14 10:30 | Rushikesh Gunjal | 2025-02-14 15:41 | Completed | 2025-02-15 11:30 | Brajesh Upadhyay | work has been done | 74.7131 | 20.3707 | Inspected | RFI Approved | 300 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/014 | Checking of Existing BT dismantling | 124500 | 125200 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-17 20:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-18 14:00 | Rushikesh Gunjal | 2025-02-18 15:00 | Completed | 2025-02-18 15:54 | Brajesh Upadhyay | work has been done | 74.7135 | 20.371 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/017 | Checking excavation up to embankment top and FDD test after excavation | 121950 | 122000 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-17 20:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-18 14:00 | Rushikesh Gunjal | 2025-02-19 12:38 | Completed | 2025-02-19 17:36 | Brajesh Upadhyay | P&P under review | 74.6995 | 20.348 | Inspected | RFI Not Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/101 | FDD and Leval Checking of EMB Top | 121000 | 123800 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:43 | Brajesh Upadhyay | 2025-01-30 09:30 | Brajesh Upadhyay | 2025-03-07 14:43 | Work done successfully. | 2025-03-07 14:43 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 2800 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/016 | Checking of Existing BT dismantling | 121220 | 121300 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-17 20:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-18 16:00 | Rushikesh Gunjal | 2025-02-18 15:14 | Completed | 2025-02-18 15:51 | Brajesh Upadhyay | work has been done | 74.6988 | 20.3432 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II/001 | Calibration of RMC Plant at Malegaon | 0 | 0 | RHS | Road | Rigid Road |  | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-01-28 13:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-01-29 11:30 | Rushikesh Gunjal | 2025-02-18 14:35 | Checked found satisfactory results | 2025-02-19 11:36 | Brajesh Upadhyay | satisfactory | 74.7214 | 20.3762 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/020 | Checking of Existing BT dismantling | 125200 | 125600 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-18 20:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-19 02:00 | Rushikesh Gunjal | 2025-02-20 17:09 | Completed | 2025-02-20 18:34 | Brajesh Upadhyay | work has been done | 74.7191 | 20.3746 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/013 | Checking excavation up to embankment top and FDD test after excavation | 121020 | 121500 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-17 20:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-18 11:30 | Rushikesh Gunjal | 2025-02-19 13:21 | Completed | 2025-02-19 17:32 | Brajesh Upadhyay | work not done | 74.6988 | 20.3448 | Inspected | RFI Not Approved | 480 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/102 | FDD and Leval Checking of EMB Top | 123850 | 129400 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:45 | Brajesh Upadhyay | 2025-02-22 09:50 | Brajesh Upadhyay | 2025-03-07 14:45 | Work done successfully. | 2025-03-07 14:45 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 5550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/028 | Collection of aggregfrome samples for filter media mix design from base camp crusher | 125900 | 125900 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-20 08:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-20 11:38 | Rushikesh Gunjal | 2025-02-20 16:01 | Sample Collected | 2025-02-20 18:17 | Brajesh Upadhyay | sampling done | 74.7225 | 20.3759 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/029 | Collection of samples for DLC mix design from base camp crusher | 125900 | 125900 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-20 08:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-20 12:30 | Rushikesh Gunjal | 2025-02-20 15:52 | Sample collected | 2025-02-20 18:15 | Brajesh Upadhyay | sampling done | 74.7212 | 20.3762 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/425 | Checking shuttering and pouring concrete for Head Wall first lift | 135230 | 135230 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 17:00 | Kishori Lal | 2025-05-09 12:14 | Work done. | 2025-05-09 17:16 | Brajesh Upadhyay | work has been done | 74.7592 | 20.4471 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/103 | FDD and Leval Checking of EMB Top | 129800 | 133200 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:46 | Brajesh Upadhyay | 2025-02-07 10:10 | Brajesh Upadhyay | 2025-03-07 14:46 | Work done successfully. | 2025-03-07 14:46 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 3400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/033 | Checking excavation up to embankment top, Level and FDD test after excavation | 123980 | 124580 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-21 08:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-21 16:00 |  | 2025-02-24 15:26 | Work in progress | 2025-02-24 19:11 | Brajesh Upadhyay | Over size Boulder s found in the EMB materials | 74.7144 | 20.3723 | Inspected | RFI Not Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/031 | Checking excavation up to embankment top, Level and FDD test after excavation | 121600 | 122000 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-21 08:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-21 14:00 |  | 2025-02-23 11:47 | Work done with oversized soil boulder | 2025-02-24 10:32 | Brajesh Upadhyay | remove oversize boulders then re submit the RFI | 74.7002 | 20.3494 | Inspected | RFI Not Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/104 | FDD and Leval Checking of EMB Top | 133250 | 134750 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:48 | Brajesh Upadhyay | 2025-02-05 11:10 | Brajesh Upadhyay | 2025-03-07 14:48 | Work done successfully. | 2025-03-07 14:48 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 1500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/039 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 126080 | 126600 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-28 19:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-01 14:00 | Rushikesh Gunjal | 2025-03-01 12:52 | BT Dismantling & level done FDD not done |  |  |  | 74.7251 | 20.3818 | Inspected | Inspected - Fail | 520 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/105 | FDD and Leval Checking of EMB Top | 121020 | 123750 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:50 | Brajesh Upadhyay | 2025-01-19 10:19 | Brajesh Upadhyay | 2025-03-07 14:50 | Work done successfully. | 2025-03-07 14:50 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 2730 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/041 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 123850 | 124500 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-28 20:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-01 15:00 | Rushikesh Gunjal | 2025-03-01 13:16 | ITF team is not available FDD not done |  |  |  | 74.7092 | 20.3661 | Inspected | Inspected - Fail | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/108 | FDD and Leval Checking of EMB Top | 133250 | 134700 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:54 | Brajesh Upadhyay | 2025-02-02 11:20 | Brajesh Upadhyay | 2025-03-07 14:54 | Work done successfully. | 2025-03-07 14:54 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 1450 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/052 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 125500 | 126000 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-02 11:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-02 15:30 | Rushikesh Gunjal | 2025-03-03 17:37 | Completed | 2025-03-04 11:30 | Brajesh Upadhyay | work done | 74.7183 | 20.3744 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/037 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 121500 | 122000 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-28 19:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-01 11:30 | Rushikesh Gunjal | 2025-03-01 14:07 | Completed | 2025-03-03 12:23 | Brajesh Upadhyay | work done | 74.7002 | 20.3491 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/051 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 124700 | 125500 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-02 11:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-02 16:00 | Rushikesh Gunjal | 2025-03-03 17:33 | FDD test not done, oversize material at embankment top |  |  |  | 74.7124 | 20.3698 | Inspected | Inspected - Fail | 800 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/036 | Checking excavation up to embankment top, Level and FDD test after excavation | 121020 | 121450 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-28 19:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-01 10:30 | Rushikesh Gunjal | 2025-03-01 14:14 | FDD not done |  |  |  | 74.6989 | 20.3429 | Inspected | Inspected - Fail | 430 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/046 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 121450 | 122000 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-02 10:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-02 14:00 | Rushikesh Gunjal | 2025-03-03 15:34 | Completed | 2025-03-04 11:17 | Brajesh Upadhyay | work done | 74.6993 | 20.3475 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/106 | FDD and Leval Checking of EMB Top | 123850 | 129500 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:51 | Brajesh Upadhyay | 2025-02-08 10:42 | Brajesh Upadhyay | 2025-03-07 14:51 | Work done successfully. | 2025-03-07 14:51 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 5650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/107 | FDD and Leval Checking of EMB Top | 129800 | 133280 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:53 | Brajesh Upadhyay | 2025-02-06 10:20 | Brajesh Upadhyay | 2025-03-07 14:53 | Work done successfully. | 2025-03-07 14:53 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 3480 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/197 | Checking Reinforcement, Shuttering and pouring of concrete for Retaining wall raft. | 130040 | 130080 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-10 10:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-10 12:25 | Kishori Lal | 2025-04-11 13:25 | Steel not approved. |  |  |  | 74.7498 | 20.4017 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/048 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 128900 | 129400 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-02 10:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-02 15:00 | Rushikesh Gunjal | 2025-03-03 18:07 | Work not done | 2025-03-04 11:28 | Brajesh Upadhyay | work done | 74.7434 | 20.395 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/038 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 121500 | 122000 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-28 19:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-01 12:00 | Rushikesh Gunjal | 2025-03-01 14:06 | Completed | 2025-03-03 11:33 | Brajesh Upadhyay | BT scarification work has been done | 74.7003 | 20.349 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/043 | Checking existing BT dismantling excavation up to embankment top, Level and FDD test after excavation | 122000 | 122800 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-02 10:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-02 01:00 | Rushikesh Gunjal | 2025-03-03 15:56 | Completed | 2025-03-04 11:31 | Brajesh Upadhyay | work done | 74.6996 | 20.3481 | Inspected | RFI Approved | 800 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/110 | HPC Final lift | 121908 | 121908 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 15:02 | Brajesh Upadhyay | 2025-02-24 10:00 | Brajesh Upadhyay | 2025-03-07 15:02 | Work done successfully. | 2025-03-07 15:02 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/112 | HPC Final lift | 124418 | 124418 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 15:05 | Brajesh Upadhyay | 2025-02-26 09:40 | Brajesh Upadhyay | 2025-03-07 15:05 | Work done successfully. | 2025-03-07 15:05 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/111 | HPC Final lift | 122070 | 122070 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 15:04 | Brajesh Upadhyay | 2025-02-23 09:00 | Brajesh Upadhyay | 2025-03-07 15:04 | Work done successfully. | 2025-03-07 15:04 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/113 | HPC Final lift | 125275 | 125275 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 15:07 | Brajesh Upadhyay | 2025-02-27 09:05 | Brajesh Upadhyay | 2025-03-07 15:07 | Work done successfully. | 2025-03-07 15:07 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/082 | FDD and Leval Checking of GSB Top | 121030 | 123700 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 13:49 | Brajesh Upadhyay | 2025-02-22 11:30 | Brajesh Upadhyay | 2025-03-07 13:49 | Work done successfully. | 2025-03-07 13:49 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 2670 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/083 | FDD and Leval Checking of GSB Top | 123870 | 129380 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 13:53 | Brajesh Upadhyay | 2025-02-23 10:40 | Brajesh Upadhyay | 2025-03-07 13:53 | Work done successfully. | 2025-03-07 13:53 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 5510 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/084 | FDD and Leval Checking of GSB Top | 129810 | 133000 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 13:56 | Brajesh Upadhyay | 2025-02-25 10:00 | Brajesh Upadhyay | 2025-03-07 13:56 | Work done successfully. | 2025-03-07 13:56 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 3190 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/184 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 122640 | 122640 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-08 11:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-08 14:45 | Kishori Lal | 2025-04-08 13:46 | Not Done. |  |  |  | 74.7033 | 20.3548 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/395 | Checking of Layout Marking & Excavation for HPC | 138728 | 138728 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 19:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 17:00 | Kishori Lal | 2025-05-08 12:48 | Only RHS work done. | 2025-05-09 18:26 | Brajesh Upadhyay | work has been done | 74.7724 | 20.4756 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/122 | Checking of Layout Marking & Excavation for HPC | 126810 | 126810 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-29 17:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-30 22:30 | Kishori Lal | 2025-04-01 17:12 | Work done | 2025-04-02 09:24 | Brajesh Upadhyay | work has been done | 74.7267 | 20.3828 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/135 | Checking of Layout Marking & Excavation for HPC | 134004 | 134004 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-01 23:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-02 10:30 | Kishori Lal | 2025-04-02 15:40 | Work done | 2025-04-03 10:10 | Brajesh Upadhyay | work has bee done | 74.7586 | 20.436 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/134 | Checking of Layout Marking & Excavation for HPC | 132669 | 132669 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-01 23:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-02 15:30 | Kishori Lal | 2025-04-02 11:56 | Layout and excavation of HPC Work Done. | 2025-04-03 10:12 | Brajesh Upadhyay | work has been done | 74.7584 | 20.4241 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/109 | HPC Final lift | 121840 | 121840 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 |  | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 15:00 |  | 2025-02-25 10:10 | Rushikesh Gunjal | 2025-03-25 17:36 | Completed | 2025-03-26 12:57 | Brajesh Upadhyay | Work has been done | 74.6995 | 20.3481 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/123 | Checking of Layout Marking & Excavation for Drain | 129500 | 129540 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-29 17:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-30 23:00 | Kishori Lal | 2025-04-01 16:21 | Checking and layout of RCC Drain found Satisfactory. | 2025-04-02 09:25 | Brajesh Upadhyay | work has been done | 74.7474 | 20.398 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/115 | Checking Shuttering and laying of PCC for head wall | 125950 | 125950 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-24 22:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-26 13:00 | Rushikesh Gunjal | 2025-03-25 17:05 | Completed | 2025-03-26 09:56 | Brajesh Upadhyay | work done | 74.7034 | 20.3548 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/192 | Checking Shuttering and laying of PCC for head wall | 131730 | 131730 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-10 10:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-10 14:00 | Kishori Lal | 2025-04-10 19:15 | Not Done. |  |  |  | 74.7581 | 20.4216 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/229 | Checking of Laying, Level & FDD of DLC top Layer | 123870 | 124500 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-18 19:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-19 11:30 | Rushikesh Gunjal | 2025-04-21 15:02 | Checked found ok | 2025-04-21 16:31 | Brajesh Upadhyay | Work has been done | 74.71 | 20.3672 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/147 | Checking of Layout Marking & Excavation for retaining wall | 130070 | 130090 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-03 10:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-03 15:00 | Kishori Lal | 2025-04-03 13:19 | Wrong RFI |  |  |  | 74.7498 | 20.4018 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/330 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 122640 | 122640 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 11:00 | Kishori Lal | 2025-05-05 15:00 | Not Done. |  |  |  | 74.7036 | 20.3545 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/116 | Demo Earthwork | 117000 | 118000 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-27 12:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-28 12:51 | Kishori Lal | 2025-04-01 18:38 | Worng RFI |  |  |  | 74.7588 | 20.4362 | Inspected | Inspected - Rejected - Work Not Done | 1000 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/114 | Checking of Layout Marking & Excavation for HPC | 125950 | 125950 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-24 22:49 |  | 2025-03-25 12:00 | Rushikesh Gunjal | 2025-03-25 17:03 | Completed | 2025-03-26 09:57 | Brajesh Upadhyay | work done | 74.7033 | 20.3549 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/145 | Checking Shuttering and laying of PCC for head wall | 134004 | 134004 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-03 10:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-03 13:30 | Kishori Lal | 2025-04-03 16:08 | Not done |  |  |  | 74.7588 | 20.4359 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/176 | Checking Shuttering and laying of PCC for head wall | 127176 | 127176 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-06 22:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-07 11:00 | Rushikesh Gunjal | 2025-04-07 18:27 | Pcc for head is not done & excavate and layout only LHS |  |  |  | 74.7296 | 20.3847 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/125 | Checking of Layout Marking & Excavation for HPC | 125740 | 125740 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-31 09:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-31 11:00 | Kishori Lal | 2025-04-01 17:33 | Work done. | 2025-04-02 09:29 | Brajesh Upadhyay | work has been done | 74.7205 | 20.3756 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/127 | Checking of Layout Marking & Excavation for HPC | 123669 | 123669 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-31 09:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-31 13:04 | Kishori Lal | 2025-04-02 15:43 | Wrong Chainage. |  |  |  | 74.7586 | 20.436 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/124 | Checking Shuttering and laying of PCC for Drain | 129500 | 129540 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-29 17:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-30 12:30 | Kishori Lal | 2025-04-01 16:36 | Checking of shuttering and laying of RCC Drain PCC Work found Satisfactory. | 2025-04-02 09:26 | Brajesh Upadhyay | work has been done | 74.7475 | 20.398 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/121 | Checking of Layout Marking & Excavation for HPC | 130736 | 130736 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-29 17:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-30 14:00 | Kishori Lal | 2025-04-01 16:06 | Excavation and level of HPC not as per design and drawing. |  |  |  | 74.7525 | 20.4076 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/119 | Checking of Layout Marking & Excavation for HPC | 122640 | 122640 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-29 17:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-30 12:00 | Kishori Lal | 2025-04-01 17:45 | Work done. | 2025-04-02 09:49 | Brajesh Upadhyay | work has been done | 74.7033 | 20.3548 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/120 | Checking of Layout Marking & Excavation for HPC | 124043 | 124043 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-29 17:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-30 13:00 | Kishori Lal | 2025-04-01 17:39 | Work done. | 2025-04-02 09:23 | Brajesh Upadhyay | work has been done | 74.7087 | 20.3654 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/178 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 124043 | 124043 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-06 22:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-07 12:00 | Rushikesh Gunjal | 2025-04-07 13:34 | Work done | 2025-04-07 16:45 | Brajesh Upadhyay | work has been done | 74.7087 | 20.3654 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/126 | Checking of Layout Marking & Excavation for HPC | 127930 | 127930 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-31 09:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-31 12:00 | Kishori Lal | 2025-04-01 16:56 | Excavation and layout work done. | 2025-04-02 09:31 | Brajesh Upadhyay | work has been done | 74.7353 | 20.3889 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/171 | Checking shuttering and pouring concrete for Head Wall first lift | 130736 | 130736 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-05 10:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-05 14:55 | Rushikesh Gunjal | 2025-04-05 16:23 | Work done | 2025-04-05 17:24 | Brajesh Upadhyay | work has been done | 74.7526 | 20.4076 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/136 | Cheacking shuttering and pouring concrete for drain raft | 129500 | 129540 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-01 23:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-02 11:00 | Kishori Lal | 2025-04-02 12:39 | Work done. | 2025-04-03 10:09 | Brajesh Upadhyay | work has been done | 74.7473 | 20.398 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/118 | Checking of Layout Marking & Excavation for HPC | 134083 | 134083 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-29 13:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-30 13:43 | Kishori Lal | 2025-04-01 18:36 | Work done | 2025-04-02 09:40 | Brajesh Upadhyay | work has been done | 74.7588 | 20.436 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/133 | Checking of Layout Marking & Excavation for HPC | 130736 | 130736 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-01 23:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-02 15:00 | Kishori Lal | 2025-04-02 12:20 | Work done | 2025-04-03 10:13 | Brajesh Upadhyay | work has bee done | 74.7526 | 20.4076 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/132 | Checking Shuttering and laying of PCC for head wall | 127930 | 127930 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-01 23:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-02 14:00 | Kishori Lal | 2025-04-02 12:54 | Work done | 2025-04-03 10:16 | Brajesh Upadhyay | work has been done | 74.7353 | 20.3889 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/131 | Checking Shuttering and laying of PCC for head wall | 126810 | 126810 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-01 23:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-02 13:00 | Kishori Lal | 2025-04-02 13:04 | Work Done. | 2025-04-03 10:27 | Brajesh Upadhyay | work has been done | 74.7267 | 20.3827 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/130 | Checking Shuttering and laying of PCC for head wall | 125740 | 125740 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-01 23:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-02 12:03 | Kishori Lal | 2025-04-02 13:16 | Work done. | 2025-04-03 10:26 | Brajesh Upadhyay | work has been done | 74.7206 | 20.3757 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/128 | Checking Shuttering and laying of PCC for head wall | 122640 | 122640 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-01 22:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-02 10:00 | Kishori Lal | 2025-04-02 14:31 | Work done | 2025-04-03 10:23 | Brajesh Upadhyay | work has been done | 74.7033 | 20.3548 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/129 | Checking Shuttering and laying of PCC for head wall | 124043 | 124043 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-01 22:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-02 11:00 | Kishori Lal | 2025-04-02 14:22 | Work done. | 2025-04-03 10:24 | Brajesh Upadhyay | work has been done | 74.7087 | 20.3654 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/139 | Cheacking shuttering and pouring concrete for Head Wall first lift | 124043 | 124043 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-03 10:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-03 11:01 | Kishori Lal | 2025-04-03 15:15 | Work done. | 2025-04-04 10:47 | Brajesh Upadhyay | Work has been done | 74.7086 | 20.3654 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/143 | Checking Shuttering and laying of PCC for head wall | 130736 | 130736 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-03 10:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-03 13:00 | Kishori Lal | 2025-04-03 13:02 | Work done | 2025-04-04 10:05 | Brajesh Upadhyay | work has been done | 74.7525 | 20.4076 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/138 | Cheacking shuttering and pouring concrete for Head Wall first lift | 122640 | 122640 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-03 10:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-03 10:30 | Rushikesh Gunjal | 2025-04-03 15:23 | Completed | 2025-04-04 10:45 | Brajesh Upadhyay | work done | 74.7034 | 20.3548 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/148 | Checking shuttering and pouring concrete for retaining wall PCC | 130040 | 130090 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-03 10:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-03 15:30 | Kishori Lal | 2025-04-03 13:18 | Worng RFI |  |  |  | 74.7498 | 20.4018 | Inspected | Inspected - Rejected - Work Not Done | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/215 | Checking of Laying, Level & FDD of DLC top Layer | 122000 | 122500 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-16 08:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-16 11:00 | Rushikesh Gunjal | 2025-04-16 16:00 | Checked and found satisfactory result | 2025-04-17 09:42 | Brajesh Upadhyay | work has been done | 74.7016 | 20.3515 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/183 | Checking shuttering, reinforcement and pouring concrete for drain Slab | 129525 | 129540 | BHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-06 22:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-07 14:30 | Rushikesh Gunjal | 2025-04-07 18:37 | Checked and found ok | 2025-04-08 09:53 | Brajesh Upadhyay | work done | 74.7472 | 20.3979 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/185 | Collection of soil sampling for Borrow area No. 07 Gut No.189 & 190 | 138800 | 138800 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-09 08:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-09 12:00 | Rushikesh Gunjal | 2025-04-09 15:31 | Work done | 2025-04-09 16:10 | Brajesh Upadhyay | Work has been done | 74.7564 | 20.4829 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/146 | Cheacking shuttering and pouring concrete for drain wall | 129500 | 129525 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-03 10:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-03 14:30 | Kishori Lal | 2025-04-03 13:29 | Work done. | 2025-04-04 10:03 | Brajesh Upadhyay | work has been done | 74.747 | 20.3978 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/199 | Checking Shuttering and laying of PCC for Drain | 134600 | 134800 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-11 09:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-11 13:24 | Kishori Lal | 2025-04-11 12:31 | Not Done. |  |  |  | 74.7578 | 20.4413 | Inspected | Inspected - Rejected - Work Not Done | 200 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/144 | Checking Shuttering and laying of PCC for head wall | 132669 | 132669 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-03 10:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-03 13:38 | Kishori Lal | 2025-04-03 16:02 | Work done. | 2025-04-04 10:04 | Brajesh Upadhyay | work has been done | 74.7585 | 20.424 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/141 | Cheacking shuttering and pouring concrete for Head Wall first lift | 126810 | 126810 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-03 10:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-03 12:03 | Kishori Lal | 2025-04-03 13:46 | Work done. | 2025-04-04 10:12 | Brajesh Upadhyay | work has been done | 74.7266 | 20.3827 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/175 | Checking shuttering and pouring concrete for retaining wall PCC | 130090 | 130170 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-06 22:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-07 10:38 | Rushikesh Gunjal | 2025-04-07 18:41 | Work Not completed |  |  |  | 74.7501 | 20.4023 | Inspected | Inspected - Rejected - Work Not Done | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/149 | Checking of Layout Marking & Excavation for retaining wall | 130070 | 130090 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 10:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 10:35 | Kishori Lal | 2025-04-04 12:18 | Work done. |  |  |  | 74.75 | 20.4021 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/140 | Cheacking shuttering and pouring concrete for Head Wall first lift | 125740 | 125740 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-03 10:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-03 11:30 | Kishori Lal | 2025-04-03 15:07 | Work done. | 2025-04-04 10:50 | Brajesh Upadhyay | Work has been done | 74.7206 | 20.3755 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/152 | Checking shuttering, reinforcement and pouring concrete for drain Slab | 129500 | 129525 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 10:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 11:30 | Kishori Lal | 2025-04-04 12:29 | Work done | 2025-04-05 11:58 | Brajesh Upadhyay | work done | 74.747 | 20.3978 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/137 | Checking of Layout Marking & Excavation for retaining wall | 130040 | 130070 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-02 14:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-02 16:00 | Kishori Lal | 2025-04-04 12:17 | Work done. | 2025-04-05 12:11 | Brajesh Upadhyay | work has been done | 74.75 | 20.4021 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/150 | Checking shuttering and pouring concrete for retaining wall PCC | 130040 | 130090 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 10:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 10:55 | Kishori Lal | 2025-04-04 12:21 | Work done. | 2025-04-05 12:37 | Brajesh Upadhyay | work has been done | 74.75 | 20.4021 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/151 | Checking shuttering and pouring concrete for drain wall | 129525 | 129540 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 10:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 10:56 | Kishori Lal | 2025-04-04 17:48 | Work done. | 2025-04-05 11:57 | Brajesh Upadhyay | work done | 74.7473 | 20.3981 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/450 | Checking shuttering and pouring concrete for Head Wall second lift & Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 134460 | 134460 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 12:30 | Kishori Lal | 2025-05-12 13:26 | Encasing not done. |  |  |  | 74.7582 | 20.4389 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/153 | Checking of Layout Marking & Excavation for HPC | 127176 | 127176 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 11:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 12:00 | Kishori Lal | 2025-04-04 17:38 | Work done. | 2025-04-05 11:59 | Brajesh Upadhyay | work done | 74.7296 | 20.3849 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/154 | Checking Shuttering and laying of PCC Below Pipe | 122640 | 122640 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 11:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 12:00 | Kishori Lal | 2025-04-04 12:54 | Work done. | 2025-04-05 09:49 | Brajesh Upadhyay | checking of shuttering and laying of PCC M- 15 work has been done | 74.7033 | 20.3549 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/157 | Checking Shuttering and laying of PCC Below Pipe | 126810 | 126810 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 11:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 14:04 | Kishori Lal | 2025-04-04 17:34 | Work done. | 2025-04-05 12:03 | Brajesh Upadhyay | work has been done | 74.7268 | 20.3829 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/159 | Checking Shuttering and laying of PCC for head wall | 130736 | 130736 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 11:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 15:39 | Kishori Lal | 2025-04-04 17:53 | Work done. | 2025-04-05 12:05 | Brajesh Upadhyay | work has been done | 74.7526 | 20.4076 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/188 | Cheacking shuttering and pouring concrete for Head Wall first lift | 127176 | 127176 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-10 10:17 |  | 2025-04-10 10:15 | Kishori Lal | 2025-04-10 18:57 | Work done. | 2025-04-11 09:41 | Brajesh Upadhyay | work has been done | 74.7295 | 20.3848 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/189 | Cheacking shuttering and pouring concrete for Head Wall Second lift | 130736 | 130736 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-10 10:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-10 11:17 | Kishori Lal | 2025-04-10 19:06 | Work done. | 2025-04-11 09:43 | Brajesh Upadhyay | work has been done | 74.7525 | 20.4077 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/162 | Cheacking shuttering and pouring concrete for Head Wall first lift | 134004 | 134004 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 11:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 16:42 | Kishori Lal | 2025-04-04 18:35 | Not Done. |  |  |  | 74.7587 | 20.4359 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/161 | Checking Shuttering and laying of PCC Below Pipe | 132669 | 132669 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 11:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 16:00 | Kishori Lal | 2025-04-04 17:54 | Work done. | 2025-04-05 08:33 | Brajesh Upadhyay | work has been done | 74.7527 | 20.4076 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/180 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 126810 | 126810 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-06 22:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-07 13:00 | Rushikesh Gunjal | 2025-04-07 18:23 | Checked and found Encasing is not done |  |  |  | 74.7267 | 20.3829 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/156 | Checking shuttering and pouring concrete for Head Wall second lift | 125740 | 125740 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 11:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 13:02 | Kishori Lal | 2025-04-04 13:06 | Work done. | 2025-04-05 12:02 | Brajesh Upadhyay | work has been done | 74.7206 | 20.3756 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/158 | Checking Shuttering and laying of PCC Below Pipe | 127930 | 127930 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 11:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 14:30 | Kishori Lal | 2025-04-04 17:42 | Work done | 2025-04-05 12:04 | Brajesh Upadhyay | work has been done | 74.7351 | 20.389 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/177 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 122640 | 122640 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-06 22:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-07 11:42 | Kishori Lal | 2025-04-08 13:44 | Not Done. |  |  |  | 74.7033 | 20.3548 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/160 | Checking Shuttering and laying of PCC for head wall | 132669 | 132669 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 11:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 15:41 | Kishori Lal | 2025-04-04 18:08 | Work done. | 2025-04-05 12:06 | Brajesh Upadhyay | work has been done | 74.7585 | 20.4241 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/174 | Checking of Layout Marking & Excavation for retaining wall | 130090 | 130170 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-06 20:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-07 10:00 | Rushikesh Gunjal | 2025-04-07 18:40 | Checked and found ok | 2025-04-08 09:50 | Brajesh Upadhyay | work done | 74.7501 | 20.4023 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/378 | Checking shuttering and pouring concrete for Head Wall first lift | 128318 | 128318 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 10:30 | Kishori Lal | 2025-05-08 14:50 | Work done. | 2025-05-08 16:56 | Brajesh Upadhyay | Work has been done | 74.7382 | 20.391 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/165 | Checking Shuttering and laying of PCC for head wall | 127176 | 127176 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-05 10:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-05 11:03 | Rushikesh Gunjal | 2025-04-05 16:57 | Work not done |  |  |  | 74.7296 | 20.3847 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/166 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 122640 | 122640 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-05 10:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-05 11:30 | Rushikesh Gunjal | 2025-04-05 17:25 | Checked and found Encasing is not done |  |  |  | 74.7034 | 20.3549 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/163 | Checking of Layout Marking & Excavation for retaining wall | 130090 | 130170 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-05 09:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-05 10:15 | Rushikesh Gunjal | 2025-04-05 15:34 | Checked and found ok | 2025-04-05 17:27 | Brajesh Upadhyay | work has been done | 74.7502 | 20.4023 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/168 | Checking shuttering and pouring concrete for Head Wall final lift | 125740 | 125740 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-05 10:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-05 12:30 | Rushikesh Gunjal | 2025-04-05 14:46 | LHS Final lift casting is done RHS final lift work not done |  |  |  | 74.7213 | 20.3775 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/164 | Checking shuttering and pouring concrete for retaining wall PCC | 130090 | 130170 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-05 10:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-05 11:01 | Rushikesh Gunjal | 2025-04-05 16:45 | Not done |  |  |  | 74.7505 | 20.4028 | Inspected | Inspected - Rejected - Work Not Done | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/167 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 124043 | 124043 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-05 10:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-05 12:08 | Rushikesh Gunjal | 2025-04-05 17:20 | Check and found Encasing is not done |  |  |  | 74.7087 | 20.3656 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/182 | Cheacking shuttering and pouring concrete for Head Wall first lift | 130736 | 130736 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-06 22:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-07 14:00 | Rushikesh Gunjal | 2025-04-07 18:44 | Work not done |  |  |  | 74.7525 | 20.4075 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/169 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 126810 | 126810 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-05 10:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-05 13:10 | Rushikesh Gunjal | 2025-04-05 14:58 | Encasing work is not done |  |  |  | 74.7268 | 20.3829 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/170 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 127930 | 127930 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-05 10:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-05 13:30 | Rushikesh Gunjal | 2025-04-05 15:06 | Pipe laying and fitting work is done But, Encasing is not done |  |  |  | 74.7354 | 20.3891 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/381 | Checking Shuttering and laying of PCC of Box Culvert | 133216 | 133216 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 10:30 | Kishori Lal | 2025-05-08 14:30 | Work done. | 2025-05-08 16:55 | Brajesh Upadhyay | Work has been done | 74.7585 | 20.429 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/172 | Checking shuttering, reinforcement and pouring concrete for drain Slab | 129525 | 129540 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-05 10:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-05 14:00 | Rushikesh Gunjal | 2025-04-05 15:16 | Work not done |  |  |  | 74.7472 | 20.3979 | Inspected | Inspected - Rejected - Work Not Done | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/383 | Checking Shuttering and laying of PCC Below Pipe | 134004 | 134004 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 14:00 | Kishori Lal | 2025-05-08 14:01 | Work done. | 2025-05-08 16:52 | Brajesh Upadhyay | Work has been done | 74.7588 | 20.4361 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/382 | Checking Shuttering and laying of PCC Below Pipe | 133500 | 133500 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 12:00 | Kishori Lal | 2025-05-08 14:03 | Work done. | 2025-05-08 16:53 | Brajesh Upadhyay | Work has been done | 74.7586 | 20.4314 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/384 | Checking pipe laying and joint filling | 134083 | 134083 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 15:31 | Kishori Lal | 2025-05-08 14:00 | Work done. | 2025-05-08 16:51 | Brajesh Upadhyay | Work has been done | 74.7587 | 20.4368 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/386 | Checking of Layout Marking & Excavation for Drain | 134600 | 134700 | BHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 10:00 | Rushikesh Gunjal | 2025-05-08 11:31 | Wrong RFI Mention Side (BHS) is wrong |  |  |  | 74.7579 | 20.4431 | Inspected | Inspected - Rejected - Work Not Done | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/155 | Checking Shuttering and laying of PCC Below Pipe | 124043 | 124043 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-04 11:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-04 12:30 | Kishori Lal | 2025-04-04 13:00 | Work done. | 2025-04-05 12:01 | Brajesh Upadhyay | work has been done | 74.7087 | 20.3655 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/206 | Checking pipe laying and joint filling | 130736 | 130736 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-12 10:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-12 14:01 | Kishori Lal | 2025-04-12 12:22 | Work done. | 2025-04-12 18:39 | Brajesh Upadhyay | Work has been done | 74.7526 | 20.4075 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/210 | Checking shuttering and pouring concrete for Head Wall final lift | 130736 | 130736 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-12 10:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-12 16:30 | Kishori Lal | 2025-04-12 12:19 | Work done. | 2025-04-12 18:38 | Brajesh Upadhyay | Work done | 74.7526 | 20.4075 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/204 | Checking of Layout Marking & Excavation for HPC | 128318 | 128318 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-12 10:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-12 12:00 | Kishori Lal | 2025-04-12 12:57 | Work done. | 2025-04-12 18:40 | Brajesh Upadhyay | Work done | 74.7383 | 20.3912 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/196 | Checking of Layout Marking & Excavation for Retaining Wall | 132910 | 133000 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-10 10:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-10 11:30 | Kishori Lal | 2025-04-11 13:07 | Work done. | 2025-04-11 16:42 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4261 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/202 | Checking of Laying, Level & FDD of DLC top Layer | 121500 | 122000 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-12 09:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-12 11:56 | Rushikesh Gunjal | 2025-04-12 15:56 | Checked and found satisfactory & ok | 2025-04-12 18:41 | Brajesh Upadhyay | Work has been done | 74.6989 | 20.3457 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/190 | Cheacking shuttering and pouring concrete for Head Wall first lift | 132669 | 132669 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-10 10:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-10 12:18 | Kishori Lal | 2025-04-11 13:13 | Work done. | 2025-04-11 16:46 | Brajesh Upadhyay | work has been done | 74.7585 | 20.4238 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/186 | Collection of soil sampling for Borrow area No. 08 Gut No.197 & 199 | 138800 | 138800 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-09 08:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-09 14:00 | Rushikesh Gunjal | 2025-04-09 15:35 | Work done | 2025-04-09 16:09 | Brajesh Upadhyay | Work has been done | 74.7565 | 20.4829 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/179 | Checking shuttering and pouring concrete for Head Wall final lift | 125740 | 125740 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-06 22:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-07 13:00 | Rushikesh Gunjal | 2025-04-07 13:42 | Checked and found ok | 2025-04-07 16:46 | Brajesh Upadhyay | work has been done | 74.7215 | 20.376 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/061 | Checking Level and FDD test for GSB Top | 121030 | 121500 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-06 23:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 16:08 | Rushikesh Gunjal | 2025-03-07 15:19 | Checked and found ok | 2025-04-07 17:37 | Brajesh Upadhyay | work done | 74.6983 | 20.3407 | Inspected | RFI Approved | 470 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/062 | Checking Level and FDD test for GSB Top | 122500 | 123150 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-06 23:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 17:10 | Rushikesh Gunjal | 2025-03-07 15:04 | Checked and found ok | 2025-04-07 17:38 | Brajesh Upadhyay | work done | 74.7054 | 20.3582 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/198 | Checking of Layout Marking & Excavation for Drain | 134600 | 134800 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-11 09:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-11 12:00 | Rushikesh Gunjal | 2025-04-11 12:30 | Work not completed |  |  |  | 74.7579 | 20.4424 | Inspected | Inspected - Rejected - Work Not Done | 200 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/194 | Checking of Layout Marking & Excavation for Drain | 134520 | 134570 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-10 10:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-10 11:22 | Kishori Lal | 2025-04-11 12:37 | Work done. | 2025-04-11 16:44 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4412 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/181 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 127930 | 127930 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-06 22:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-07 13:30 | Rushikesh Gunjal | 2025-04-07 18:31 | Work done | 2025-04-08 09:51 | Brajesh Upadhyay | work done | 74.7352 | 20.389 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/195 | Checking Shuttering and laying of PCC for Drain | 134520 | 134570 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-10 10:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-10 12:30 | Kishori Lal | 2025-04-11 12:40 | Work Done. | 2025-04-11 16:43 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4409 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/213 | Checking Shuttering and laying of PCC for head wall | 131730 | 131730 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-12 20:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-13 12:11 | Rushikesh Gunjal | 2025-04-15 16:54 | Completed | 2025-04-15 20:25 | Brajesh Upadhyay | Work done | 74.7555 | 20.4161 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/200 | Checking of Layout Marking & Excavation for Drain | 134080 | 134340 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-11 09:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-11 11:25 | Kishori Lal | 2025-04-11 12:47 | Not Done. |  |  |  | 74.7586 | 20.4367 | Inspected | Inspected - Rejected - Work Not Done | 260 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/212 | Checking Shuttering and laying of PCC for head wall | 127176 | 127176 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-12 20:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-13 11:10 | Rushikesh Gunjal | 2025-04-15 16:45 | LHS completed RHS not done |  |  |  | 74.7296 | 20.3848 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/191 | Checking of Layout Marking & Excavation for HPC | 131730 | 131730 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-10 10:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-10 13:00 | Kishori Lal | 2025-04-10 19:12 | Work done. | 2025-04-11 09:49 | Brajesh Upadhyay | work has been done | 74.7556 | 20.4161 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/452 | Checking Reinforcement, shuttering and pouring concrete for Drain wall | 134600 | 134700 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 13:30 | Kishori Lal | 2025-05-10 15:50 | Work done. | 2025-05-11 11:10 | Brajesh Upadhyay | work has been done | 74.7578 | 20.4419 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/193 | Cheacking shuttering and pouring concrete for Head Wall first lift | 134004 | 134004 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-10 10:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-10 14:30 | Kishori Lal | 2025-04-11 12:52 | Not Done. |  |  |  | 74.7589 | 20.436 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/390 | Checking shuttering and pouring concrete for Head Wall first lift | 135178 | 135178 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 19:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 14:05 | Kishori Lal | 2025-05-08 13:38 | Wrong Chainage. |  |  |  | 74.7593 | 20.4467 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/209 | Checking Reinforcement, Shuttering and pouring of concrete for Drain Wall | 134520 | 134570 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-12 10:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-12 15:30 | Rushikesh Gunjal | 2025-04-12 11:47 | Approval of the steel used was not obtained.(SRJ) Shuttering is not completed |  |  |  | 74.7579 | 20.4405 | Inspected | Inspected - Rejected - Work Not Done | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/207 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 132669 | 132669 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-12 10:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-12 15:07 | Kishori Lal | 2025-04-12 12:11 | Not Done. |  |  |  | 74.7586 | 20.424 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/205 | Checking Reinforcement, Shuttering and pouring of concrete for Retaining wall 1st lift | 130040 | 130070 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-12 10:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-12 13:01 | Rushikesh Gunjal | 2025-04-12 12:33 | Approval of the steel used was not obtained. (SRJ) Shuttering work is not done |  |  |  | 74.7499 | 20.402 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/203 | Checking shuttering and pouring concrete for Head Wall final lift | 127176 | 127176 | LHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-12 10:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-12 11:00 | Kishori Lal | 2025-04-12 13:05 | Work done. | 2025-04-12 18:41 | Brajesh Upadhyay | Work has been done | 74.7295 | 20.3848 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/219 | Checking shuttering and pouring concrete for Head Wall first lift | 131730 | 131730 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-16 19:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-17 12:30 | Kishori Lal | 2025-04-17 15:45 | Work done. | 2025-04-17 18:07 | Brajesh Upadhyay | Work done | 74.7556 | 20.4158 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/214 | Checking Shuttering and laying of PCC for head wall | 132386 | 132386 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-12 20:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-13 13:12 | Rushikesh Gunjal | 2025-04-16 16:50 | LHS work done RHS work in progress | 2025-04-17 09:46 | Brajesh Upadhyay | work has been done | 74.7582 | 20.4216 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/211 | Checking of Layout Marking & Excavation for HPC | 127176 | 127176 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-12 20:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-13 10:09 | Rushikesh Gunjal | 2025-04-15 16:43 | LHS layout marking completed RHS work in progress | 2025-04-15 20:25 | Brajesh Upadhyay | Work done | 74.7296 | 20.3848 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/224 | Checking shuttering and pouring concrete for Drain PCC | 134980 | 135010 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-16 19:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-17 15:33 | Kishori Lal | 2025-04-17 16:57 | Work done. | 2025-04-17 18:05 | Brajesh Upadhyay | Work done | 74.7584 | 20.4446 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/222 | Checking pipe laying and joint filling | 132318 | 132318 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-16 19:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-17 14:31 | Kishori Lal | 2025-04-17 16:17 | Work not executed as per design and drawing. |  |  |  | 74.758 | 20.4213 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/223 | Checking shuttering and pouring concrete for Drain PCC | 134620 | 134690 | BHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-16 19:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-17 14:31 | Kishori Lal | 2025-04-17 16:40 | Work done. | 2025-04-17 18:06 | Brajesh Upadhyay | Work has been done | 74.7579 | 20.4419 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/225 | Checking shuttering and pouring concrete for Retaining Wall PCC | 132910 | 133000 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-16 19:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-17 16:34 | Kishori Lal | 2025-04-17 16:23 | Work done. | 2025-04-17 18:04 | Brajesh Upadhyay | Work has been done | 74.7582 | 20.4267 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/227 | Collection of aggregate sampling for PQC mix design from base camp | 125900 | 125900 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-16 19:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-17 10:30 | Rushikesh Gunjal | 2025-04-17 17:18 | Sample collected | 2025-04-17 18:03 | Brajesh Upadhyay | Work done | 74.7214 | 20.3761 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/347 | Checking of Laying of PQC | 121800 | 122500 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 18:27 | Rushikesh Gunjal | 2025-05-10 16:09 | Checked and ok | 2025-05-12 11:48 | Brajesh Upadhyay | Work has been done | 74.7028 | 20.3536 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/337 | Checking shuttering and pouring concrete for Head Wall first lift | 135821 | 135821 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 17:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 15:00 | Kishori Lal | 2025-05-05 11:53 | Not Done. |  |  |  | 74.7613 | 20.4519 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/447 | Checking shuttering and pouring concrete for Head Wall second lift & Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 133500 | 133500 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 11:00 | Kishori Lal | 2025-05-10 12:13 | Encasing not done. |  |  |  | 74.7599 | 20.433 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/396 | Checking of Layout Marking & Excavation for HPC | 138983 | 138983 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 19:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 17:30 | Kishori Lal | 2025-05-08 17:13 | Work done. | 2025-05-08 17:14 | Brajesh Upadhyay | Work has been done | 74.7739 | 20.4777 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/394 | Checking Shuttering and laying of PCC for head wall | 137018 | 137018 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 19:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 16:30 | Kishori Lal | 2025-05-08 12:52 | Not Done. |  |  |  | 74.7659 | 20.4615 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/392 | Checking Reinforcement, shuttering and pouring concrete for Drain slab | 135260 | 135340 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 19:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 15:30 | Rushikesh Gunjal | 2025-05-08 11:26 | Ok | 2025-05-08 12:46 | Brajesh Upadhyay | Work done | 74.7587 | 20.4454 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/217 | Checking shuttering and pouring concrete for Head Wall first lift | 127176 | 127176 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-16 19:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-17 10:30 | Kishori Lal | 2025-04-17 15:10 | Not Done. |  |  |  | 74.7296 | 20.3847 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/218 | Checking pipe laying and joint filling | 127176 | 127176 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-16 19:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-17 11:30 | Kishori Lal | 2025-04-17 15:12 | Not Done. |  |  |  | 74.7296 | 20.3847 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/220 | Checking pipe laying and joint filling | 131730 | 131730 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-16 19:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-17 13:29 | Kishori Lal | 2025-04-17 15:48 | Not Done. |  |  |  | 74.7554 | 20.4162 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/221 | Checking shuttering and pouring concrete for Head Wall first lift | 132318 | 132318 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-16 19:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-17 14:30 | Kishori Lal | 2025-04-17 16:13 | Work done. | 2025-04-17 18:06 | Brajesh Upadhyay | Work done | 74.7582 | 20.4215 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/216 | Checking of Laying, Level & FDD of DLC top Layer | 122500 | 123000 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-16 18:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-17 10:30 | Rushikesh Gunjal | 2025-04-17 15:27 | Checked and found satisfactory result | 2025-04-17 18:35 | Brajesh Upadhyay | Work done | 74.7039 | 20.3559 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/226 | Checking of Laying, Level & FDD of DLC top Layer | 123000 | 123300 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-16 19:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-17 19:35 | Rushikesh Gunjal | 2025-04-18 15:48 | Checked and found satisfactory result | 2025-04-19 09:21 | Brajesh Upadhyay | work has been done | 74.7063 | 20.3594 | Inspected | RFI Approved | 300 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/228 | Checking of Laying, Level & FDD of DLC top Layer | 123300 | 123450 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-18 19:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-19 10:09 | Rushikesh Gunjal | 2025-04-19 16:12 | Checked and found satisfactory result | 2025-04-19 19:56 | Brajesh Upadhyay | Work done | 74.7077 | 20.3645 | Inspected | RFI Approved | 150 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/230 | Checking of Laying, Level & FDD of DLC top Layer | 124500 | 125200 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-22 08:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-22 10:30 | Rushikesh Gunjal | 2025-04-22 16:16 | Checked and found satisfactory | 2025-04-22 17:23 | Brajesh Upadhyay | Work has been done | 74.717 | 20.3733 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/473 | Checking pipe laying and joint filling & Checking shuttering and pouring concrete for Head Wall second lift | 137018 | 137018 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 15:00 | Kishori Lal | 2025-05-12 12:29 | Not ready. |  |  |  | 74.7659 | 20.4616 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/496 | Checking shuttering and pouring concrete for Head Wall final lift | 137018 | 137018 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 17:20 | Kishori Lal | 2025-05-12 12:31 | Not Ready. |  |  |  | 74.7658 | 20.4616 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/389 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134750 | 134820 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 10:30 | Rushikesh Gunjal | 2025-05-08 11:33 | Ok | 2025-05-08 12:47 | Brajesh Upadhyay | Work done | 74.758 | 20.443 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/448 | Checking shuttering and pouring concrete for Head Wall second lift & Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 134004 | 134004 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 11:30 | Kishori Lal | 2025-05-10 12:12 | Encasing not Done. |  |  |  | 74.7586 | 20.4357 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/379 | Checking Reinforcement, shuttering and pouring concrete for Raft of Retaining Wall | 130090 | 130170 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 11:00 | Rushikesh Gunjal | 2025-05-08 11:54 | Ok | 2025-05-08 12:50 | Brajesh Upadhyay | Work done | 74.7503 | 20.4026 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/387 | Checking Shuttering and pouring concrete of PCC for Drain | 134600 | 134700 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 17:00 | Rushikesh Gunjal | 2025-05-08 11:35 | Ok | 2025-05-08 12:49 | Brajesh Upadhyay | Work done | 74.7579 | 20.4426 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/242 | Checking of Layout Marking & Excavation for Retaining Wall | 128288 | 128348 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 14:00 | Rushikesh Gunjal | 2025-04-28 15:20 | Excavation and layout is done | 2025-04-28 17:30 | Brajesh Upadhyay | work has been done | 74.7386 | 20.3912 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/377 | Checking Reinforcement, shuttering and pouring concrete for Wall second lift of Retaining Wall | 128288 | 128348 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 10:00 | Rushikesh Gunjal | 2025-05-08 12:04 | Ok | 2025-05-08 12:51 | Brajesh Upadhyay | Work done | 74.7382 | 20.391 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/336 | Checking Shuttering and laying of PCC for head wall | 135368 | 135368 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 17:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 16:30 | Kishori Lal | 2025-05-05 11:57 | Not Done. |  |  |  | 74.76 | 20.4479 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/231 | Checking of Laying, Level & FDD of DLC top Layer | 125300 | 126000 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-23 08:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-23 10:00 | Rushikesh Gunjal | 2025-04-23 11:38 | Checked and found ok | 2025-04-23 20:17 | Brajesh Upadhyay | Work has been done | 74.7189 | 20.3746 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/391 | Checking Shuttering and laying of PCC for head wall | 135230 | 135230 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 19:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 15:09 | Kishori Lal | 2025-05-08 13:04 | Work done. | 2025-05-08 16:48 | Brajesh Upadhyay | Work has been done | 74.7594 | 20.4469 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/388 | Checking shuttering and pouring concrete for Head Wall first lift | 134718 | 134718 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 11:37 | Kishori Lal | 2025-05-08 13:50 | Work done. | 2025-05-08 16:49 | Brajesh Upadhyay | Work has been done | 74.7579 | 20.4424 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/385 | Checking shuttering and pouring concrete for Head Wall first lift | 134460 | 134460 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 16:00 | Kishori Lal | 2025-05-08 13:58 | Work done. | 2025-05-08 16:50 | Brajesh Upadhyay | Work has been done | 74.7582 | 20.439 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/529 | Checking Reinforcement, shuttering and pouring concrete for Wall final lift of Retaining Wall | 130140 | 130190 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-14 14:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-15 09:30 | Rushikesh Gunjal | 2025-05-15 11:58 | Checked and found ok | 2025-05-15 16:28 | Brajesh Upadhyay | Work has been done | 74.7502 | 20.4025 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/469 | Checking Shuttering and pouring concrete of PCC for Drain | 134600 | 134700 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 13:00 | Kishori Lal | 2025-05-12 13:15 | Not Done. |  |  |  | 74.7578 | 20.4419 | Inspected | Inspected - Rejected - Work Not Done | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/492 | Checking Shuttering and pouring concrete of raft for Drain | 134600 | 134700 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 13:00 | Kishori Lal | 2025-05-12 13:17 | Not Ready. |  |  |  | 74.7578 | 20.4419 | Inspected | Inspected - Rejected - Work Not Done | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/327 | Checking of Layout Marking & Excavation for HPC | 135178 | 135178 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 10:30 | Kishori Lal | 2025-05-05 12:01 | Not Done. |  |  |  | 74.7593 | 20.447 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/449 | Checking shuttering and pouring concrete for Head Wall final lift | 134083 | 134083 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 11:30 | Kishori Lal | 2025-05-12 13:30 | Work done. | 2025-05-13 11:43 | Brajesh Upadhyay | work has been done | 74.7585 | 20.4368 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/466 | Checking pipe laying and joint filling & Checking shuttering and pouring concrete for Head Wall second lift | 134004 | 134004 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 11:30 | Kishori Lal | 2025-05-12 13:33 | Work done. | 2025-05-13 11:21 | Brajesh Upadhyay | work has been done | 74.7588 | 20.4362 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/457 | Collecting sampling for SBC for hard rock (UCS) Test | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 09:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 12:00 | Kishori Lal | 2025-05-10 15:01 | Work done. | 2025-05-11 11:13 | Brajesh Upadhyay | work has been done | 74.7483 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/465 | Checking pipe laying and joint filling & Checking shuttering and pouring concrete for Head Wall second lift | 133500 | 133500 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 11:00 | Kishori Lal | 2025-05-12 13:37 | Work done. | 2025-05-13 11:41 | Brajesh Upadhyay | work has been done | 74.7589 | 20.4318 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/446 | Checking Reinforcement, shuttering and pouring concrete for final lift of Retaining Wall | 130090 | 130170 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 10:30 | Kishori Lal | 2025-05-10 15:10 | Not Done. (Steel not approved) |  |  |  | 74.7501 | 20.4024 | Inspected | Inspected - Rejected - Work Not Done | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/489 | Checking shuttering and pouring concrete for Head Wall final lift | 133500 | 133500 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 10:30 | Kishori Lal | 2025-05-12 13:38 | Work done. | 2025-05-13 10:54 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4315 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/397 | Checking of Laying, Level and FDD of DLC top layer | 128950 | 129350 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 19:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 12:14 | Rushikesh Gunjal | 2025-05-10 15:15 | Checked and found ok | 2025-05-12 11:47 | Brajesh Upadhyay | Work has been done | 74.7401 | 20.3925 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/517 | Checking shuttering and pouring concrete for Head Wall final lift | 125950 | 125950 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 18:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-14 18:22 | Kishori Lal | 2025-05-15 16:03 | Work done. | 2025-05-15 16:29 | Brajesh Upadhyay | Work has been done | 74.7215 | 20.3773 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/464 | Checking Reinforcement, shuttering and pouring concrete for final lift of Retaining Wall | 130090 | 130170 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 10:30 | Kishori Lal | 2025-05-12 13:49 | Not Ready. |  |  |  | 74.7502 | 20.4024 | Inspected | Inspected - Rejected - Work Not Done | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/463 | Checking Shuttering and laying of PCC for Minor Bridge | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 10:00 | Kishori Lal | 2025-05-12 13:53 | Not Ready. |  |  |  | 74.7484 | 20.3989 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/459 | Checking of Layout Marking & Excavation for Drain | 134600 | 134700 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 09:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 17:04 | Kishori Lal | 2025-05-10 15:46 | Work done | 2025-05-11 11:16 | Brajesh Upadhyay | work has been done | 74.7578 | 20.4419 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/453 | Checking shuttering and pouring concrete for Head Wall second lift & Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 134718 | 134718 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 14:00 | Kishori Lal | 2025-05-10 15:52 | Not Done. |  |  |  | 74.7577 | 20.4425 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/462 | Checking shuttering and pouring concrete for Head Wall final lift | 128318 | 128318 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 09:30 | Kishori Lal | 2025-05-12 13:59 | Not satisfactory. |  |  |  | 74.7385 | 20.3914 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/460 | Checking of Layout Marking & Excavation for Drain | 135050 | 135150 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 09:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 17:30 | Kishori Lal | 2025-05-10 16:00 | Not Done. |  |  |  | 74.7587 | 20.4449 | Inspected | Inspected - Rejected - Work Not Done | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/454 | Checking Shuttering and laying of PCC Below Pipe | 135230 | 135230 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 14:30 | Kishori Lal | 2025-05-10 16:12 | Work done. | 2025-05-11 11:11 | Brajesh Upadhyay | work has been done | 74.7592 | 20.4469 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/458 | Checking of Layout Marking & Excavation for HPC | 135020 | 135020 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 09:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 16:30 | Kishori Lal | 2025-05-10 16:05 | LHS Work done. | 2025-05-11 11:15 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4451 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/328 | Checking of Laying of PQC | 121800 | 122500 | BHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 18:00 | Rushikesh Gunjal | 2025-05-10 16:10 | Wrong RFI Mention side is wrong |  |  |  | 74.7028 | 20.3535 | Inspected | Inspected - Rejected - Work Not Done | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/443 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 135890 | 136360 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 17:00 | Saurabh SE | 2025-05-10 16:19 | Not done |  |  |  | 74.7619 | 20.4532 | Inspected | Inspected - Rejected - Work Not Done | 470 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/455 | Checking shuttering and pouring concrete for Head Wall first lift & PCC Below Pipe | 137018 | 137018 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 15:00 | Kishori Lal | 2025-05-10 16:25 | Work done. | 2025-05-11 11:12 | Brajesh Upadhyay | work has been done | 74.7658 | 20.4615 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/376 | Checking shuttering and pouring concrete for Head Wall first lift | 126806 | 126806 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 18:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 13:30 | Kishori Lal | 2025-05-08 16:32 | Work done. | 2025-05-08 16:57 | Brajesh Upadhyay | Work has been done | 74.7265 | 20.3826 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/456 | Checking Reinforcement, shuttering and pouring concrete for Wall first lift of Retaining Wall | 140450 | 141000 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 15:30 | Kishori Lal | 2025-05-10 16:34 | Not Done. |  |  |  | 74.7812 | 20.4888 | Inspected | Inspected - Rejected - Work Not Done | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/393 | Checking of Layout Marking & Excavation for HPC | 136078 | 136078 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 19:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 16:00 | Kishori Lal | 2025-05-08 12:59 | Work done. | 2025-05-08 16:47 | Brajesh Upadhyay | Work has been done | 74.7623 | 20.4538 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/475 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 135890 | 136360 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 16:00 | Saurabh SE | 2025-05-13 16:40 | BT not dismentaling |  |  |  | 74.7614 | 20.4522 | Inspected | Inspected - Rejected - Work Not Done | 470 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/490 | Checking shuttering and pouring concrete for Head Wall final lift | 134004 | 134004 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 12:00 | Kishori Lal | 2025-05-12 13:34 | Work done. | 2025-05-13 11:02 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4361 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/329 | Checking of Laying, Level and FDD of DLC top layer | 128200 | 128950 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 22:00 | Rushikesh Gunjal | 2025-05-08 15:20 | Checked and found ok | 2025-05-08 17:50 | Brajesh Upadhyay | Work done | 74.7359 | 20.3895 | Inspected | RFI Approved | 750 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/491 | Checking shuttering and pouring concrete for Head Wall final lift | 134460 | 134460 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 12:30 | Kishori Lal | 2025-05-12 13:27 | Work done. | 2025-05-13 11:03 | Brajesh Upadhyay | work has been done | 74.7582 | 20.4388 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/468 | Checking Reinforcement, shuttering and pouring concrete for Drain slab | 134600 | 134700 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 12:30 | Kishori Lal | 2025-05-12 13:13 | Work done. | 2025-05-13 11:32 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4421 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/467 | Checking pipe laying and joint filling & Checking shuttering and pouring concrete for Head Wall second lift | 134460 | 134460 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 12:00 | Kishori Lal | 2025-05-12 15:39 | Work done. | 2025-05-13 11:30 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4389 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/471 | Checking Shuttering and laying of PCC for head wall | 135020 | 135020 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 14:00 | Kishori Lal | 2025-05-12 12:56 | Work done. | 2025-05-13 11:38 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4449 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/470 | Checking pipe laying and joint filling & Checking shuttering and pouring concrete for Head Wall second lift | 134718 | 134718 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 13:30 | Kishori Lal | 2025-05-12 13:06 | LHS Work done. | 2025-05-13 11:36 | Brajesh Upadhyay | work has been done | 74.7577 | 20.4425 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/472 | Checking pipe laying and joint filling & Checking shuttering and pouring concrete for Head Wall second lift | 135230 | 135230 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 14:30 | Kishori Lal | 2025-05-12 12:40 | Work done. | 2025-05-13 11:39 | Brajesh Upadhyay | work has been done | 74.7592 | 20.4468 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/493 | Checking shuttering and pouring concrete for Head Wall final lift | 134718 | 134718 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 14:00 | Kishori Lal | 2025-05-12 13:08 | Work done. | 2025-05-13 11:12 | Brajesh Upadhyay | work has been done | 74.7578 | 20.4419 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/494 | Checking shuttering and pouring concrete for Head Wall first lift & PCC Below Pipe | 135020 | 135020 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 15:00 | Kishori Lal | 2025-05-12 12:59 | Work done. | 2025-05-13 11:18 | Brajesh Upadhyay | work has been done | 74.7588 | 20.445 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/495 | Checking shuttering and pouring concrete for Head Wall final lift | 135230 | 135230 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 16:00 | Kishori Lal | 2025-05-12 12:43 | Work done. | 2025-05-13 11:19 | Brajesh Upadhyay | work has been done | 74.7593 | 20.4468 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/451 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134600 | 134700 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 11:00 | Kishori Lal | 2025-05-12 13:11 | Work done. | 2025-05-13 11:45 | Brajesh Upadhyay | work has been done | 74.7578 | 20.4419 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/403 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 137900 | 138630 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 11:00 | Rushikesh Gunjal | 2025-05-17 12:34 | Checked and ok | 2025-05-17 18:16 | Brajesh Upadhyay | Work has been done | 74.767 | 20.4653 | Inspected | RFI Approved | 730 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/412 | Checking shuttering and pouring concrete for Head Wall Second lift | 126806 | 126806 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 10:00 | Kishori Lal | 2025-05-09 13:25 | Work done. | 2025-05-09 17:27 | Brajesh Upadhyay | work has ben done | 74.7282 | 20.3841 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/413 | Checking Reinforcement, shuttering and pouring concrete for Wall Final lift of Retaining Wall | 128288 | 128348 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 10:30 | Rushikesh Gunjal | 2025-05-09 11:31 | Ok | 2025-05-09 17:28 | Brajesh Upadhyay | work has been done | 74.7382 | 20.391 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/414 | Checking Shuttering and laying of PCC Below Pipe | 128318 | 128318 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 11:00 | Kishori Lal | 2025-05-09 13:14 | Work done. | 2025-05-09 17:29 | Brajesh Upadhyay | work has been done | 74.7382 | 20.3912 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/416 | Checking Reinforcement, shuttering and pouring concrete for raft box culvert | 133216 | 133216 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 11:00 | Kishori Lal | 2025-05-09 16:30 | Work done. | 2025-05-09 17:30 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4294 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/417 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 133500 | 133500 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 12:30 | Kishori Lal | 2025-05-09 12:43 | Not Done. |  |  |  | 74.7582 | 20.4315 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/415 | Checking Reinforcement, shuttering and pouring concrete for first lift of Retaining Wall | 130090 | 130170 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 11:30 | Rushikesh Gunjal | 2025-05-10 12:03 | Checked and ok | 2025-05-12 11:46 | Brajesh Upadhyay | Work has been done | 74.7505 | 20.4024 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/516 | Checking shuttering and pouring concrete for Head Wall final lift. | 135020 | 135020 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 18:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-13 18:20 | Kishori Lal | 2025-05-15 18:20 | RHS Not Ready. |  |  |  | 74.7579 | 20.4423 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/236 | Checking shuttering and pouring concrete for Head Wall first lift | 132386 | 132386 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-27 16:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 10:30 | Kishori Lal | 2025-04-29 16:44 | Work done. | 2025-04-29 17:52 | Brajesh Upadhyay | Work has been done | 74.7581 | 20.4217 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/419 | Checking shuttering and pouring concrete for Head Wall second lift | 134083 | 134083 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 13:30 | Kishori Lal | 2025-05-09 12:37 | Work done. | 2025-05-09 17:05 | Brajesh Upadhyay | work has been done | 74.7584 | 20.4366 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/418 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 134004 | 134004 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 13:00 | Kishori Lal | 2025-05-09 12:39 | Not Done. |  |  |  | 74.7584 | 20.4364 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/266 | Checking Shuttering and pouring concrete of PCC for Drain | 135045 | 135100 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 22:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 10:52 | Rushikesh Gunjal | 2025-04-29 15:46 | Checked and ok | 2025-04-29 17:42 | Brajesh Upadhyay | Work has been done | 74.7587 | 20.4452 | Inspected | RFI Approved | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/264 | Checking Shuttering and pouring concrete of PCC for Drain | 134740 | 134780 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 22:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 10:00 | Rushikesh Gunjal | 2025-04-29 16:00 | Ok | 2025-04-29 17:44 | Brajesh Upadhyay | Work has been done | 74.758 | 20.4429 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/291 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135045 | 135100 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 22:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 10:00 | Kishori Lal | 2025-05-01 14:18 | Steel not approved. |  |  |  | 74.7587 | 20.4449 | Inspected | Inspected - Rejected - Work Not Done | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/269 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134980 | 135020 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 22:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 12:00 | Rushikesh Gunjal | 2025-04-29 15:39 | Checked and ok | 2025-04-29 17:40 | Brajesh Upadhyay | Work has been done | 74.7585 | 20.4449 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/270 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135045 | 135100 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 22:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 13:00 | Rushikesh Gunjal | 2025-04-29 15:42 | Ok | 2025-04-29 17:39 | Brajesh Upadhyay | Work has been done | 74.7588 | 20.4453 | Inspected | RFI Approved | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/271 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134645 | 134690 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 22:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 13:30 | Rushikesh Gunjal | 2025-04-29 15:25 | Work done | 2025-04-29 17:38 | Brajesh Upadhyay | Work has been done | 74.7578 | 20.442 | Inspected | RFI Approved | 45 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/277 | Checking of Layout Marking & Excavation for Drain | 135170 | 135210 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 16:30 | Rushikesh Gunjal | 2025-04-29 15:50 | Ok | 2025-04-29 17:30 | Brajesh Upadhyay | Work has been done | 74.7591 | 20.4462 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/275 | Checking of Layout Marking & Excavation for Drain | 135170 | 135210 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 15:30 | Rushikesh Gunjal | 2025-04-29 15:49 | Ok | 2025-04-29 17:34 | Brajesh Upadhyay | Work has been done | 74.759 | 20.4461 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/272 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 129525 | 129535 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 22:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 13:58 | Rushikesh Gunjal | 2025-04-29 17:29 | Work done | 2025-04-29 17:37 | Brajesh Upadhyay | Work has been done | 74.7471 | 20.3979 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/278 | Checking of Layout Marking & Excavation for Drain | 135270 | 135340 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 16:30 | Rushikesh Gunjal | 2025-04-29 15:53 | Work not completed |  |  |  | 74.7594 | 20.4471 | Inspected | Inspected - Rejected - Work Not Done | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/281 | Checking Reinforcement, shuttering and pouring concrete for Raft of Retaining Wall | 130040 | 130140 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 18:09 | Rushikesh Gunjal | 2025-04-29 17:25 | work done | 2025-04-29 17:28 | Brajesh Upadhyay | Work has been done | 74.7387 | 20.3913 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/280 | Checking Shuttering and laying of PCC for head wall | 134083 | 134083 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 15:08 | Kishori Lal | 2025-04-29 17:22 | Work Done RHS. | 2025-04-29 17:29 | Brajesh Upadhyay | Work has been done | 74.7587 | 20.4367 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/279 | Checking of Layout Marking & Excavation for HPC | 134083 | 134083 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 10:07 | Kishori Lal | 2025-04-29 17:20 | Work done RHS. | 2025-04-29 17:30 | Brajesh Upadhyay | Work has been done | 74.7588 | 20.4367 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/284 | Checking Reinforcement, shuttering and pouring concrete for Raft of Retaining Wall | 132910 | 133000 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 11:14 | Rushikesh Gunjal | 2025-04-29 17:19 | Ok | 2025-04-29 17:26 | Brajesh Upadhyay | Work has been done | 74.7381 | 20.391 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/286 | Checking shuttering and pouring concrete for Head Wall second lift | 132386 | 132386 | BHS | Culvert | Hume Pipe Culvert |  | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 12:21 | Kishori Lal | 2025-04-29 16:45 | Work done. | 2025-04-29 17:25 | Brajesh Upadhyay | Work has been done | 74.7582 | 20.4215 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/288 | Checking of Laying of PQC | 121040 | 121200 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 17:24 | Rushikesh Gunjal | 2025-05-10 16:14 | Checked and ok | 2025-05-13 17:44 | Brajesh Upadhyay | Work has been done | 74.7025 | 20.3532 | Inspected | RFI Approved | 160 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/276 | Checking of Layout Marking & Excavation for Drain | 135260 | 135340 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 16:04 | Rushikesh Gunjal | 2025-04-29 15:55 | Ok | 2025-04-29 17:33 | Brajesh Upadhyay | Work has been done | 74.7594 | 20.4473 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/287 | Checking trail Patch of PQC Laying | 121040 | 121100 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 16:30 | Rushikesh Gunjal | 2025-05-01 01:42 | Checked and found ok | 2025-05-01 10:06 | Brajesh Upadhyay | work has been done | 74.6984 | 20.3409 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/274 | Checking of Layout Marking & Excavation for Drain | 134750 | 134820 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 15:02 | Rushikesh Gunjal | 2025-04-29 15:30 | Ok | 2025-04-29 17:35 | Brajesh Upadhyay | Work has been done | 74.758 | 20.4425 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/268 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134740 | 134780 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 22:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 11:30 | Rushikesh Gunjal | 2025-04-29 15:29 | Checked and ok | 2025-04-29 17:40 | Brajesh Upadhyay | Work has been done | 74.758 | 20.4425 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/267 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134690 | 134710 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 22:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 11:30 | Rushikesh Gunjal | 2025-04-29 15:22 | Work done | 2025-04-29 17:41 | Brajesh Upadhyay | Work has been done | 74.7579 | 20.4421 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/282 | Checking Shuttering and pouring of PCC for Retaining Wall | 128288 | 128348 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 10:30 | Rushikesh Gunjal | 2025-04-29 12:25 | Work done | 2025-04-29 17:27 | Brajesh Upadhyay | Work has been done | 74.7383 | 20.391 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/285 | Checking shuttering and pouring concrete for Head Wall Final lift | 131730 | 131730 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 23:30 | Kishori Lal | 2025-05-01 14:52 | Not Done. |  |  |  | 74.7554 | 20.416 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/265 | Checking Shuttering and pouring concrete of PCC for Drain | 134980 | 135020 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 22:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 10:30 | Rushikesh Gunjal | 2025-04-29 16:02 | Checked and ok | 2025-04-29 17:43 | Brajesh Upadhyay | Work has been done | 74.7579 | 20.4429 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/263 | Checking of Laying, Level and FDD of DLC top layer | 126800 | 127500 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 22:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 09:30 | Rushikesh Gunjal | 2025-04-29 12:45 | Checked and found ok | 2025-04-29 17:45 | Brajesh Upadhyay | Work has been done | 74.7311 | 20.386 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/233 | Checking of Laying, Level and FDD of DLC top layer | 125200 | 126000 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-27 16:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 10:00 | Rushikesh Gunjal | 2025-04-28 18:55 | Checked found ok | 2025-04-29 07:04 | Brajesh Upadhyay | work has been done | 74.7209 | 20.3764 | Inspected | RFI Approved | 800 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/257 | Checking of Layout Marking & Excavation for Box Culvert | 133216 | 133216 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 09:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 14:00 | Kishori Lal | 2025-04-29 17:04 | Work done. | 2025-04-29 17:49 | Brajesh Upadhyay | Work has been done | 74.7583 | 20.429 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/239 | Checking of Layout Marking & Excavation for HPC | 133500 | 133500 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-27 16:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 12:30 | Kishori Lal | 2025-04-29 17:11 | Work done. | 2025-04-29 17:51 | Brajesh Upadhyay | Work has been done | 74.7586 | 20.4313 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/423 | Checking Shuttering and laying of PCC Below Pipe | 134718 | 134718 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 15:36 | Kishori Lal | 2025-05-09 12:27 | LHS Work done. | 2025-05-09 17:10 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4426 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/260 | Checking Shuttering and laying of PCC for head wall | 135821 | 135821 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 09:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 15:30 | Kishori Lal | 2025-04-29 18:08 | Work done. | 2025-04-30 11:11 | Brajesh Upadhyay | work has been done | 74.7612 | 20.452 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/326 | Checking of Layout Marking & Excavation for HPC | 134718 | 134718 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 12:00 | Kishori Lal | 2025-05-05 12:11 | Not Done. |  |  |  | 74.7579 | 20.4427 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/247 | Checking Reinforcement, Shuttering and pouring of concrete for Drain Raft | 134645 | 134690 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 16:30 | Rushikesh Gunjal | 2025-04-28 15:56 | Work done | 2025-04-28 17:17 | Brajesh Upadhyay | work done | 74.7579 | 20.4421 | Inspected | RFI Approved | 45 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/253 | Checking of Layout Marking & Excavation for Drain | 135045 | 135100 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 12:00 | Rushikesh Gunjal | 2025-04-28 16:17 | Work done | 2025-04-28 17:07 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4452 | Inspected | RFI Approved | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/250 | Checking shuttering and pouring concrete for Drain PCC | 134740 | 134780 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 13:00 | Rushikesh Gunjal | 2025-04-28 16:02 | Checked and found ok | 2025-04-28 17:21 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4427 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/252 | Checking shuttering and pouring concrete for Drain PCC | 134980 | 135020 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 11:30 | Rushikesh Gunjal | 2025-04-28 16:09 | Work done | 2025-04-28 17:25 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4448 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/251 | Checking of Layout Marking & Excavation for Drain | 134980 | 135020 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 11:00 | Rushikesh Gunjal | 2025-04-28 16:07 | Work done | 2025-04-28 17:23 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4448 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/246 | Checking Reinforcement, Shuttering and pouring of concrete for Drain Slab | 134520 | 134570 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 16:00 | Rushikesh Gunjal | 2025-04-28 15:51 | Work done | 2025-04-28 17:16 | Brajesh Upadhyay | work done | 74.7579 | 20.4412 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/248 | Checking shuttering and pouring concrete for Drain PCC | 134690 | 134710 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 14:00 | Rushikesh Gunjal | 2025-04-28 16:00 | Work done | 2025-04-28 17:18 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4429 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/254 | Checking shuttering and pouring concrete for Drain PCC | 135045 | 135100 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 12:30 | Rushikesh Gunjal | 2025-04-28 16:16 | Work done | 2025-04-28 17:06 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4453 | Inspected | RFI Approved | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/245 | Checking Reinforcement, Shuttering and pouring of concrete for Drain Wall | 129525 | 129535 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 15:30 | Rushikesh Gunjal | 2025-04-28 15:31 | Checked and found ok | 2025-04-28 17:14 | Brajesh Upadhyay | work has been done | 74.7474 | 20.398 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/256 | Checking Shuttering and laying of PCC Below Pipe | 132386 | 132386 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 09:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 13:30 | Kishori Lal | 2025-04-29 16:48 | Work done. | 2025-04-29 17:50 | Brajesh Upadhyay | Work has been done | 74.7581 | 20.4215 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/258 | Checking of Layout Marking & Excavation for HPC | 135368 | 135368 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 09:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 14:30 | Kishori Lal | 2025-04-29 18:02 | Work done. | 2025-04-30 11:10 | Brajesh Upadhyay | Work has been done | 74.7596 | 20.4479 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/255 | Checking shuttering and pouring concrete for Head Wall Second lift | 127176 | 127176 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 13:00 | Kishori Lal | 2025-04-29 16:00 | Shuttering alignment not proper. |  |  |  | 74.7295 | 20.3847 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/243 | Checking Shuttering and laying of PCC for Retaining Wall | 128288 | 128348 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 14:30 | Rushikesh Gunjal | 2025-04-28 15:24 | Checked and found ok | 2025-04-28 17:10 | Brajesh Upadhyay | work has been done | 74.7383 | 20.391 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/237 | Checking of Layout Marking & Excavation for HPC | 133023 | 133023 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-27 16:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 11:00 | Kishori Lal | 2025-04-29 16:53 | Work done. | 2025-04-29 17:52 | Brajesh Upadhyay | Work has been done | 74.7582 | 20.4271 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/261 | Checking of Layout Marking & Excavation for HPC | 136078 | 136078 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 09:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 16:06 | Kishori Lal | 2025-04-29 18:13 | Not Done. |  |  |  | 74.7624 | 20.4539 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/238 | Checking of Layout Marking & Excavation for HPC | 133216 | 133216 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-27 16:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 12:00 | Kishori Lal | 2025-04-29 17:06 | Wrong Chainage. |  |  |  | 74.7583 | 20.4291 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/240 | Checking Shuttering and laying of PCC Below Pipe | 134004 | 134004 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-27 16:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 14:00 | Kishori Lal | 2025-04-29 17:17 | Work done. | 2025-04-29 17:50 | Brajesh Upadhyay | Work has been done | 74.758 | 20.4373 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/293 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134740 | 134780 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 22:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 10:30 | Rushikesh Gunjal | 2025-05-01 11:30 | Checked and ok | 2025-05-01 16:55 | Brajesh Upadhyay | Work has been done | 74.7579 | 20.4428 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/234 | Checking of Laying, Level and FDD of DLC top layer | 126000 | 126800 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-27 16:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 15:30 | Rushikesh Gunjal | 2025-04-29 17:11 | Checked and found ok | 2025-04-29 17:54 | Brajesh Upadhyay | Work has been done | 74.722 | 20.3789 | Inspected | RFI Approved | 800 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/235 | Checking shuttering and pouring concrete for Head Wall second lift | 131730 | 131730 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-27 16:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 10:00 | Kishori Lal | 2025-04-29 16:28 | Work done. | 2025-04-29 17:53 | Brajesh Upadhyay | Work has been done | 74.7555 | 20.4161 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/325 | Checking of Layout Marking & Excavation for HPC | 134460 | 134460 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 13:30 | Kishori Lal | 2025-05-05 12:24 | Not Done. |  |  |  | 74.7579 | 20.4389 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/444 | Checking shuttering and pouring concrete for Head Wall final lift | 126806 | 126806 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 09:40 | Kishori Lal | 2025-05-10 12:59 | Work done. | 2025-05-11 11:18 | Brajesh Upadhyay | work done | 74.7268 | 20.3829 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/445 | Checking pipe laying and joint filling & Checking shuttering and pouring concrete for Head Wall second lift | 128318 | 128318 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 10:00 | Kishori Lal | 2025-05-10 12:52 | Work done. | 2025-05-11 11:19 | Brajesh Upadhyay | work done | 74.7377 | 20.3914 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/313 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 134500 | 134960 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 09:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-04 11:30 | Rushikesh Gunjal | 2025-05-17 12:50 | Ok | 2025-05-17 18:23 | Brajesh Upadhyay | Work has been done | 74.7578 | 20.4418 | Inspected | RFI Approved | 460 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/315 | Checking of Layout Marking & Excavation for HPC | 126806 | 126806 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 15:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 12:00 | Kishori Lal | 2025-05-05 13:48 | Work already done. | 2025-05-05 17:56 | Brajesh Upadhyay | work done | 74.7268 | 20.3829 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/476 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 137150 | 137900 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 16:30 | Saurabh SE | 2025-05-13 14:13 | BT not dismentaling |  |  |  | 74.7661 | 20.4629 | Inspected | Inspected - Rejected - Work Not Done | 750 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/259 | Checking of Layout Marking & Excavation for HPC | 135821 | 135821 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 09:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 15:02 | Kishori Lal | 2025-04-29 18:06 | Work done. | 2025-04-30 11:10 | Brajesh Upadhyay | Work has been done | 74.7612 | 20.4518 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/273 | Checking of Layout Marking & Excavation for Drain | 134780 | 134820 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 14:30 | Rushikesh Gunjal | 2025-04-29 15:31 | Ok | 2025-04-29 17:36 | Brajesh Upadhyay | Work has been done | 74.7579 | 20.4426 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/421 | Checking Shuttering and pouring concrete of PCC for Drain | 134600 | 134700 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 14:30 | Rushikesh Gunjal | 2025-05-09 10:35 | Ok | 2025-05-09 16:52 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4422 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/262 | Checking of Laying, Level and FDD of DLC top layer | 126000 | 126800 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 13:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 15:00 | Rushikesh Gunjal | 2025-04-28 18:58 | Checked and ok | 2025-04-29 07:01 | Brajesh Upadhyay | work has been done | 74.7226 | 20.3799 | Inspected | RFI Approved | 800 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/289 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134740 | 134780 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 22:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 09:00 | Kishori Lal | 2025-05-01 14:26 | Steel not approved. |  |  |  | 74.758 | 20.4427 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/296 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134645 | 134690 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 12:30 | Rushikesh Gunjal | 2025-05-01 11:40 | Ok | 2025-05-01 16:52 | Brajesh Upadhyay | Work has been done | 74.7579 | 20.4417 | Inspected | RFI Approved | 45 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/294 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134980 | 135020 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 22:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 11:30 | Rushikesh Gunjal | 2025-05-01 11:34 | Ok | 2025-05-01 16:53 | Brajesh Upadhyay | Work has been done | 74.7585 | 20.4446 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/241 | Checking Shuttering and laying of PCC for Retaining Wall | 130090 | 130170 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-27 16:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 16:00 | Rushikesh Gunjal | 2025-04-28 15:36 | Checked and found not ok Work not done |  |  |  | 74.7503 | 20.4024 | Inspected | Inspected - Rejected - Work Not Done | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/301 | Checking Shuttering and pouring concrete of PCC for Drain | 135170 | 135210 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 15:05 | Rushikesh Gunjal | 2025-05-01 11:13 | Ok | 2025-05-01 16:47 | Brajesh Upadhyay | Work has been done | 74.7591 | 20.4462 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/299 | Checking Shuttering and pouring concrete of PCC for Drain | 135170 | 135210 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 14:00 | Rushikesh Gunjal | 2025-05-01 11:17 | Ok | 2025-05-01 16:49 | Brajesh Upadhyay | Work has been done | 74.7591 | 20.4462 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/305 | Checking Reinforcement, shuttering and pouring concrete for Raft of Retaining Wall | 140450 | 141000 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 17:30 | Rushikesh Gunjal | 2025-05-01 10:41 | Not ok |  |  |  | 74.7817 | 20.4906 | Inspected | Inspected - Rejected - Work Not Done | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/304 | Checking Reinforcement, shuttering and pouring concrete for Raft of Retaining Wall | 128288 | 128348 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 17:08 | Rushikesh Gunjal | 2025-05-01 12:49 | Ok | 2025-05-01 16:45 | Brajesh Upadhyay | Work has been done | 74.7381 | 20.3909 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/308 | Checking Pipe laying, shuttering & concrete pouring for encasing of pipe. | 132386 | 132386 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 11:11 | Kishori Lal | 2025-05-01 14:47 | Not done. |  |  |  | 74.7582 | 20.4215 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/249 | Checking of Layout Marking & Excavation for Drain | 134740 | 134780 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 08:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-28 10:48 | Rushikesh Gunjal | 2025-04-28 16:04 | Checked and found ok | 2025-04-28 17:20 | Brajesh Upadhyay | work hasbeen done | 74.758 | 20.4428 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/323 | Checking Shuttering and laying of PCC for head wall | 134004 | 134004 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 16:30 | Kishori Lal | 2025-05-05 12:43 | Work done. | 2025-05-05 17:50 | Brajesh Upadhyay | work done | 74.7586 | 20.4363 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/428 | Checking Shuttering and laying of PCC for head wall & Below pipe | 138728 | 138728 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 18:00 | Kishori Lal | 2025-05-09 11:45 | Not Ready. |  |  |  | 74.7724 | 20.4757 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/427 | Checking shuttering and pouring concrete for Head Wall first lift & PCC Below Pipe | 137018 | 137018 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 17:39 | Kishori Lal | 2025-05-09 11:56 | Not Satisfactory. |  |  |  | 74.7658 | 20.4615 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/322 | Checking Shuttering and laying of PCC for head wall | 133500 | 133500 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 16:00 | Kishori Lal | 2025-05-05 12:52 | Work done. | 2025-05-05 17:49 | Brajesh Upadhyay | work done | 74.7587 | 20.4316 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/426 | Checking Shuttering and laying of PCC for head wall & Below pipe | 136078 | 136078 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 17:00 | Kishori Lal | 2025-05-09 12:07 | Not Ready. |  |  |  | 74.7623 | 20.4539 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/332 | Checking Shuttering and laying of PCC of Box Culvert | 133216 | 133216 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 10:00 | Kishori Lal | 2025-05-05 12:57 | Without checking work. |  |  |  | 74.7584 | 20.4289 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/424 | Checking Shuttering and laying of PCC Below Pipe | 135178 | 135178 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 16:00 | Kishori Lal | 2025-05-09 12:16 | Wrong Chainage. |  |  |  | 74.7592 | 20.4469 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/321 | Checking shuttering and pouring concrete for Head Wall final lift | 132669 | 132669 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 10:30 | Kishori Lal | 2025-05-05 13:11 | Work done. | 2025-05-05 17:47 | Brajesh Upadhyay | work done | 74.7584 | 20.424 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/320 | Checking shuttering and pouring concrete for Head Wall final lift | 132386 | 132386 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 09:03 | Kishori Lal | 2025-05-05 13:14 | Work done. | 2025-05-05 17:46 | Brajesh Upadhyay | work done | 74.7583 | 20.4215 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/283 | Checking Shuttering and pouring of PCC for Retaining Wall | 140450 | 141000 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-28 23:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-29 12:00 | Rushikesh Gunjal | 2025-05-01 10:42 | Not ok |  |  |  | 74.7816 | 20.4906 | Inspected | Inspected - Rejected - Work Not Done | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/302 | Checking Shuttering and pouring concrete of PCC for Drain | 135270 | 135340 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 15:30 | Rushikesh Gunjal | 2025-05-01 11:04 | Checked and found ok | 2025-05-01 16:46 | Brajesh Upadhyay | Work has been done | 74.7593 | 20.4473 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/298 | Checking Shuttering and pouring concrete of PCC for Drain | 134750 | 134820 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 13:30 | Rushikesh Gunjal | 2025-05-01 11:24 | Checked and ok | 2025-05-01 16:50 | Brajesh Upadhyay | Work has been done | 74.7579 | 20.4431 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/297 | Checking Shuttering and pouring concrete of PCC for Drain | 134780 | 134820 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 13:00 | Rushikesh Gunjal | 2025-05-01 11:25 | Ok | 2025-05-01 16:51 | Brajesh Upadhyay | Work has been done | 74.7579 | 20.4431 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/306 | Checking Reinforcement, shuttering and pouring concrete for Wall first lift of Retaining Wall | 132910 | 133000 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 17:30 | Rushikesh Gunjal | 2025-05-01 12:02 | Checked and ok | 2025-05-01 16:44 | Brajesh Upadhyay | Work has been done | 74.7582 | 20.4268 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/292 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134690 | 134710 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 22:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 11:00 | Rushikesh Gunjal | 2025-05-01 11:42 | Ok | 2025-05-01 16:55 | Brajesh Upadhyay | Work has been done | 74.7578 | 20.442 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/346 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135270 | 135340 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 16:09 | Rushikesh Gunjal | 2025-05-05 13:26 | Not done |  |  |  | 74.7595 | 20.4472 | Inspected | Inspected - Rejected - Work Not Done | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/300 | Checking Shuttering and pouring concrete of PCC for Drain | 135260 | 135340 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 14:30 | Kishori Lal | 2025-05-01 14:14 | Work done. | 2025-05-01 16:48 | Brajesh Upadhyay | Work has been done | 74.7594 | 20.4472 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/290 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134980 | 135020 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 22:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 09:30 | Kishori Lal | 2025-05-01 14:22 | Steel not approved. |  |  |  | 74.7586 | 20.4445 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/310 | Checking shuttering and pouring concrete for Head Wall first lift | 134083 | 134083 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-07 13:13 | Kishori Lal | 2025-05-01 14:40 | Work done. | 2025-05-01 16:43 | Brajesh Upadhyay | Work has been done | 74.7587 | 20.4368 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/309 | Checking Shuttering and laying of PCC for head wall | 134083 | 134083 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 12:12 | Kishori Lal | 2025-05-01 14:38 | Work done. | 2025-05-01 16:43 | Brajesh Upadhyay | Work has been done | 74.7581 | 20.4373 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/345 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135170 | 135210 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 18:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 15:30 | Rushikesh Gunjal | 2025-05-05 13:33 | Checked and found not ok |  |  |  | 74.7592 | 20.4466 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/318 | Checking Shuttering and laying of PCC for head wall | 128318 | 128318 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 11:02 | Kishori Lal | 2025-05-05 13:37 | Work done. | 2025-05-05 18:00 | Brajesh Upadhyay | work done | 74.7382 | 20.3913 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/349 | Checking Shuttering and laying of PCC for head wall | 125737 | 125737 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 11:00 | Kishori Lal | 2025-05-08 16:26 | Work done | 2025-05-08 17:01 | Brajesh Upadhyay | Work has been done | 74.7216 | 20.3762 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/342 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135170 | 135210 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 18:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 14:04 | Rushikesh Gunjal | 2025-05-05 13:40 | Ok | 2025-05-05 17:34 | Brajesh Upadhyay | work done | 74.7593 | 20.4468 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/295 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135045 | 135100 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 22:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 12:00 | Rushikesh Gunjal | 2025-05-01 11:36 | Ok | 2025-05-01 16:52 | Brajesh Upadhyay | Work has been done | 74.7587 | 20.4453 | Inspected | RFI Approved | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/317 | Checking shuttering and pouring concrete for Head Wall second lift | 127930 | 127930 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 15:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 13:56 | Kishori Lal | 2025-05-05 13:43 | Work done. | 2025-05-05 17:59 | Brajesh Upadhyay | work done | 74.7353 | 20.3891 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/340 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134980 | 135020 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 18:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 17:03 | Rushikesh Gunjal | 2025-05-05 13:44 | Ok | 2025-05-05 17:32 | Brajesh Upadhyay | work done | 74.7587 | 20.4453 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/312 | Checking of Laying, Level and FDD of DLC top layer | 127500 | 128200 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-03 08:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-03 11:00 | Rushikesh Gunjal | 2025-05-03 17:39 | Checked and found ok | 2025-05-03 19:54 | Brajesh Upadhyay | Work done | 74.4838 | 19.9184 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/338 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134690 | 134710 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 18:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 16:00 | Rushikesh Gunjal | 2025-05-05 13:54 | Ok | 2025-05-05 17:30 | Brajesh Upadhyay | work done | 74.7579 | 20.4422 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/316 | Checking shuttering and pouring concrete for Head Wall first lift | 125950 | 125950 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 15:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 14:00 | Kishori Lal | 2025-05-05 13:52 | Work done. | 2025-05-05 17:58 | Brajesh Upadhyay | work done | 74.7215 | 20.3773 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/314 | Checking of Layout Marking & Excavation for HPC | 125737 | 125737 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 15:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 10:00 | Kishori Lal | 2025-05-05 14:44 | Work done. | 2025-05-05 17:55 | Brajesh Upadhyay | work done | 74.7207 | 20.3754 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/339 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134740 | 134780 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 16:30 | Rushikesh Gunjal | 2025-05-05 13:49 | Ok | 2025-05-05 17:31 | Brajesh Upadhyay | work done | 74.7578 | 20.4428 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/341 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135045 | 135100 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 18:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 17:30 | Rushikesh Gunjal | 2025-05-05 13:43 | Ok | 2025-05-05 17:33 | Brajesh Upadhyay | work done | 74.7587 | 20.4454 | Inspected | RFI Approved | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/343 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135260 | 135340 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 13:30 | Rushikesh Gunjal | 2025-05-05 13:37 | Ok | 2025-05-05 17:36 | Brajesh Upadhyay | work done | 74.7594 | 20.4475 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/344 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134750 | 134820 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 14:30 | Rushikesh Gunjal | 2025-05-05 13:48 | Ok | 2025-05-05 17:37 | Brajesh Upadhyay | work done | 74.758 | 20.4431 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/331 | Checking shuttering and pouring concrete for Head Wall second lift | 124043 | 124043 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 12:00 | Kishori Lal | 2025-05-05 14:53 | Work done. | 2025-05-05 17:38 | Brajesh Upadhyay | work done | 74.7088 | 20.3655 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/335 | Checking of Layout Marking & Excavation for HPC | 135178 | 135178 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 16:00 | Kishori Lal | 2025-05-05 12:06 | Work done. | 2025-05-05 17:42 | Brajesh Upadhyay | work done | 74.759 | 20.4468 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/319 | Checking shuttering and pouring concrete for Head Wall final lift | 131730 | 131730 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 12:00 | Kishori Lal | 2025-05-05 13:20 | Work done. | 2025-05-05 17:45 | Brajesh Upadhyay | work done | 74.7553 | 20.4163 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/333 | Checking of Layout Marking & Excavation for HPC | 134460 | 134460 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 09:00 | Kishori Lal | 2025-05-05 12:27 | Work done | 2025-05-05 17:40 | Brajesh Upadhyay | work done | 74.7582 | 20.439 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/334 | Checking of Layout Marking & Excavation for HPC | 134718 | 134718 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-04 16:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-05 10:30 | Kishori Lal | 2025-05-05 12:14 | LHS Work done. | 2025-05-05 17:41 | Brajesh Upadhyay | work done | 74.7576 | 20.4422 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/367 | Checking Reinforcement, shuttering and pouring concrete for Drain wall | 135270 | 135340 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 16:30 | Rushikesh Gunjal | 2025-05-08 16:44 | Work not done |  |  |  | 74.7594 | 20.4471 | Inspected | Inspected - Rejected - Work Not Done | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/370 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 139950 | 140680 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 09:48 | Rushikesh Gunjal | 2025-05-17 12:25 | Ok | 2025-05-17 18:21 | Brajesh Upadhyay | Work has been done | 74.7744 | 20.4791 | Inspected | RFI Approved | 730 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/366 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135260 | 135300 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 17:44 | Rushikesh Gunjal | 2025-05-08 11:21 | Wrong RFI |  |  |  | 74.7593 | 20.447 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/365 | Checking Reinforcement, shuttering and pouring concrete for Drain wall | 135260 | 135340 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 16:43 | Rushikesh Gunjal | 2025-05-07 17:33 | Ok | 2025-05-08 12:54 | Brajesh Upadhyay | Work done | 74.7596 | 20.4477 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/364 | Checking Shuttering and laying of PCC for head wall | 135230 | 135230 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 15:42 | Kishori Lal | 2025-05-06 11:36 | Not Done. |  |  |  | 74.7595 | 20.4469 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/354 | Checking shuttering and pouring concrete for Head Wall first lift | 128318 | 128318 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 11:34 | Kishori Lal | 2025-05-06 12:53 | Work done. | 2025-05-06 17:22 | Brajesh Upadhyay | Work has been done | 74.7382 | 20.3911 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/353 | Checking Reinforcement, shuttering and pouring concrete for Wall first lift of Retaining Wall | 128288 | 128348 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 10:30 | Rushikesh Gunjal | 2025-05-06 12:42 | Ok | 2025-05-06 17:24 | Brajesh Upadhyay | Work has been done | 74.7383 | 20.3913 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/363 | Checking Shuttering and laying of PCC for head wall | 135178 | 135178 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 14:41 | Kishori Lal | 2025-05-08 13:39 | Wrong Chainage. |  |  |  | 74.7593 | 20.4467 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/362 | Checking Reinforcement, shuttering and pouring concrete for Drain wall | 135170 | 135210 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 13:30 | Rushikesh Gunjal | 2025-05-06 11:55 | Ok | 2025-05-06 11:56 | Brajesh Upadhyay | Work has been done | 74.7591 | 20.4462 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/361 | Checking Reinforcement, shuttering and pouring concrete for Drain wall | 134750 | 134820 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 11:50 | Rushikesh Gunjal | 2025-05-06 12:11 | Checked and found ok | 2025-05-06 17:19 | Brajesh Upadhyay | Work has been done | 74.758 | 20.443 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/351 | Checking Shuttering and laying of PCC for head wall | 126806 | 126806 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 10:31 | Kishori Lal | 2025-05-06 12:58 | Work done. | 2025-05-06 17:27 | Brajesh Upadhyay | Work has been done | 74.7268 | 20.3829 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/359 | Checking of Layout Marking & Excavation for Drain | 134650 | 134700 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 10:37 | Rushikesh Gunjal | 2025-05-06 12:15 | Not ok |  |  |  | 74.7578 | 20.442 | Inspected | Inspected - Rejected - Work Not Done | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/352 | Checking shuttering and pouring concrete for Head Wall final lift | 127930 | 127930 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 09:00 | Kishori Lal | 2025-05-06 12:55 | Work done. | 2025-05-06 17:26 | Brajesh Upadhyay | Work has been done | 74.7363 | 20.3894 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/360 | Checking Shuttering and laying of PCC for head wall | 134718 | 134718 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 11:38 | Kishori Lal | 2025-05-06 11:54 | Work done. | 2025-05-06 11:55 | Brajesh Upadhyay | Work has been done | 74.7577 | 20.4424 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/358 | Checking Shuttering and laying of PCC for head wall | 134460 | 134460 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 10:00 | Kishori Lal | 2025-05-06 12:01 | Work done. | 2025-05-06 12:02 | Brajesh Upadhyay | Work has been done | 74.7583 | 20.4388 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/356 | Checking shuttering and pouring concrete for Head Wall first lift | 134004 | 134004 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 16:00 | Kishori Lal | 2025-05-06 12:14 | Work done. | 2025-05-06 17:20 | Brajesh Upadhyay | Work has been done | 74.7586 | 20.4364 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/355 | Checking shuttering and pouring concrete for Head Wall first lift | 133500 | 133500 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 16:35 | Kishori Lal | 2025-05-06 12:41 | Work done. | 2025-05-06 17:21 | Brajesh Upadhyay | Work has been done | 74.7581 | 20.4314 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/350 | Checking shuttering and pouring concrete for Head Wall second lift | 125950 | 125950 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 12:00 | Kishori Lal | 2025-05-08 16:28 | Work done. | 2025-05-08 17:00 | Brajesh Upadhyay | Work has been done | 74.7211 | 20.3762 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/368 | Checking of Layout Marking & Excavation for HPC | 137018 | 137018 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-05 23:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-06 12:00 | Kishori Lal | 2025-05-06 11:24 | RHS work done. | 2025-05-06 11:48 | Brajesh Upadhyay | Work has been done | 74.7659 | 20.4615 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/311 | Checking of Laying of PQC | 121200 | 121800 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-03 08:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-03 18:00 | Rushikesh Gunjal | 2025-05-05 23:16 | Checked and found ok | 2025-05-06 12:01 | Brajesh Upadhyay | Work has been done | 74.6992 | 20.3473 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/307 | Checking Shuttering and pouring of PCC for Retaining Wall | 130090 | 130170 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 18:10 | Rushikesh Gunjal | 2025-05-05 17:03 | Ok | 2025-05-06 12:03 | Brajesh Upadhyay | Work has been done | 74.7503 | 20.4025 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/303 | Checking Reinforcement, shuttering and pouring concrete for Wall first lift of Retaining Wall | 130040 | 130140 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-04-29 23:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-04-30 16:07 | Rushikesh Gunjal | 2025-05-05 17:01 | Ok | 2025-05-06 12:04 | Brajesh Upadhyay | Work has been done | 74.7499 | 20.4021 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/500 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 139950 | 140680 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-12 09:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 11:50 | Saurabh SE | 2025-05-13 13:09 | Work not done |  |  |  | 74.7768 | 20.4857 | Inspected | Inspected - Rejected - Work Not Done | 730 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/432 | Dismantling the existing bridge | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 12:46 | Kishori Lal | 2025-05-09 13:08 | Work done. | 2025-05-09 16:34 | Brajesh Upadhyay | Dismantling work has been done | 74.7483 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/431 | Checking Reinforcement, shuttering and pouring concrete for Wall final lift of Retaining Wall | 130040 | 130140 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 14:30 | Rushikesh Gunjal | 2025-05-09 11:24 | Ok | 2025-05-09 16:41 | Brajesh Upadhyay | work has been done | 74.75 | 20.4022 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/502 | Checking Level and FDD test for GSB Top | 132950 | 133500 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-12 09:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 10:55 | Saurabh SE | 2025-05-17 15:51 | Level and FDD found ok | 2025-05-17 18:00 | Brajesh Upadhyay | Work has been done | 74.7486 | 20.3998 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/508 | Checking Level and FDD test for GSB Top | 133500 | 134500 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 09:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-13 12:00 | Rushikesh Gunjal | 2025-05-17 11:29 | Ok | 2025-05-17 17:59 | Brajesh Upadhyay | Work has been done | 74.7583 | 20.4291 | Inspected | RFI Approved | 1000 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/519 | Checking Reinforcement, shuttering and pouring concrete for Drain slab | 135170 | 135210 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 18:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-14 18:35 | Rushikesh Gunjal | 2025-05-14 15:25 | Ok | 2025-05-14 18:09 | Brajesh Upadhyay | Work has been done | 74.7588 | 20.4455 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/371 | Checking of Laying of PQC | 122550 | 123150 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-07 10:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-08 18:00 | Rushikesh Gunjal | 2025-05-16 12:22 | Checked and found ok | 2025-05-17 18:21 | Brajesh Upadhyay | Work has been done | 74.7067 | 20.3599 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/422 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134600 | 134700 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 18:33 | Rushikesh Gunjal | 2025-05-09 10:37 | Ok | 2025-05-09 17:09 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4422 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/420 | Checking Shuttering and laying of PCC Below Pipe | 134460 | 134460 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 07:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 14:00 | Kishori Lal | 2025-05-09 12:33 | Work done. | 2025-05-09 17:06 | Brajesh Upadhyay | work has been done | 74.7579 | 20.44 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/518 | Checking shuttering and pouring concrete for Head Wall final lift | 135230 | 135230 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 18:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-14 12:30 | Kishori Lal | 2025-05-15 18:39 | Work done. | 2025-05-16 11:00 | Brajesh Upadhyay | work has been done | 74.7593 | 20.4468 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/504 | Checking pipe laying and joint filling & Checking shuttering and pouring concrete for Head Wall second lift. | 135020 | 135020 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 09:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-13 11:00 | Kishori Lal | 2025-05-15 18:15 | Work done. | 2025-05-16 11:11 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4419 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/522 | Checking Level & FDD test for GSB Top Layer | 137750 | 138580 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-14 13:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-14 13:26 | Rushikesh Gunjal | 2025-05-14 15:34 | Wrong RFI |  |  |  | 74.768 | 20.4672 | Inspected | Inspected - Rejected - Work Not Done | 830 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/523 | Checking Level & FDD test for GSB Top Layer | 138580 | 139040 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-14 13:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-14 13:30 | Rushikesh Gunjal | 2025-05-14 15:38 | Wrong RFI |  |  |  | 74.7719 | 20.4749 | Inspected | Inspected - Rejected - Work Not Done | 460 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/524 | Checking Level & FDD test for GSB Top layer | 139040 | 139770 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-14 13:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-14 13:50 | Rushikesh Gunjal | 2025-05-14 15:41 | Wrong RFI |  |  |  | 74.7738 | 20.4778 | Inspected | Inspected - Rejected - Work Not Done | 730 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/525 | Checking FDD test for Subgrade 1st layer | 139770 | 140050 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-14 13:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-14 15:50 | Rushikesh Gunjal | 2025-05-16 17:28 | Checked and found ok | 2025-05-16 19:15 | Brajesh Upadhyay | work has been done | 74.7754 | 20.4843 | Inspected | RFI Approved | 280 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1817 | Checking Of Layout Marking , Excavation & Laying PCC For HPC | 124418 | 124418 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 14:00 | Rushikesh Gunjal | 2025-12-02 17:41 | Work already done | 2025-12-03 09:04 | Brajesh Upadhyay | work has been done | 74.7109 | 20.3682 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1645 | Checking Of Laying DLC Top | 134540 | 135160 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 16:39 | Rushikesh Gunjal | 2025-10-30 15:45 | Work was already done | 2025-10-31 07:44 | Brajesh Upadhyay | work has been done | 74.7596 | 20.4478 | Inspected | RFI Approved | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1691 | Checking Of Reinforcement , shuttering & Pouring Concrete For Wall Final lift , Top Haunch & Slab Of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-27 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-28 16:00 | Rushikesh Gunjal | 2025-10-29 12:45 | Work done | 2025-10-30 10:55 | Brajesh Upadhyay | work has been done | 74.7828 | 20.4996 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1654 | Checking Of Laying PQC Top | 129810 | 130610 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 17:08 | Rushikesh Gunjal | 2025-10-30 11:18 | Work was already done | 2025-10-30 11:26 | Brajesh Upadhyay | work has been done | 74.7507 | 20.4036 | Inspected | RFI Approved | 800 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1669 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 129703 | 129800 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 12:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 12:42 | Rushikesh Gunjal | 2025-10-30 11:20 | Work was already done | 2025-10-30 11:25 | Brajesh Upadhyay | work has been done | 74.7508 | 20.4036 | Inspected | RFI Approved | 97 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1651 | Checking Of Laying DLC Top | 129360 | 129660 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 16:44 | Rushikesh Gunjal | 2025-10-30 11:17 | Work was already done | 2025-10-30 11:27 | Brajesh Upadhyay | work has been done | 74.7509 | 20.4037 | Inspected | RFI Approved | 300 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1638 | Checking Of Level & FDD Test For GSB Top | 129720 | 130210 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 16:30 | Rushikesh Gunjal | 2025-10-30 11:16 | Work was already done | 2025-10-30 11:29 | Brajesh Upadhyay | work has been done | 74.7508 | 20.4036 | Inspected | RFI Approved | 490 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1692 | Checking Of Pipe Laying & Jointing Of HPC | 117008 | 117008 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-28 17:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-29 17:33 | Rushikesh Gunjal | 2025-10-29 16:51 | BHS Work not done |  |  |  | 74.6729 | 20.3179 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1682 | Checking Of Level & FDD Test For GSB Top | 123700 | 123781 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 16:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:49 | Rushikesh Gunjal | 2025-10-28 12:41 | Work was already done | 2025-10-28 18:31 | Brajesh Upadhyay | work has been done | 74.7071 | 20.3607 | Inspected | RFI Approved | 81 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2066 | Checking Of Reinforcement, Shuttering & Pouring Concrete For R. Wall 1st Lift A1,A2 Of MNB | 123800 | 123800 | LHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-06 18:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-07 11:30 | Kishori Lal | 2026-02-07 15:05 | Work done. | 2026-02-08 09:56 | Brajesh Upadhyay | work has been done | 74.7052 | 20.3629 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2027 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Terminal Slab A1,A2 Of BC | 140928 | 140928 | LHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-07 18:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-08 13:00 | Rushikesh Gunjal | 2026-01-09 16:20 | Work done | 2026-01-10 09:35 | Brajesh Upadhyay | work has been done | 74.7821 | 20.4922 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1265 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 120229 | 120229 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-14 10:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 17:00 | Kishori Lal | 2025-09-14 17:21 | Work not done. |  |  |  | 74.6929 | 20.3353 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2005 | Checking Of Pouring Concrete For Raft Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-29 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-30 14:00 | Rushikesh Gunjal | 2026-01-07 11:02 | Work done | 2026-01-10 09:36 | Brajesh Upadhyay | work has been done | 74.7075 | 20.3637 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1992 | Checking Of Layout Marking , Excavation & Laying PCC For Cut Off Wall Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-26 15:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-27 11:00 | Kishori Lal | 2025-12-29 11:28 | Work not done. |  |  |  | 74.7469 | 20.3991 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1998 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Cut Off Wall Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-27 17:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-28 09:00 | Kishori Lal | 2025-12-29 11:30 | Work not done. |  |  |  | 74.747 | 20.3996 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2065 | Checking Of Reinforcement, Shuttering & Pouring Concrete For R. Wall Raft A1,A2 Of MNB | 123800 | 123800 | LHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-05 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-06 10:30 | Kishori Lal | 2026-02-07 15:03 | Work done. | 2026-02-08 09:57 | Brajesh Upadhyay | work has been done | 74.7073 | 20.3637 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2006 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135130 | 135140 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-30 18:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-31 11:00 | Rushikesh Gunjal | 2025-12-31 15:28 | Work done | 2026-01-01 14:07 | Brajesh Upadhyay | work has been done | 74.758 | 20.4424 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2001 | Checking Of Reinforcement & shuttering For MNB Raft | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-29 14:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-30 09:30 | Kishori Lal | 2025-12-31 17:19 | Reinforcement and Shuttering work checked and found satisfactory. | 2026-01-01 14:08 | Brajesh Upadhyay | work has been done | 74.7073 | 20.3636 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2000 | Checking Of Reinforcement, shuttering and pouring concrete for Drain Raft | 135130 | 135140 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-27 18:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-28 12:00 | Rushikesh Gunjal | 2025-12-29 16:42 | Work already done | 2026-01-01 14:09 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4423 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1999 | Checking of Reinforcement, shuttering and pouring concrete for Drain Raft | 134700 | 134715 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-27 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-28 11:00 | Rushikesh Gunjal | 2025-12-29 16:51 | Work already done | 2026-01-01 14:09 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4425 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1990 | Checking Of Layout Marking , Excavation & Laying PCC For MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-25 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-26 11:00 | Kishori Lal | 2025-12-29 12:31 | Work done. | 2026-01-01 14:09 | Brajesh Upadhyay | work has been done | 74.7076 | 20.3637 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1250 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 120360 | 120400 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-13 18:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 15:00 | Kishori Lal | 2025-09-14 17:30 | Not Ready. |  |  |  | 74.6937 | 20.3364 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1802 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall second Lift Of HPC | 125737 | 125737 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 15:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 16:00 | Rushikesh Gunjal | 2025-12-01 16:01 | Work done | 2025-12-02 09:08 | Brajesh Upadhyay | work has been done | 74.7203 | 20.3757 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2004 | Checking Of Reinforcement, shuttering and pouring concrete for Drain Wall | 135130 | 135140 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-29 17:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-30 13:00 | Kishori Lal | 2025-12-31 16:39 | Work done. | 2026-01-01 14:07 | Brajesh Upadhyay | work has been done | 74.7591 | 20.4459 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2003 | Checking Of Reinforcement, Shuttering and pouring concrete for Drain Wall | 134700 | 134715 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-29 17:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-30 10:00 | Kishori Lal | 2025-12-31 16:42 | Work done. | 2026-01-01 14:08 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4419 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2002 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 134723 | 134750 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-29 17:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-30 11:00 | Kishori Lal | 2025-12-31 16:43 | Work already done. | 2026-01-01 14:08 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4422 | Inspected | RFI Approved | 27 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1801 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 123410 | 123781 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 15:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 15:00 | Rushikesh Gunjal | 2025-12-01 15:53 | Check fdd test found satisfactory result | 2025-12-02 09:08 | Brajesh Upadhyay | work has been done | 74.7091 | 20.3661 | Inspected | RFI Approved | 371 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/938 | Checking Of Laying DLC Top | 137060 | 137870 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-22 17:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-23 17:30 | Rushikesh Gunjal | 2025-07-24 12:39 | Check and found OK | 2025-07-28 09:59 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4323 | Inspected | RFI Approved | 810 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/933 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134700 | 134721 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-21 18:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-22 13:30 | Rushikesh Gunjal | 2025-07-24 16:09 | OK | 2025-07-28 10:02 | Brajesh Upadhyay | work has been done | 74.759 | 20.4461 | Inspected | RFI Approved | 21 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/855 | Checking Of Shuttering & Laying PCC For Drain | 135050 | 135130 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-11 19:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-12 15:30 | Rushikesh Gunjal | 2025-07-12 11:18 | Check and found OK | 2025-07-14 09:25 | Brajesh Upadhyay | work has been done | 74.7589 | 20.4456 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/856 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135024 | 135040 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-11 19:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-12 16:00 | Rushikesh Gunjal | 2025-07-12 11:21 | OK | 2025-07-14 09:26 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4448 | Inspected | RFI Approved | 16 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/860 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135040 | 135080 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-12 17:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-13 14:30 | Rushikesh Gunjal | 2025-07-14 17:39 | Check and found OK | 2025-07-15 08:38 | Brajesh Upadhyay | work has been done | 74.7588 | 20.4454 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/859 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134780 | 134820 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-12 17:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-13 11:15 | Rushikesh Gunjal | 2025-07-14 17:36 | OK | 2025-07-15 08:48 | Brajesh Upadhyay | work has been done | 74.7588 | 20.4454 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/858 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall second Lift Of HPC | 120895 | 120895 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-12 17:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-13 14:10 | Rushikesh Gunjal | 2025-07-14 15:46 | Murum filled in the second lift at the bottom of the headwall Pipe joint not filling |  |  |  | 74.6976 | 20.3399 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/857 | Checking Of Laying DLC Top | 131660 | 132260 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-12 17:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-13 16:00 | Rushikesh Gunjal | 2025-07-14 17:21 | OK | 2025-07-15 08:45 | Brajesh Upadhyay | work has been done | 74.7527 | 20.4081 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/964 | Checking Of Laying PQC Top | 134530 | 135170 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-25 15:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-26 09:15 | Rushikesh Gunjal | 2025-08-05 12:07 | Check found OK | 2025-08-06 20:30 | Brajesh Upadhyay | work has been done | 74.7595 | 20.4478 | Inspected | RFI Approved | 640 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/966 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Final Lift | 140600 | 140640 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-25 15:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-26 11:15 | Rushikesh Gunjal | 2025-07-26 11:03 | OK | 2025-07-28 09:45 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4896 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/865 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120360 | 120380 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-14 19:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-15 11:30 | Rushikesh Gunjal | 2025-07-15 14:54 | Shuttering work not done |  |  |  | 74.6941 | 20.3364 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/867 | Checking Reinforcement, shuttering and pouring concrete for Wall First Lift Of Retaining Wall | 140640 | 140655 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-14 19:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-15 10:45 | Rushikesh Gunjal | 2025-07-15 12:08 | Check and found OK | 2025-07-16 08:53 | Brajesh Upadhyay | work has been done | 74.7814 | 20.4896 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/871 | Checking Of Shuttering & Concrete Pouring For Head Wall First lift Of HPC | 120400 | 120400 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-14 19:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-15 15:00 | Kishori Lal | 2025-07-15 14:33 | Not Ready. |  |  |  | 74.6943 | 20.3366 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/870 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall second Lift Of HPC | 120895 | 120895 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-14 19:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-15 14:30 | Kishori Lal | 2025-07-15 14:41 | Work not as per design and drawing. |  |  |  | 74.6975 | 20.3397 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/864 | Checking Reinforcement, shuttering and pouring concrete for Wall Final Lift Of Retaining Wall | 140720 | 140760 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-14 19:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-15 10:00 | Rushikesh Gunjal | 2025-07-15 12:01 | Shuttering work not done |  |  |  | 74.7817 | 20.491 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/868 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135080 | 135100 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-14 19:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-15 12:30 | Rushikesh Gunjal | 2025-07-15 18:29 | Check and found OK | 2025-07-16 08:54 | Brajesh Upadhyay | work has been done | 74.7589 | 20.4455 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/862 | Checking Shuttering & Laying Of PCC For Retaining Wall | 140600 | 140650 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-12 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-13 15:30 | Rushikesh Gunjal | 2025-07-14 17:55 | Check and found OK | 2025-07-15 08:43 | Brajesh Upadhyay | work has been done | 74.7815 | 20.4899 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/782 | Checking Of Laying PQC Top | 125360 | 126100 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-29 18:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-30 08:15 | Rushikesh Gunjal | 2025-07-10 16:19 | Check and found OK | 2025-07-15 08:59 | Brajesh Upadhyay | work has been done | 74.7203 | 20.3755 | Inspected | RFI Approved | 740 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/969 | Checking Of Layout Marking , Excavation & Laying Pcc For Retaining Wall | 140830 | 140870 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-25 17:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-26 17:00 | Rushikesh Gunjal | 2025-07-26 10:22 | Work not done |  |  |  | 74.7819 | 20.4914 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/968 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall First Lift | 140735 | 140770 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-25 17:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-26 16:15 | Rushikesh Gunjal | 2025-07-26 10:37 | Check found OK | 2025-07-28 09:36 | Brajesh Upadhyay | work has been done | 74.7817 | 20.4906 | Inspected | RFI Approved | 35 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/861 | Checking Reinforcement, shuttering and pouring concrete for Wall Final Lift Of Retaining Wall | 140680 | 140720 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-12 18:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-13 15:00 | Rushikesh Gunjal | 2025-07-15 12:00 | Shuttering Work not done |  |  |  | 74.7816 | 20.491 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/866 | Checking Reinforcement, shuttering and pouring concrete for Raft Of Retaining Wall | 140665 | 140705 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-14 19:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-15 10:45 | Rushikesh Gunjal | 2025-07-15 12:11 | Work not done |  |  |  | 74.7815 | 20.4897 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1788 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 123410 | 123781 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-29 15:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-30 14:00 | Rushikesh Gunjal | 2025-12-01 15:44 | Check fdd test and found a satisfactory result | 2025-12-02 09:10 | Brajesh Upadhyay | work has been done | 74.7091 | 20.366 | Inspected | RFI Approved | 371 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/875 | Checking Of Pipe Laying & Reinforcement, shuttering and pouring concrete for Second Lift Of HPC | 120895 | 120895 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-15 18:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-16 12:30 | Kishori Lal | 2025-08-13 14:59 | Wrong RFI. |  |  |  | 74.6975 | 20.3395 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/877 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135080 | 135100 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-15 19:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-16 10:45 | Rushikesh Gunjal | 2025-07-16 12:35 | Shuttering & R/f work not done |  |  |  | 74.7589 | 20.4456 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/878 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135040 | 135060 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-15 19:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-16 10:55 | Rushikesh Gunjal | 2025-07-16 12:39 | Check and found OK | 2025-07-16 15:33 | Brajesh Upadhyay | work has been done | 74.7588 | 20.4452 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/879 | Checking Of Layout Marking , Excavation Of Drain | 135130 | 135150 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-15 19:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-16 11:10 | Rushikesh Gunjal | 2025-07-16 12:33 | Excavation work is not completed |  |  |  | 74.7591 | 20.446 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/882 | Checking Of Layout Marking , Excavation For Retaining Wall | 140540 | 140600 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-15 19:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-16 14:45 | Rushikesh Gunjal | 2025-07-16 12:20 | Loyout marking is not done |  |  |  | 74.7813 | 20.4892 | Inspected | Inspected - Rejected - Work Not Done | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1784 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 129540 | 129590 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-29 14:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-30 11:00 | Rushikesh Gunjal | 2025-12-01 16:07 | Work done | 2025-12-02 09:10 | Brajesh Upadhyay | work has been done | 74.7474 | 20.3981 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/881 | Checking Reinforcement, shuttering and pouring concrete for Wall Final Lift Of Retaining Wall | 140720 | 140760 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-15 19:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-16 14:30 | Rushikesh Gunjal | 2025-07-16 12:05 | L/d not provides on top Surface of the reinforcement |  |  |  | 74.7816 | 20.4905 | Inspected | Inspected - Fail | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/880 | Checking Reinforcement, shuttering and pouring concrete for Raft Of Retaining Wall | 140665 | 140685 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-15 19:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-16 14:00 | Rushikesh Gunjal | 2025-07-16 12:17 | Work not done |  |  |  | 74.7815 | 20.49 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/876 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135100 | 135130 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-15 19:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-16 10:30 | Rushikesh Gunjal | 2025-07-16 12:36 | Raft Reinforcement work not completed |  |  |  | 74.7589 | 20.4457 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/869 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135040 | 135080 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-14 19:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-15 12:50 | Rushikesh Gunjal | 2025-07-15 18:27 | Check and found OK | 2025-07-16 08:54 | Brajesh Upadhyay | work has been done | 74.7589 | 20.4455 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1263 | Checking OF Reinforcement , Shuttering & Pouring Concrete For Retaining Wall Final lift | 132970 | 132981 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-14 09:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 12:30 | Kishori Lal | 2025-09-14 15:16 | Work done. | 2025-09-14 18:54 | Brajesh Upadhyay | work has been done | 74.7582 | 20.4268 | Inspected | RFI Approved | 11 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1252 | Checking Of Level & FDD Test & Filling Of Earthen Shoulder | 125200 | 125900 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-14 09:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 13:00 | Saurabh SE | 2025-09-14 15:39 | Work done | 2025-09-14 18:56 | Brajesh Upadhyay | work has been done | 74.7215 | 20.3762 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1254 | Checking Of Laying DLC Top | 140840 | 141650 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-14 09:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 13:30 | Saurabh SE | 2025-09-14 14:51 | Work done | 2025-09-14 18:57 | Brajesh Upadhyay | work has been done | 74.7828 | 20.4956 | Inspected | RFI Approved | 810 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1258 | Checking Of Laying DLC Top | 137280 | 138150 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-14 09:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 15:20 | Saurabh SE | 2025-09-14 15:02 | Work done | 2025-09-14 18:59 | Brajesh Upadhyay | work has been done | 74.7672 | 20.4659 | Inspected | RFI Approved | 870 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1261 | Checking Of Level & FDD test for GSB Top Layer | 119750 | 120400 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-14 09:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 16:00 | Saurabh SE | 2025-09-14 17:23 | Work done | 2025-09-14 18:59 | Brajesh Upadhyay | work has been done | 74.6921 | 20.3344 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/883 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135042 | 135260 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 14:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 11:30 | Rushikesh Gunjal | 2025-07-17 12:32 | In the mention of Chainage work not done |  |  |  | 74.7588 | 20.4454 | Inspected | Inspected - Rejected - Work Not Done | 218 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1246 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119890 | 119910 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-13 18:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 13:30 | Kishori Lal | 2025-09-14 17:48 | Work done. | 2025-09-14 19:02 | Brajesh Upadhyay | work has been done | 74.6913 | 20.3333 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/886 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135150 | 135170 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 14:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 12:15 | Rushikesh Gunjal | 2025-07-17 12:22 | Work not done |  |  |  | 74.7591 | 20.446 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/887 | Checking Reinforcement, shuttering and pouring concrete for Wall Final Lift Of Retaining Wall | 132910 | 132930 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 14:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 14:00 | Rushikesh Gunjal | 2025-07-17 12:41 | Shuttering & r/f work is not done |  |  |  | 74.7583 | 20.4265 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/888 | Checking Reinforcement, shuttering and pouring concrete for Wall Final Lift Of Retaining Wall | 135930 | 135950 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 14:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 14:15 | Rushikesh Gunjal | 2025-07-17 12:19 | Wrong RFI No retaining wall at mention Chainage |  |  |  | 74.7591 | 20.446 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/885 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135300 | 135340 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 14:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 11:50 | Rushikesh Gunjal | 2025-07-17 12:28 | Wall & slab joint was not repaired well |  |  |  | 74.7596 | 20.4477 | Inspected | Inspected - Fail | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/889 | Checking Reinforcement, shuttering and pouring concrete for Wall First Lift Of Retaining Wall | 132950 | 132981 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 15:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 10:30 | Rushikesh Gunjal | 2025-07-17 12:42 | Work is already done without inspection |  |  |  | 74.7583 | 20.4265 | Inspected | Inspected - Fail | 31 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/789 | Checking Of Laying PQC Top | 126980 | 127800 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-29 18:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-30 17:30 | Rushikesh Gunjal | 2025-07-16 15:35 | Check and found OK | 2025-07-16 15:42 | Brajesh Upadhyay | work has been done | 74.7377 | 20.3907 | Inspected | RFI Approved | 820 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/790 | Checking Of Laying PQC Top | 127800 | 128460 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-29 18:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-30 22:30 | Rushikesh Gunjal | 2025-07-16 15:39 | Check and found OK | 2025-07-16 15:43 | Brajesh Upadhyay | work has been done | 74.7376 | 20.3907 | Inspected | RFI Approved | 660 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1247 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119910 | 119930 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-13 18:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 14:15 | Kishori Lal | 2025-09-14 17:46 | Work done. | 2025-09-14 19:03 | Brajesh Upadhyay | work has been done | 74.6914 | 20.3334 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1248 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119970 | 119990 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-13 18:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 14:45 | Kishori Lal | 2025-09-14 17:43 | Work done. | 2025-09-14 19:03 | Brajesh Upadhyay | work has been done | 74.6916 | 20.3338 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/892 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135242 | 135260 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 16:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 11:30 | Rushikesh Gunjal | 2025-07-17 17:47 | OK | 2025-07-18 09:07 | Brajesh Upadhyay | work has been done | 74.7594 | 20.447 | Inspected | RFI Approved | 18 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1249 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119770 | 119800 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-13 18:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 11:30 | Kishori Lal | 2025-09-14 17:52 | Work done. | 2025-09-14 19:04 | Brajesh Upadhyay | work has been done | 74.6906 | 20.3325 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/894 | Checking shuttering and pouring concrete for Final Lift Of HPC | 120895 | 120895 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 14:30 | Rushikesh Gunjal | 2025-07-17 17:01 | LHS head wall concreting not done Shuttering work is not properly |  |  |  | 74.6976 | 20.3398 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/893 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Final Lift With Top Haunch & Top Slab Of Box Culvert | 133216 | 133216 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 18:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 15:00 | Rushikesh Gunjal | 2025-07-17 17:35 | Reinforcement work is not completed 1st lift RFI was not approved |  |  |  | 74.7583 | 20.4289 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/895 | Checking Reinforcement, shuttering and pouring concrete for Wall Final Lift Of Retaining Wall | 140720 | 140760 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 18:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 10:30 | Rushikesh Gunjal | 2025-07-17 11:59 | Shuttering work is not done |  |  |  | 74.7816 | 20.4906 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/896 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135060 | 135080 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 19:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 14:30 | Rushikesh Gunjal | 2025-07-17 17:43 | Shuttering & reinforcement work is not done |  |  |  | 74.7588 | 20.4453 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/898 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135100 | 135120 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 19:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 16:00 | Rushikesh Gunjal | 2025-07-17 17:45 | Shuttering work not done |  |  |  | 74.759 | 20.4456 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/897 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135080 | 135100 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 19:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 15:00 | Rushikesh Gunjal | 2025-07-17 17:46 | Check found OK | 2025-07-18 08:53 | Brajesh Upadhyay | work has been done | 74.759 | 20.4456 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/986 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall First Lift | 140770 | 140790 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-28 17:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-29 15:30 | Rushikesh Gunjal | 2025-07-29 16:11 | Check found SATISFACTORY | 2025-07-29 18:27 | Brajesh Upadhyay | work has been done | 74.7818 | 20.4908 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1206 | Checking Of Level & FDD test for GSB Top Layer | 141280 | 141690 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 16:30 | Saurabh SE | 2025-09-14 14:49 | Work done | 2025-09-14 19:23 | Brajesh Upadhyay | work has been done | 74.7829 | 20.4958 | Inspected | RFI Approved | 410 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1204 | Checking Of Level & FDD test for GSB Top Layer | 140260 | 140840 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 14:30 | Saurabh SE | 2025-09-14 14:39 | Work done | 2025-09-14 19:24 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4893 | Inspected | RFI Approved | 580 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/967 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall Raft | 140780 | 140800 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-25 17:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-26 16:00 | Rushikesh Gunjal | 2025-07-26 10:30 | Check and found OK | 2025-07-28 09:35 | Brajesh Upadhyay | work has been done | 74.7817 | 20.4908 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/965 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Final Lift | 140680 | 140720 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-25 15:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-26 11:00 | Rushikesh Gunjal | 2025-07-26 10:59 | Top Surface not in level |  |  |  | 74.7814 | 20.4899 | Inspected | Inspected - Fail | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1205 | Checking Of Level & FDD test for GSB Top Layer | 140840 | 141280 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 15:30 | Saurabh SE | 2025-09-14 14:44 | Work done | 2025-09-14 19:27 | Brajesh Upadhyay | work has been done | 74.7815 | 20.4899 | Inspected | RFI Approved | 440 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/884 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135260 | 135300 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-16 14:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-17 11:35 | Rushikesh Gunjal | 2025-07-17 12:24 | Ok | 2025-07-18 09:06 | Brajesh Upadhyay | work has been done | 74.7595 | 20.4473 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/765 | Checking Of Level & FDD test for GSB Top Layer | 128720 | 129280 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-06-26 18:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-06-27 20:00 | Rushikesh Gunjal | 2025-07-09 16:31 | Check and found OK | 2025-07-18 09:21 | Brajesh Upadhyay | work has been done | 74.7414 | 20.3934 | Inspected | RFI Approved | 560 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/995 | Checking Of Shuttering & Pouring Concrete Head Wall First Lift & Below Pipe PCC | 120400 | 120400 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-29 17:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-30 15:30 | Rushikesh Gunjal | 2025-07-30 16:29 | First lift not in alignment Honeycombing found |  |  |  | 74.6943 | 20.3366 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/996 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 120895 | 120895 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-29 17:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-30 15:45 | Rushikesh Gunjal | 2025-07-30 16:07 | LHS head wall not in alignment Pipe joint not filling |  |  |  | 74.6975 | 20.3399 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/997 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135140 | 135150 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-29 17:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-30 14:45 | Rushikesh Gunjal | 2025-07-30 12:17 | Check found SATISFACTORY | 2025-07-31 07:45 | Brajesh Upadhyay | work has been done | 74.7591 | 20.4461 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/980 | Checking Of Level & FDD Test & Filling Of Earthen Shoulder | 121600 | 122200 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-26 18:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-27 10:00 | Rushikesh Gunjal | 2025-07-28 15:42 | Check and found OK | 2025-07-28 21:00 | Brajesh Upadhyay | work has been done | 74.6991 | 20.3464 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/970 | Checking Of Level & FDD Test & Filling Of Earthen Shoulder | 121020 | 121600 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-25 17:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-26 10:00 | Rushikesh Gunjal | 2025-07-28 15:47 | Check and found satisfactory result | 2025-07-28 21:01 | Brajesh Upadhyay | work has been done | 74.6991 | 20.3465 | Inspected | RFI Approved | 580 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/903 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Final Lift With Top Haunch & Top Slab Of Box Culvert | 133216 | 133216 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-19 15:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-20 11:30 | Rushikesh Gunjal | 2025-07-21 16:28 | OK | 2025-07-22 12:08 | Brajesh Upadhyay | work has been done | 74.7582 | 20.4289 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/904 | Checking Reinforcement, shuttering and pouring concrete for Wall Final Lift Of Retaining Wall | 140720 | 140760 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-19 16:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-20 14:00 | Rushikesh Gunjal | 2025-07-21 18:26 | OK | 2025-07-22 12:09 | Brajesh Upadhyay | work has been done | 74.7815 | 20.4901 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/906 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135100 | 135120 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-19 17:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-20 15:00 | Rushikesh Gunjal | 2025-07-24 12:14 | Ok | 2025-07-28 10:07 | Brajesh Upadhyay | work has been done | 74.7591 | 20.446 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/910 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135300 | 135340 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-19 17:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-20 14:40 | Rushikesh Gunjal | 2025-07-21 17:55 | OK | 2025-07-22 12:04 | Brajesh Upadhyay | work has been done | 74.7595 | 20.4474 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/908 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall First Lift | 132940 | 132981 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-19 17:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-20 14:00 | Rushikesh Gunjal | 2025-07-21 16:16 | OK | 2025-07-22 12:10 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4265 | Inspected | RFI Approved | 41 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/909 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Final Lift | 132910 | 132940 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-19 17:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-20 15:30 | Rushikesh Gunjal | 2025-07-21 16:21 | OK | 2025-07-22 12:11 | Brajesh Upadhyay | work has been done | 74.7582 | 20.4264 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/905 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 120895 | 120895 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-19 17:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-20 11:00 | Rushikesh Gunjal | 2025-07-21 12:40 | Check and found honeycombing in the final lift & wall not in alignment |  |  |  | 74.6975 | 20.3398 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1033 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Final Lift | 140810 | 140840 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-18 16:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-19 14:30 | Kishori Lal | 2025-08-20 14:46 | Work already done without checking. |  |  |  | 74.7818 | 20.4911 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/917 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134710 | 134722 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-20 19:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-21 10:30 | Rushikesh Gunjal | 2025-07-21 17:25 | Shuttering & reinforcement Work not done |  |  |  | 74.758 | 20.4423 | Inspected | Inspected - Rejected - Work Not Done | 12 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/916 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134720 | 134730 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-20 19:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-21 10:15 | Rushikesh Gunjal | 2025-07-21 17:30 | The pipe culvert is in the mentioned Chainage |  |  |  | 74.758 | 20.4424 | Inspected | Inspected - Fail | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/915 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134722 | 134730 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-20 19:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-21 10:00 | Rushikesh Gunjal | 2025-07-21 17:36 | The pipe culvert is in the mentioned Chainage |  |  |  | 74.7586 | 20.4448 | Inspected | Inspected - Fail | 8 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/918 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135160 | 135170 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-20 19:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-21 10:50 | Rushikesh Gunjal | 2025-07-21 17:50 | Work not done |  |  |  | 74.759 | 20.4462 | Inspected | Inspected - Rejected - Work Not Done | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/922 | Checking Of Layout Marking & Excavation For Return Wall A1,A2 OF Box Culvert | 133216 | 133216 | LHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-20 19:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-21 16:00 | Rushikesh Gunjal | 2025-07-21 16:26 | Layout marking not done |  |  |  | 74.7582 | 20.4289 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/924 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135100 | 135110 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-20 19:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-21 11:40 | Rushikesh Gunjal | 2025-07-21 17:45 | Work not done |  |  |  | 74.759 | 20.4457 | Inspected | Inspected - Rejected - Work Not Done | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/919 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135130 | 135160 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-20 19:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-21 11:00 | Rushikesh Gunjal | 2025-07-21 17:47 | Work not done |  |  |  | 74.759 | 20.4457 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/920 | Checking Reinforcement, shuttering and pouring concrete for Wall Final Lift Of Retaining Wall | 140760 | 140800 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-20 19:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-21 15:00 | Rushikesh Gunjal | 2025-07-21 18:35 | OK | 2025-07-22 11:53 | Brajesh Upadhyay | work has been done | 74.7816 | 20.4906 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/925 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135000 | 135020 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-20 19:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-21 12:10 | Rushikesh Gunjal | 2025-07-21 17:34 | OK | 2025-07-22 11:55 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4448 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/921 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Raft | 140665 | 140695 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-20 19:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-21 15:15 | Rushikesh Gunjal | 2025-07-21 18:32 | Check and found OK | 2025-07-22 11:54 | Brajesh Upadhyay | work has been done | 74.7815 | 20.4902 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/926 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135100 | 135120 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-20 19:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-21 12:30 | Rushikesh Gunjal | 2025-07-21 17:44 | Ok | 2025-07-22 11:56 | Brajesh Upadhyay | work has been done | 74.759 | 20.4457 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/971 | Checking Of Laying PQC Top | 135170 | 135680 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-26 16:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-27 09:30 | Rushikesh Gunjal | 2025-08-08 12:13 | Check found OK | 2025-08-12 07:56 | Brajesh Upadhyay | work has been done | 74.7608 | 20.4508 | Inspected | RFI Approved | 510 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/973 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Raft | 120340 | 120350 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-26 17:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-27 15:15 | Rushikesh Gunjal | 2025-07-28 17:18 | Wrong description No retaining wall at mention Chainage |  |  |  | 74.7591 | 20.4461 | Inspected | Inspected - Rejected - Work Not Done | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/974 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 120280 | 120340 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-26 17:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-27 16:15 | Rushikesh Gunjal | 2025-07-29 15:07 | PCC not in alignment |  |  |  | 74.6938 | 20.3362 | Inspected | Inspected - Fail | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/976 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135100 | 135110 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-26 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-27 15:00 | Rushikesh Gunjal | 2025-07-29 15:46 | OK | 2025-07-29 18:34 | Brajesh Upadhyay | work has been done | 74.759 | 20.4457 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/977 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135140 | 135150 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-26 18:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-27 15:20 | Rushikesh Gunjal | 2025-07-29 15:47 | OK | 2025-07-29 18:34 | Brajesh Upadhyay | work has been done | 74.7591 | 20.4459 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/923 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135235 | 135242 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-20 19:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-21 11:30 | Rushikesh Gunjal | 2025-07-21 17:52 | Wrong Chainage mention Drain start from 135240 |  |  |  | 74.7594 | 20.4468 | Inspected | Inspected - Fail | 7 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/927 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135140 | 135170 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-21 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-22 11:30 | Rushikesh Gunjal | 2025-07-22 11:59 | Shuttering & reinforcement work not completed |  |  |  | 74.7591 | 20.446 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/931 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134710 | 134720 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-21 18:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-22 10:45 | Rushikesh Gunjal | 2025-07-23 16:27 | Repeated Chainage RFI No.933 |  |  |  | 74.7579 | 20.4423 | Inspected | Inspected - Rejected - Work Not Done | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/929 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135100 | 135120 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-21 18:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-22 11:35 | Rushikesh Gunjal | 2025-07-23 16:38 | Work not done |  |  |  | 74.759 | 20.4459 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/930 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Final Lift | 140800 | 140834 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-21 18:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-22 15:00 | Rushikesh Gunjal | 2025-07-23 17:30 | OK | 2025-07-24 07:07 | Brajesh Upadhyay | work has been done | 74.7818 | 20.4912 | Inspected | RFI Approved | 34 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/928 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135080 | 135100 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-21 18:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-22 18:20 | Rushikesh Gunjal | 2025-07-23 16:31 | Oky | 2025-07-24 07:09 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4451 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/934 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135100 | 135110 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-21 18:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-22 11:35 | Rushikesh Gunjal | 2025-07-23 16:34 | OK | 2025-07-24 07:08 | Brajesh Upadhyay | work has been done | 74.759 | 20.4459 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/935 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135235 | 135242 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-21 18:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-22 11:55 | Rushikesh Gunjal | 2025-07-24 16:19 | There is a pipe culvert at this Chainage Wrong Chainage |  |  |  | 74.7592 | 20.4468 | Inspected | Inspected - Rejected - Work Not Done | 7 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/937 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Raft | 140695 | 140725 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-21 18:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-22 14:50 | Rushikesh Gunjal | 2025-07-23 17:21 | Work done without reinforcement Checking |  |  |  | 74.7815 | 20.4902 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/936 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Final Lift | 140800 | 140850 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-21 18:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-22 14:30 | Rushikesh Gunjal | 2025-07-23 17:29 | Repeated RFI RFI no. 930 |  |  |  | 74.7818 | 20.4912 | Inspected | Inspected - Rejected - Work Not Done | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/907 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135060 | 135080 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-19 17:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-20 15:15 | Rushikesh Gunjal | 2025-07-21 17:38 | OK | 2025-07-22 12:10 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4451 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/940 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135160 | 135170 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-22 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-23 11:30 | Rushikesh Gunjal | 2025-07-23 16:41 | Work not done |  |  |  | 74.759 | 20.4459 | Inspected | Inspected - Rejected - Work Not Done | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/941 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135140 | 135170 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-22 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-23 10:30 | Rushikesh Gunjal | 2025-07-23 16:42 | Work not done |  |  |  | 74.759 | 20.4459 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/943 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall RAft | 140600 | 140640 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-22 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-23 15:15 | Rushikesh Gunjal | 2025-07-23 17:06 | Work not done in mention Chainage |  |  |  | 74.7813 | 20.4892 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/944 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall First Lift | 140665 | 140700 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-22 18:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-23 15:30 | Rushikesh Gunjal | 2025-07-23 17:10 | Concrete poure without inspection |  |  |  | 74.7815 | 20.4898 | Inspected | Inspected - Rejected - Work Not Done | 35 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/946 | Checking Reinforcement, shuttering and pouring concrete for Drain Excavation & PCC | 135120 | 135130 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-22 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-23 16:00 | Rushikesh Gunjal | 2025-07-24 12:11 | Check found OK | 2025-07-24 21:38 | Brajesh Upadhyay | work has been done | 74.7591 | 20.446 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/945 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall PCC | 140725 | 140780 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-22 18:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-23 15:10 | Rushikesh Gunjal | 2025-07-23 17:18 | Contractor representative not available for Checking Cracks found on laid PCC |  |  |  | 74.7817 | 20.4906 | Inspected | Inspected - Rejected - Work Not Done | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/999 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135120 | 135130 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-29 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-30 15:15 | Rushikesh Gunjal | 2025-07-31 11:53 | Check and OK | 2025-07-31 21:20 | Brajesh Upadhyay | work has been done | 74.759 | 20.4458 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/983 | Checking Of Level & FDD Test & Filling Of Earthen Shoulder | 122200 | 122800 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-27 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-28 10:00 | Rushikesh Gunjal | 2025-07-28 15:31 | Check level and FDD and found satisfactory Result | 2025-07-28 20:57 | Brajesh Upadhyay | work has been done | 74.7028 | 20.3535 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/982 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135120 | 135130 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-27 17:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-28 14:30 | Rushikesh Gunjal | 2025-07-28 16:12 | Check found OK | 2025-07-28 20:57 | Brajesh Upadhyay | work has been done | 74.6939 | 20.3362 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/994 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120340 | 120350 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-29 17:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-30 14:30 | Rushikesh Gunjal | 2025-07-30 16:21 | Raft Slope does not maintain Not in alignment |  |  |  | 74.6939 | 20.3363 | Inspected | Inspected - Fail | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/932 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134727 | 134730 | BHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-21 18:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-22 11:10 | Rushikesh Gunjal | 2025-07-23 16:28 | Mention side BHS |  |  |  | 74.7579 | 20.4422 | Inspected | Inspected - Rejected - Work Not Done | 3 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/942 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall Excavation & PCC | 140540 | 140585 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-22 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-23 15:00 | Rushikesh Gunjal | 2025-07-23 17:01 | Work not done up to the Chainage |  |  |  | 74.7812 | 20.4891 | Inspected | Inspected - Rejected - Work Not Done | 45 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/948 | Checking Of Laying PQC Top | 133230 | 133840 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-23 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-24 08:00 | Rushikesh Gunjal | 2025-07-30 17:20 | Check found OK | 2025-08-01 21:25 | Brajesh Upadhyay | work has been done | 74.7585 | 20.4302 | Inspected | RFI Approved | 610 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/949 | Checking Reinforcement, shuttering and pouring concrete for Retaing Wall Raft | 140725 | 140780 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-23 18:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-24 15:30 | Rushikesh Gunjal | 2025-07-24 16:41 | Check found OK | 2025-07-24 21:33 | Brajesh Upadhyay | work has been done | 74.7817 | 20.4907 | Inspected | RFI Approved | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/950 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135100 | 135120 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-23 18:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-24 15:45 | Rushikesh Gunjal | 2025-07-24 12:01 | Work not done |  |  |  | 74.7589 | 20.4456 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/951 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135140 | 135170 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-23 18:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-24 15:45 | Rushikesh Gunjal | 2025-07-24 12:05 | Work not done |  |  |  | 74.7591 | 20.446 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/952 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135120 | 135130 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-23 18:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-24 16:00 | Rushikesh Gunjal | 2025-07-24 12:12 | Work not done |  |  |  | 74.7591 | 20.446 | Inspected | Inspected - Rejected - Work Not Done | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/955 | Checking Of Layout Marking , Excavation & Laying Pcc For Drain | 135210 | 135240 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-23 18:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-24 15:10 | Rushikesh Gunjal | 2025-07-24 11:56 | Check found OK | 2025-07-24 21:25 | Brajesh Upadhyay | work has been done | 74.7593 | 20.4466 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/953 | Checking Layout Marking & Laying PCC for Retaining Wall | 140540 | 140585 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-23 18:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-24 16:30 | Rushikesh Gunjal | 2025-07-24 16:34 | Work not done |  |  |  | 74.7812 | 20.4892 | Inspected | Inspected - Rejected - Work Not Done | 45 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/939 | Checking Of Laying PQC Top | 132850 | 133210 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-22 17:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-23 10:00 | Rushikesh Gunjal | 2025-07-23 16:06 | Check found OK | 2025-07-24 06:56 | Brajesh Upadhyay | work has been done | 74.7548 | 20.4143 | Inspected | RFI Approved | 360 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/947 | Checking Of Laying DLC Top | 137870 | 138480 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-23 18:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-24 16:30 | Rushikesh Gunjal | 2025-07-24 12:40 | Check and ok | 2025-07-24 21:32 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4323 | Inspected | RFI Approved | 610 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/990 | Checking Of Laying PQC Top | 137050 | 137860 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-29 16:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-30 14:30 | Rushikesh Gunjal | 2025-08-13 16:13 | Check found OK | 2025-08-14 10:00 | Brajesh Upadhyay | work has been done | 74.7663 | 20.464 | Inspected | RFI Approved | 810 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/954 | Checking Layout Marking & Laying PCC For Drain | 134980 | 135000 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-23 18:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-24 14:30 | Rushikesh Gunjal | 2025-07-24 12:17 | Pcc & excavation layout not done |  |  |  | 74.7586 | 20.4446 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2008 | Checking Of Reinforcement, shuttering and pouring concrete for Drain Raft | 134723 | 134750 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-30 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-31 13:00 | Rushikesh Gunjal | 2025-12-31 15:26 | Work already done | 2026-01-01 14:06 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4423 | Inspected | RFI Approved | 27 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/975 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120340 | 120350 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-26 18:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-27 16:00 | Rushikesh Gunjal | 2025-07-29 15:09 | Raft Slope does not maintain |  |  |  | 74.6938 | 20.3362 | Inspected | Inspected - Fail | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/978 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135150 | 135170 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-26 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-27 15:30 | Rushikesh Gunjal | 2025-07-29 12:17 | OK | 2025-07-29 18:35 | Brajesh Upadhyay | work has been done | 74.7591 | 20.446 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/985 | Checking Of Laying PQC Top | 136330 | 137050 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-28 17:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-29 14:00 | Rushikesh Gunjal | 2025-08-12 16:01 | Check and found Satisfactory | 2025-08-14 10:04 | Brajesh Upadhyay | work has been done | 74.7657 | 20.4609 | Inspected | RFI Approved | 720 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/957 | Checking Reinforcement, shuttering and pouring concrete for Drain raft | 135210 | 135240 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-24 17:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-25 14:30 | Rushikesh Gunjal | 2025-07-26 11:19 | Reinforcement and shuttering work not completed |  |  |  | 74.7592 | 20.4466 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/958 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall First Lift | 140695 | 140735 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-24 17:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-25 15:40 | Rushikesh Gunjal | 2025-07-26 10:45 | Checked and found OK | 2025-07-28 09:51 | Brajesh Upadhyay | work has been done | 74.7817 | 20.4906 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/959 | Checking Shuttering & Laying PCC for Retailing Wall | 140780 | 140830 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-24 17:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-25 16:15 | Rushikesh Gunjal | 2025-07-25 11:44 | Check and found OK | 2025-07-25 20:16 | Brajesh Upadhyay | work has been done | 74.7818 | 20.4909 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/962 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall First Lift | 140665 | 140695 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-24 17:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-25 16:10 | Rushikesh Gunjal | 2025-07-25 11:49 | OK | 2025-07-25 20:07 | Brajesh Upadhyay | work has been done | 74.7815 | 20.4901 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/992 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Raft | 140610 | 140650 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-29 17:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-30 11:30 | Rushikesh Gunjal | 2025-07-30 17:50 | OK | 2025-07-31 07:44 | Brajesh Upadhyay | work has been done | 74.7814 | 20.4894 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/987 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall Raft | 140800 | 140840 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-28 17:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-29 15:45 | Rushikesh Gunjal | 2025-07-29 11:47 | Check found OK | 2025-07-29 18:28 | Brajesh Upadhyay | work has been done | 74.7818 | 20.491 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/979 | Checking Of Layout Marking & Excavation For Drain | 120200 | 120280 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-26 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-27 14:30 | Rushikesh Gunjal | 2025-07-29 15:14 | Check found OK | 2025-07-29 18:35 | Brajesh Upadhyay | work has been done | 74.6933 | 20.3357 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/993 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall First Lift | 140790 | 140800 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-29 17:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-30 12:30 | Rushikesh Gunjal | 2025-07-30 11:36 | Check and found OK | 2025-07-31 07:45 | Brajesh Upadhyay | work has been done | 74.7818 | 20.4909 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/998 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135150 | 135170 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-29 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-30 13:30 | Rushikesh Gunjal | 2025-07-30 12:14 | Check found OK | 2025-07-31 07:37 | Brajesh Upadhyay | work has been done | 74.7592 | 20.446 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1044 | Checking of Reinforcement, Shuttering & Pouring Concrete For HPC Encasing | 138728 | 138728 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-19 18:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-20 16:25 | Kishori Lal | 2025-08-20 15:26 | Wrong Chainage. |  |  |  | 74.7728 | 20.4764 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1229 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Raft | 119890 | 119910 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-06 16:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-07 14:30 | Kishori Lal | 2025-09-07 17:08 | Not Ready. |  |  |  | 74.6911 | 20.3331 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/972 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120360 | 120380 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-26 16:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-27 11:00 | Rushikesh Gunjal | 2025-07-30 16:24 | Clear Cover is not maintain Wall is not in alignment |  |  |  | 74.6939 | 20.3363 | Inspected | Inspected - Fail | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1001 | Checking Of Layout Marking , Excavation & Laying Pcc For Retaining Wall | 140830 | 140840 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-30 17:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-31 14:30 | Rushikesh Gunjal | 2025-07-31 11:17 | Check found OK | 2025-07-31 21:21 | Brajesh Upadhyay | work has been done | 74.7819 | 20.4913 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1002 | Checking Of Layout Marking , Excavation & Laying Pcc For Retaining Wall | 140550 | 140585 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-30 17:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-31 14:15 | Rushikesh Gunjal | 2025-07-31 16:51 | OK | 2025-07-31 21:21 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4891 | Inspected | RFI Approved | 35 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/991 | Checking Reinforcement, shuttering and pouring concrete for Drain raft | 135210 | 135240 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-29 17:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-30 10:30 | Rushikesh Gunjal | 2025-07-30 12:20 | Check and OK | 2025-07-31 07:43 | Brajesh Upadhyay | work has been done | 74.7593 | 20.4466 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/989 | Checking Of Level & FDD Test & Filling Of Earthen Shoulder | 123880 | 124500 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-29 16:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-30 16:15 | Rushikesh Gunjal | 2025-07-30 16:49 | Check level and FDD and found satisfactory result | 2025-07-31 07:48 | Brajesh Upadhyay | work has been done | 74.7097 | 20.3667 | Inspected | RFI Approved | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1003 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall First Lift | 140610 | 140650 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-30 17:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-31 14:45 | Rushikesh Gunjal | 2025-07-31 11:27 | Check found satisfactory | 2025-07-31 21:22 | Brajesh Upadhyay | work has been done | 74.7815 | 20.4896 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2009 | Checking Of Laying PQC Top | 134460 | 134650 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-02 08:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-02 14:00 | Rushikesh Gunjal | 2026-01-03 11:27 | Work done | 2026-01-04 11:35 | Brajesh Upadhyay | work has been done | 74.758 | 20.44 | Inspected | RFI Approved | 190 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2054 | Checking Of Providing & Fixing of Metal Beam Crash Barrier | 140350 | 140570 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-23 17:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-24 14:00 | Rushikesh Gunjal | 2026-01-24 14:56 | Work not done |  |  |  | 74.7794 | 20.4879 | Inspected | Inspected - Rejected - Work Not Done | 220 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2032 | Checking of Layout Marking , Excavation & Laying PCC Of Terminal Slab A1,A2 of BC | 133216 | 133216 | LHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-12 09:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-12 16:00 | Rushikesh Gunjal | 2026-01-12 16:34 | Work done | 2026-01-12 17:12 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4288 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1004 | Checking Of Level & FDD Test & Filling Of Earthen Shoulder | 124500 | 125200 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-30 17:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-31 10:30 | Rushikesh Gunjal | 2025-07-31 14:36 | Check found OK | 2025-07-31 21:22 | Brajesh Upadhyay | work has been done | 74.7135 | 20.371 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1008 | Checking Of Utility Pipe Laying | 124880 | 124880 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-31 17:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-01 14:00 | Rushikesh Gunjal | 2025-08-01 15:53 | Check and found No GSB has been put down the pipe. Pipe joint not filling |  |  |  | 74.7138 | 20.3711 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1009 | Checking Of Utility Pipe Laying | 134460 | 134460 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-31 17:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-01 16:30 | Rushikesh Gunjal | 2025-08-01 16:59 | Check and found No GSB has been put below the pipe. Pipe joint not filled. |  |  |  | 74.758 | 20.44 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1227 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120100 | 120110 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-06 16:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-07 11:30 | Kishori Lal | 2025-09-07 16:58 | Formwork checked and found Satisfactory and allowing for concrete pouring. | 2025-09-07 19:09 | Brajesh Upadhyay | work has been done | 74.6922 | 20.3345 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1216 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall Final lift | 140650 | 140665 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-03 18:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-04 10:00 | Rushikesh Gunjal | 2025-09-04 18:20 | Check found OK | 2025-09-04 20:37 | Brajesh Upadhyay | work has been done | 74.7815 | 20.4897 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1010 | Checking Of Level & FDD Test & Filling Of Earthen Shoulder | 125200 | 125900 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-31 17:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-01 10:30 | Rushikesh Gunjal | 2025-08-01 15:36 | Check FDD and found satisfactory The material used for the earthen shoulder is not suitable. i.e. their CBR value is less than 30 |  |  |  | 74.7189 | 20.3745 | Inspected | Inspected - Fail | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1167 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Slab | 120150 | 120170 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-01 18:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-02 13:30 | Kishori Lal | 2025-09-02 14:02 | Not Ready. |  |  |  | 74.6927 | 20.3351 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1164 | Checking Of Level & FDD Test For Earthen Shoulder | 135400 | 136000 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-01 18:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-02 11:45 | Rushikesh Gunjal | 2025-09-03 12:22 | Check found OK | 2025-09-04 20:48 | Brajesh Upadhyay | work has been done | 74.7626 | 20.4548 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1122 | Checking Of Level & FDD Test For GSB Top | 135550 | 136400 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-28 17:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-29 15:00 | Rushikesh Gunjal | 2025-09-02 12:56 | Check found Satisfactory level & result | 2025-09-04 20:57 | Brajesh Upadhyay | work has been done | 74.7605 | 20.4505 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1123 | Checking Of Laying DLC Top | 134650 | 135550 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-28 17:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-29 17:30 | Rushikesh Gunjal | 2025-09-02 12:52 | Check found OK | 2025-09-04 20:57 | Brajesh Upadhyay | work has been done | 74.7605 | 20.4505 | Inspected | RFI Approved | 900 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1232 | Checking Of Layout Marking ,Excavation & Laying PCC For Toe Wall | 119020 | 119060 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-06 16:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-07 10:10 | Kishori Lal | 2025-09-07 17:23 | Work done. | 2025-09-07 19:10 | Brajesh Upadhyay | work has been done | 74.6894 | 20.3269 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1225 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 120250 | 120270 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-06 16:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-07 10:35 | Kishori Lal | 2025-09-07 16:44 | Work done. | 2025-09-07 19:12 | Brajesh Upadhyay | work has been done | 74.6931 | 20.336 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1046 | Checking Of Utility Pipe Laying | 138360 | 138360 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-20 16:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-21 10:30 | Saurabh SE | 2025-08-21 12:37 | No found here utility pipe |  |  |  | 74.7707 | 20.4727 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1047 | Checking Of Utility Pipe Laying | 138540 | 138540 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-20 16:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-21 12:30 | Saurabh SE | 2025-08-21 12:31 | No found here utility pipe |  |  |  | 74.7715 | 20.4742 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1226 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 120270 | 120290 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-06 16:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-07 14:00 | Kishori Lal | 2025-09-07 16:46 | Work done. | 2025-09-07 19:13 | Brajesh Upadhyay | work has been done | 74.6931 | 20.336 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1018 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Final Lift | 140735 | 140770 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-11 16:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-12 11:31 | Rushikesh Gunjal | 2025-08-12 17:22 | OK | 2025-08-12 20:58 | Brajesh Upadhyay | work has been done | 74.7817 | 20.4903 | Inspected | RFI Approved | 35 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1051 | Checking Of Layout Marking & Excavation & Laying PCC Of Drain | 120260 | 120280 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-20 16:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-21 11:30 | Kishori Lal | 2025-08-21 16:24 | Work done. | 2025-08-21 17:48 | Brajesh Upadhyay | work has been done | 74.6934 | 20.3356 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1012 | Checking Reinforcement, shuttering and pouring concrete for Wall First Lift Of Retaining Wall | 140830 | 140840 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-02 19:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-03 15:00 | Rushikesh Gunjal | 2025-08-04 17:19 | Check found OK | 2025-08-04 21:44 | Brajesh Upadhyay | work has been done | 74.7819 | 20.4912 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1015 | Checking Of Shuttering & Pouring Concrete For HPC Encasing | 120400 | 120400 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-05 19:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-06 15:00 | Rushikesh Gunjal | 2025-08-07 14:42 | OK | 2025-08-07 20:01 | Brajesh Upadhyay | work has been done | 74.694 | 20.3367 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1013 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 120895 | 120895 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-05 15:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-06 15:15 | Rushikesh Gunjal | 2025-08-07 14:36 | Ok | 2025-08-07 20:03 | Brajesh Upadhyay | work has been done | 74.6932 | 20.3323 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1020 | Checking of Layout , Excavation & Laying PCC For Toe Wall | 140840 | 140890 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-12 17:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-13 11:45 | Rushikesh Gunjal | 2025-08-13 16:44 | OK | 2025-08-14 09:52 | Brajesh Upadhyay | work has been done | 74.7819 | 20.4914 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1014 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Final Lift | 140665 | 140715 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-05 19:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-06 16:00 | Rushikesh Gunjal | 2025-08-12 17:23 | OK | 2025-08-12 21:11 | Brajesh Upadhyay | work has been done | 74.7817 | 20.4903 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1041 | Checking Of Utility Pipe Laying | 139270 | 139270 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-19 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-20 11:07 | Saurabh SE | 2025-08-20 14:56 | Work done | 2025-08-20 17:24 | Brajesh Upadhyay | work has been done | 74.7745 | 20.4801 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1042 | Checking Of Utility Pipe Laying | 139290 | 139290 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-19 18:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-20 11:11 | Saurabh SE | 2025-08-20 14:53 | Work done | 2025-08-20 17:25 | Brajesh Upadhyay | work has been done | 74.7747 | 20.4802 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1043 | Checking Of Utility Pipe Laying | 139310 | 139310 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-19 18:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-20 11:18 | Saurabh SE | 2025-08-20 14:51 | Work done | 2025-08-20 17:25 | Brajesh Upadhyay | work has been done | 74.7748 | 20.4804 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1017 | Checking Of Utility Pipe Laying | 137880 | 137880 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-07 08:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-07 12:00 | Rushikesh Gunjal | 2025-08-12 16:56 | Ok | 2025-08-12 21:08 | Brajesh Upadhyay | work has been done | 74.7676 | 20.4661 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1016 | Checking Of Utility Pipe Laying | 137560 | 137560 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-07 08:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-07 23:54 | Rushikesh Gunjal | 2025-08-08 12:02 | Check and found filter media not laid below the pipe |  |  |  | 74.7677 | 20.4665 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1023 | Checking of Level & FDD Test & Filling of Earthen Shoulder | 126600 | 127300 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-13 17:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-14 12:38 | Rushikesh Gunjal | 2025-08-14 12:24 | Check found Satisfactory result | 2025-08-14 17:08 | Brajesh Upadhyay | work has been done | 74.7291 | 20.3845 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1192 | Checking Of Laying PQC Top | 139900 | 140830 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 17:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 17:50 | Rushikesh Gunjal | 2025-09-13 15:04 | Check found ok | 2025-09-14 11:00 | Brajesh Upadhyay | work has been done | 74.7774 | 20.4862 | Inspected | RFI Approved | 930 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1048 | Checking Of Utility Pipe Laying | 138570 | 138570 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-20 16:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-21 14:00 | Saurabh SE | 2025-08-21 12:25 | No found here utility pipe |  |  |  | 74.7715 | 20.4744 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1021 | Checking of Level & FDD Test & Filling of Earthen Shoulder | 125900 | 126600 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-12 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-13 11:50 | Rushikesh Gunjal | 2025-08-13 15:35 | Check found Satisfactory Result | 2025-08-14 09:52 | Brajesh Upadhyay | work has been done | 74.7216 | 20.378 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/981 | Checking Of Laying PQC Top | 135680 | 136330 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-27 17:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-28 10:30 | Rushikesh Gunjal | 2025-08-12 15:59 | Check and found OK | 2025-08-14 10:05 | Brajesh Upadhyay | work has been done | 74.7656 | 20.4609 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1049 | Checking Of Utility Pipe Laying | 138300 | 138300 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-20 16:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-21 16:00 | Saurabh SE | 2025-08-21 12:40 | No found here utility pipe |  |  |  | 74.7704 | 20.4722 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1022 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Final Lift | 140770 | 140810 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-13 17:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-14 11:36 | Rushikesh Gunjal | 2025-08-14 11:10 | Check found OK | 2025-08-14 17:08 | Brajesh Upadhyay | work has been done | 74.7818 | 20.491 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1045 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 120400 | 120400 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-20 16:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-21 14:30 | Kishori Lal | 2025-08-21 16:03 | Work done. | 2025-08-21 17:47 | Brajesh Upadhyay | work has been done | 74.6943 | 20.3366 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1052 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Raft | 120210 | 120230 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-20 16:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-21 14:30 | Kishori Lal | 2025-08-21 16:19 | Work done. | 2025-08-21 17:49 | Brajesh Upadhyay | work has been done | 74.6929 | 20.3355 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1647 | Checking Of Laying DLC Top | 135690 | 136320 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 16:40 | Rushikesh Gunjal | 2025-10-30 15:42 | Work was already done | 2025-10-31 07:44 | Brajesh Upadhyay | work has been done | 74.7612 | 20.4519 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1643 | Checking Of Laying DLC Top | 133230 | 133840 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 16:36 | Rushikesh Gunjal | 2025-10-30 16:12 | Work was already done | 2025-10-31 07:45 | Brajesh Upadhyay | work has been done | 74.7584 | 20.4252 | Inspected | RFI Approved | 610 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1584 | Checking Of Laying DLC Top | 130250 | 130870 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:37 | Rushikesh Gunjal | 2025-10-30 11:43 | Work was already done | 2025-10-31 07:52 | Brajesh Upadhyay | work has been done | 74.7528 | 20.4086 | Inspected | RFI Approved | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1576 | Checking Of Level & FDD Test For GSB Top | 121000 | 121510 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:20 | Rushikesh Gunjal | 2025-10-30 16:54 | Work was already done | 2025-10-31 07:52 | Brajesh Upadhyay | work has been done | 74.7382 | 20.3911 | Inspected | RFI Approved | 510 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1613 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 133628 | 133628 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:34 | Rushikesh Gunjal | 2025-10-30 16:15 | Work was already done | 2025-10-31 07:47 | Brajesh Upadhyay | work has been done | 74.7585 | 20.4239 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1211 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 120250 | 120270 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 14:20 | Kishori Lal | 2025-09-03 18:38 | Not Ready. |  |  |  | 74.6934 | 20.3357 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1210 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 119825 | 119845 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 16:30 | Kishori Lal | 2025-09-03 19:06 | Work done. | 2025-09-04 20:40 | Brajesh Upadhyay | work has been done | 74.691 | 20.3325 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1209 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Raft | 119850 | 119870 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 16:00 | Kishori Lal | 2025-09-03 19:03 | Reinforcement checked and found Satisfactory and allowing for concrete pouring for drain Raft. | 2025-09-04 20:39 | Brajesh Upadhyay | work has been done | 74.6911 | 20.333 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1212 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119870 | 119970 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 15:20 | Saurabh SE | 2025-09-03 18:58 | Work done | 2025-09-04 20:40 | Brajesh Upadhyay | work has been done | 74.6912 | 20.3332 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1461 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 134000 | 134500 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:18 | Rushikesh Gunjal | 2025-10-30 15:58 | Work was already done | 2025-10-31 08:05 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4372 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1203 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top,Level & FDD Test | 140850 | 141700 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 13:30 | Rushikesh Gunjal | 2025-09-13 15:28 | Check found OK | 2025-09-14 10:58 | Brajesh Upadhyay | work has been done | 74.7819 | 20.4916 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1194 | Checking Of Laying PQC Top | 119750 | 120400 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 19:50 | Rushikesh Gunjal | 2025-09-13 16:43 | Ok | 2025-09-14 11:02 | Brajesh Upadhyay | work has been done | 74.696 | 20.3382 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1197 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top,Level & FDD Test | 140850 | 141700 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 08:25 | Rushikesh Gunjal | 2025-09-13 15:32 | Check found OK | 2025-09-14 11:07 | Brajesh Upadhyay | work has been done | 74.7819 | 20.4916 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1208 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119990 | 120000 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 15:30 | Kishori Lal | 2025-09-03 18:55 | Not Ready. |  |  |  | 74.6911 | 20.3331 | Inspected | Inspected - Rejected - Work Not Done | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1183 | Checking Of Laying PQC Top | 134650 | 135550 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 14:00 | Rushikesh Gunjal | 2025-09-06 11:29 | Check found OK | 2025-09-07 09:30 | Brajesh Upadhyay | work has been done | 74.758 | 20.4425 | Inspected | RFI Approved | 900 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1191 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120100 | 120110 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 17:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 14:30 | Kishori Lal | 2025-09-03 18:49 | Work done. | 2025-09-04 20:42 | Brajesh Upadhyay | work has been done | 74.6911 | 20.3338 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1182 | Checking Of Laying PQC Top | 133640 | 134460 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 13:00 | Rushikesh Gunjal | 2025-09-05 12:25 | Check found OK | 2025-09-06 08:06 | Brajesh Upadhyay | work has been done | 74.7582 | 20.4386 | Inspected | RFI Approved | 820 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1185 | Checking Of Laying PQC Top | 136400 | 137280 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 16:20 | Rushikesh Gunjal | 2025-09-11 13:35 | Check found OK | 2025-09-14 11:13 | Brajesh Upadhyay | work has been done | 74.7634 | 20.4562 | Inspected | RFI Approved | 880 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1189 | Checking Of Laying DLC Top | 140250 | 140840 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 11:35 | Rushikesh Gunjal | 2025-09-13 15:38 | Check found Satisfactory result | 2025-09-14 11:48 | Brajesh Upadhyay | work has been done | 74.7819 | 20.4915 | Inspected | RFI Approved | 590 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1054 | Checking Of Utility Pipe Laying | 140250 | 140250 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-21 17:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-22 09:30 | Rushikesh Gunjal | 2025-08-22 17:26 | Check and OK | 2025-08-23 08:38 | Brajesh Upadhyay | work has been done | 74.7747 | 20.48 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1186 | Checking Of Laying PQC Top | 137280 | 138150 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 17:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 17:10 | Rushikesh Gunjal | 2025-09-13 12:26 | Check found OK | 2025-09-14 11:38 | Brajesh Upadhyay | work has been done | 74.7659 | 20.4616 | Inspected | RFI Approved | 870 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1055 | Checking Of Utility Pipe Laying | 140257 | 140257 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-21 17:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-22 11:00 | Rushikesh Gunjal | 2025-08-22 17:24 | Check found OK | 2025-08-23 08:25 | Brajesh Upadhyay | work has been done | 74.7748 | 20.4802 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1178 | Checking Of Laying DLC Top | 119750 | 120400 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 10:30 | Rushikesh Gunjal | 2025-09-13 16:40 | OK | 2025-09-14 11:59 | Brajesh Upadhyay | work has been done | 74.696 | 20.3381 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1057 | Checking Of Utility Pipe Laying | 140600 | 140600 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-21 17:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-22 16:00 | Rushikesh Gunjal | 2025-08-22 11:46 | Check and found a laid utility pipe | 2025-08-23 08:26 | Brajesh Upadhyay | work has been done | 74.7814 | 20.4891 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1175 | Checking Of Laying DLC Top | 139060 | 139900 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 08:30 | Rushikesh Gunjal | 2025-09-11 13:18 | Check found OK | 2025-09-14 11:57 | Brajesh Upadhyay | work has been done | 74.7745 | 20.4797 | Inspected | RFI Approved | 840 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1176 | Checking Of Laying DLC Top | 139900 | 140250 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 10:30 | Rushikesh Gunjal | 2025-09-13 14:46 | Check found OK | 2025-09-14 11:58 | Brajesh Upadhyay | work has been done | 74.776 | 20.4849 | Inspected | RFI Approved | 350 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1180 | Checking Of Laying PQC Top | 132840 | 133210 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 09:30 | Rushikesh Gunjal | 2025-09-04 12:28 | Check found OK | 2025-09-04 20:43 | Brajesh Upadhyay | work has been done | 74.7585 | 20.4351 | Inspected | RFI Approved | 370 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1177 | Checking Of Laying DLC Top | 123450 | 123870 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 14:30 | Rushikesh Gunjal | 2025-09-13 14:48 | Ok | 2025-09-14 11:58 | Brajesh Upadhyay | work has been done | 74.776 | 20.485 | Inspected | RFI Approved | 420 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1168 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Wall | 119830 | 119850 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-01 18:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-02 11:30 | Kishori Lal | 2025-09-02 14:10 | Work done. | 2025-09-03 10:03 | Brajesh Upadhyay | work has been done | 74.691 | 20.3327 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1170 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119990 | 120000 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-01 18:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-02 16:10 | Kishori Lal | 2025-09-02 14:06 | Work done. | 2025-09-03 10:02 | Brajesh Upadhyay | work has been done | 74.6915 | 20.3338 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1165 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall Raft | 140650 | 140665 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-01 18:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-02 14:30 | Kishori Lal | 2025-09-02 11:10 | Work done. | 2025-09-03 10:06 | Brajesh Upadhyay | work has been done | 74.7815 | 20.4899 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1169 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119850 | 119870 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-01 18:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-02 14:00 | Kishori Lal | 2025-09-02 14:11 | Work done. | 2025-09-03 10:03 | Brajesh Upadhyay | work has been done | 74.6912 | 20.3326 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1157 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Slab | 120185 | 120205 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-31 18:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-01 16:00 | Kishori Lal | 2025-09-02 14:00 | Work done. | 2025-09-03 10:07 | Brajesh Upadhyay | work has been done | 74.6929 | 20.3352 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1000 | Checking Of Laying PQC Top | 137860 | 138490 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-07-30 14:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-07-31 10:30 | Rushikesh Gunjal | 2025-08-21 16:31 | Checked and found OK | 2025-08-21 17:53 | Brajesh Upadhyay | work has been done | 74.7695 | 20.47 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1317 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119840 | 119860 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-27 18:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-28 15:00 | Kishori Lal | 2025-09-29 11:41 | PCC Formwork not ready. |  |  |  | 74.6908 | 20.3326 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1060 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Wall | 120210 | 120230 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-21 18:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-22 15:00 | Rushikesh Gunjal | 2025-08-22 15:37 | Shuttering Work not done |  |  |  | 74.6932 | 20.3355 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1058 | Checking Of Layout Marking & Excavation & Laying PCC For Drain | 120000 | 120030 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-21 18:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-22 14:00 | Rushikesh Gunjal | 2025-08-22 15:52 | Check and found OK | 2025-08-23 08:27 | Brajesh Upadhyay | work has been done | 74.6917 | 20.334 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1059 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Raft | 120030 | 120050 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-21 18:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-22 14:30 | Rushikesh Gunjal | 2025-08-22 15:50 | Check found OK | 2025-08-23 08:28 | Brajesh Upadhyay | work has been done | 74.6918 | 20.334 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1181 | Checking Of Laying PQC Top | 133230 | 133640 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 11:00 | Rushikesh Gunjal | 2025-09-05 12:19 | Check and Ok | 2025-09-06 08:06 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4387 | Inspected | RFI Approved | 410 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1056 | Checking Of Utility Pipe Laying | 140265 | 140265 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-21 17:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-22 14:00 | Rushikesh Gunjal | 2025-08-22 17:23 | Check and found OK | 2025-08-23 08:26 | Brajesh Upadhyay | work has been done | 74.7747 | 20.4801 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1062 | Checking Of Layout Marking , Excavation & Laying PCC For Retaining Wall | 140540 | 140590 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-22 18:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-23 14:30 | Rushikesh Gunjal | 2025-08-23 11:30 | Check found OK | 2025-08-25 21:51 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4888 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1063 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119780 | 119820 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-22 18:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-23 12:30 | Rushikesh Gunjal | 2025-08-23 14:01 | Check found Ok | 2025-08-25 21:52 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3322 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1064 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Wall | 120210 | 120230 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-22 18:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-23 13:30 | Rushikesh Gunjal | 2025-08-23 13:37 | Check found OK | 2025-08-25 21:52 | Brajesh Upadhyay | work has been done | 74.6931 | 20.3354 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1065 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Raft | 120000 | 120020 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-22 18:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-23 14:00 | Rushikesh Gunjal | 2025-08-23 13:43 | OK | 2025-08-25 21:53 | Brajesh Upadhyay | work has been done | 74.6917 | 20.3339 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1066 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Wall | 120020 | 120040 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-22 18:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-23 15:00 | Rushikesh Gunjal | 2025-08-23 13:46 | Check found OK | 2025-08-25 09:41 | Brajesh Upadhyay | work has been done | 74.6918 | 20.3341 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1061 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Raft | 120190 | 120210 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-21 18:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-22 16:00 | Rushikesh Gunjal | 2025-08-22 15:35 | Check found OK | 2025-08-23 08:29 | Brajesh Upadhyay | work has been done | 74.6934 | 20.3358 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1213 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall First lift | 140650 | 140665 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 19:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 15:00 | Kishori Lal | 2025-09-03 16:09 | Work already done. |  |  |  | 74.7798 | 20.4896 | Inspected | Inspected - Rejected - Work Not Done | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1166 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall Final lift | 140590 | 140610 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-01 18:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-02 15:30 | Kishori Lal | 2025-09-03 16:26 | Not Ready. |  |  |  | 74.7814 | 20.4893 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1069 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119780 | 119800 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-23 18:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-24 15:45 | Rushikesh Gunjal | 2025-08-25 13:21 | Wrong Chainage i. e. 119790 to 119810 |  |  |  | 74.6908 | 20.3326 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1215 | Checking Of Reinforcement , Shuttering & pouring Concrete For Drain Slab | 120040 | 120060 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-03 16:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-04 15:30 | Rushikesh Gunjal | 2025-09-04 16:42 | Check and OK | 2025-09-04 20:35 | Brajesh Upadhyay | work has been done | 74.6929 | 20.3352 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1207 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120110 | 120130 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 14:45 | Kishori Lal | 2025-09-03 18:52 | Work done. | 2025-09-04 20:41 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3326 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1067 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall Raft | 140540 | 140590 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-23 18:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-24 14:15 | Rushikesh Gunjal | 2025-08-25 16:53 | Work done | 2025-08-25 21:47 | Brajesh Upadhyay | work has been done | 74.7826 | 20.4884 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1068 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Raft | 120260 | 120280 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-23 18:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-24 15:30 | Rushikesh Gunjal | 2025-08-25 13:30 | OK | 2025-08-25 21:49 | Brajesh Upadhyay | work has been done | 74.693 | 20.336 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1262 | Checking Of Level & FDD test for GSB Top Layer | 120400 | 121000 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-14 09:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 16:40 | Saurabh SE | 2025-09-15 15:16 | Work done | 2025-09-16 08:10 | Brajesh Upadhyay | work has been done | 74.6972 | 20.3394 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1228 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Wall | 119870 | 119890 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-06 16:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-07 13:30 | Kishori Lal | 2025-09-07 17:07 | Work done. | 2025-09-07 19:09 | Brajesh Upadhyay | work has been done | 74.6943 | 20.3314 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1230 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 119845 | 119870 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-06 16:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-07 15:30 | Kishori Lal | 2025-09-07 17:15 | Work done. | 2025-09-07 19:10 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3328 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1070 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Wall | 120260 | 120280 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-25 16:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-26 14:30 | Rushikesh Gunjal | 2025-08-26 14:03 | Check found Satisfactory | 2025-08-27 09:39 | Brajesh Upadhyay | work has been done | 74.693 | 20.336 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1071 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Wall | 120170 | 120210 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-25 16:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-26 14:45 | Rushikesh Gunjal | 2025-08-26 14:14 | OK | 2025-08-27 09:48 | Brajesh Upadhyay | work has been done | 74.6928 | 20.335 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1073 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Wall | 119785 | 119805 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-25 16:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-26 15:15 | Rushikesh Gunjal | 2025-08-26 14:50 | OK | 2025-08-27 09:49 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3323 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1072 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Wall | 120000 | 120020 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-25 16:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-26 15:00 | Rushikesh Gunjal | 2025-08-26 14:30 | Ok | 2025-08-27 09:49 | Brajesh Upadhyay | work has been done | 74.6917 | 20.334 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1076 | Checking Of Layout Marking ,Excavation & Laying PCC For Drain | 120050 | 120070 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-25 16:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-26 16:00 | Rushikesh Gunjal | 2025-08-26 14:34 | Work not done |  |  |  | 74.692 | 20.3341 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1077 | Checking Of Layout Marking ,Excavation & Laying PCC For Drain | 119820 | 119830 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-25 16:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-26 16:15 | Rushikesh Gunjal | 2025-08-26 14:51 | Check found OK | 2025-08-27 09:51 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3326 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1079 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall First Lift | 140540 | 140590 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-25 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-26 14:00 | Rushikesh Gunjal | 2025-08-26 12:26 | Check found OK | 2025-08-27 09:36 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4891 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1214 | Checking Of Reinforcement , Shuttering & pouring Concrete For Drain Slab | 120165 | 120185 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-03 16:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-04 14:30 | Rushikesh Gunjal | 2025-09-04 16:37 | Work not done |  |  |  | 74.6919 | 20.3343 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1080 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 123750 | 123850 | BHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 13:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-26 15:30 | Rushikesh Gunjal | 2025-09-13 15:17 | Check and found OK | 2025-09-14 12:21 | Brajesh Upadhyay | work has been done | 74.7792 | 20.4876 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1086 | Checking Of Level & FDD test for GSB Top Layer | 134500 | 134990 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 14:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-27 14:30 | Rushikesh Gunjal | 2025-08-30 11:13 | Check found Satisfactory | 2025-09-01 09:35 | Brajesh Upadhyay | work has been done | 74.758 | 20.442 | Inspected | RFI Approved | 490 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1087 | Checking Of Level & FDD test for GSB Top Layer | 140050 | 140260 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 14:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-27 17:30 | Rushikesh Gunjal | 2025-09-13 15:00 | Check found Satisfactory result | 2025-09-14 12:20 | Brajesh Upadhyay | work has been done | 74.7774 | 20.4862 | Inspected | RFI Approved | 210 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1075 | Checking Of Layout Marking ,Excavation & Laying PCC For Drain | 120150 | 120170 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-25 16:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-26 15:40 | Rushikesh Gunjal | 2025-08-26 14:18 | Check found OK | 2025-08-27 09:50 | Brajesh Upadhyay | work has been done | 74.6927 | 20.335 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1083 | Checking Of Laying PQC Top | 138490 | 139140 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 14:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-27 09:30 | Rushikesh Gunjal | 2025-08-29 11:42 | Check and OK | 2025-08-29 12:26 | Brajesh Upadhyay | work has been done | 74.7762 | 20.4853 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1092 | Checking Of Layout Marking ,Excavation & Laying PCC For Drain | 120110 | 120150 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 18:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-27 14:30 | Kishori Lal | 2025-08-27 17:40 | Work done. | 2025-08-27 20:07 | Brajesh Upadhyay | work has been done | 74.6922 | 20.3347 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1093 | Checking Of Reinforcement , Shuttering & pouring Concrete For Drain Raft | 119805 | 119830 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 18:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-27 14:45 | Kishori Lal | 2025-08-27 17:55 | Work done. | 2025-08-27 20:08 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3326 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1094 | Checking Of Reinforcement , Shuttering & pouring Concrete For Drain Raft | 120150 | 120170 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 18:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-27 15:15 | Kishori Lal | 2025-08-27 17:43 | Work done. | 2025-08-27 20:09 | Brajesh Upadhyay | work has been done | 74.6925 | 20.3351 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1095 | Checking Of Reinforcement , Shuttering & pouring Concrete For Drain Raft | 120240 | 120260 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 18:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-27 16:00 | Kishori Lal | 2025-08-27 17:47 | Work done. | 2025-08-27 19:53 | Brajesh Upadhyay | work has been done | 74.6932 | 20.3356 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1089 | Checking Of Laying PQC Top | 139140 | 139790 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 16:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-27 16:30 | Rushikesh Gunjal | 2025-08-29 11:38 | OK | 2025-08-29 12:27 | Brajesh Upadhyay | work has been done | 74.7765 | 20.4855 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1090 | Checking OF Reinforcement , Shuttering & Pouring Concrete For Retaining Wall Final lift | 132970 | 132981 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-27 14:10 | Rushikesh Gunjal | 2025-08-28 18:36 | Shuttering and Reinforcement work is not done |  |  |  | 74.7582 | 20.4265 | Inspected | Inspected - Rejected - Work Not Done | 11 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1074 | Checking Of Layout Marking ,Excavation & Laying PCC For Drain | 120230 | 120260 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-25 16:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-26 15:30 | Rushikesh Gunjal | 2025-08-26 14:07 | OK | 2025-08-27 09:50 | Brajesh Upadhyay | work has been done | 74.693 | 20.336 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1078 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Final Lift | 140810 | 140840 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-25 16:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-26 11:00 | Rushikesh Gunjal | 2025-08-26 12:06 | OK | 2025-08-27 09:51 | Brajesh Upadhyay | work has been done | 74.7818 | 20.4913 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1231 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119990 | 120000 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-06 16:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-07 16:00 | Kishori Lal | 2025-09-07 17:02 | Not Ready. |  |  |  | 74.69 | 20.3393 | Inspected | Inspected - Rejected - Work Not Done | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1224 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 120145 | 120165 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-06 16:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-07 10:30 | Kishori Lal | 2025-09-07 16:51 | Work done. | 2025-09-07 19:12 | Brajesh Upadhyay | work has been done | 74.6925 | 20.335 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1096 | Checking Of Laying PQC Top | 135170 | 135340 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 17:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 08:30 | Rushikesh Gunjal | 2025-08-30 11:42 | Ok | 2025-09-01 09:25 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4369 | Inspected | RFI Approved | 170 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1100 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 140680 | 140850 | BHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 17:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 15:30 | Rushikesh Gunjal | 2025-08-29 11:25 | Check found Satisfactory result | 2025-08-29 12:21 | Brajesh Upadhyay | work has been done | 74.7814 | 20.4898 | Inspected | RFI Approved | 170 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1101 | Checking existing BT dismentaling excavation up to embankment top, Level and FDD test after excavation | 134490 | 134500 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 17:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 13:00 | Rushikesh Gunjal | 2025-08-30 12:07 | Check found Satisfactory | 2025-09-01 09:28 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4285 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1091 | Checking Of Layout Marking ,Excavation & Laying PCC For Drain | 120050 | 120070 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-26 18:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-27 13:30 | Kishori Lal | 2025-08-27 17:37 | Work done. | 2025-08-27 20:07 | Brajesh Upadhyay | work has been done | 74.6922 | 20.3344 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1113 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Slab | 120205 | 120225 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 18:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 16:30 | Rushikesh Gunjal | 2025-08-28 17:43 | Reinforcement work is not done |  |  |  | 74.693 | 20.3353 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1112 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Slab | 119785 | 119805 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 18:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 16:00 | Rushikesh Gunjal | 2025-08-28 17:17 | Check found OK | 2025-08-29 11:05 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3326 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1111 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Raft | 120050 | 120070 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 18:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 15:30 | Rushikesh Gunjal | 2025-08-28 17:32 | OK | 2025-08-29 11:04 | Brajesh Upadhyay | work has been done | 74.6921 | 20.3343 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1107 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Wall | 120240 | 120260 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 18:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 14:00 | Rushikesh Gunjal | 2025-08-28 17:48 | Check found OK | 2025-08-29 12:19 | Brajesh Upadhyay | work has been done | 74.6933 | 20.3357 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1108 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Wall | 120150 | 120170 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 18:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 14:30 | Rushikesh Gunjal | 2025-08-28 17:52 | OK | 2025-08-29 12:20 | Brajesh Upadhyay | work has been done | 74.6927 | 20.335 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1109 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Wall | 119805 | 119830 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 18:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 15:00 | Rushikesh Gunjal | 2025-08-28 17:22 | Check found OK | 2025-08-29 12:20 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3323 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1110 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Drain Raft | 120110 | 120150 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 18:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 15:30 | Rushikesh Gunjal | 2025-08-28 17:37 | OK | 2025-08-29 12:20 | Brajesh Upadhyay | work has been done | 74.6928 | 20.3351 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1822 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall A1, A2 Raft Of Box Culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 18:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 15:30 | Rushikesh Gunjal | 2025-12-02 15:14 | Work done | 2025-12-02 16:48 | Brajesh Upadhyay | work has been done | 74.782 | 20.4923 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1217 | Checking Of Reinforcement Shuttering & Pouring Concrete For Retaining Wall Final Lift | 140540 | 140590 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-04 17:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-05 14:00 | Kishori Lal | 2025-09-05 17:54 | Not Ready. |  |  |  | 74.7811 | 20.4887 | Inspected | Inspected - Rejected - Work Not Done | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1218 | Checking Of Layout Marking , Excavation & Laying PCC For Retaining Wall | 140520 | 140540 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-04 17:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-05 13:30 | Kishori Lal | 2025-09-05 17:53 | Not Ready. |  |  |  | 74.7811 | 20.4888 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1425 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120190 | 120230 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-16 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:30 | Rushikesh Gunjal | 2025-10-31 10:53 | Work was already done | 2025-10-31 20:05 | Brajesh Upadhyay | work has been done | 74.6924 | 20.3348 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1115 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top,Level & FDD Test | 117650 | 118150 | BHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-28 16:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-29 14:30 | Rushikesh Gunjal | 2025-09-13 17:03 | OK | 2025-09-14 12:14 | Brajesh Upadhyay | work has been done | 74.696 | 20.3382 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1121 | Checking Of Level & FDD Test For GSB Top | 134990 | 135550 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-28 17:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-29 10:00 | Rushikesh Gunjal | 2025-08-30 11:34 | Check found OK | 2025-09-01 09:17 | Brajesh Upadhyay | work has been done | 74.7587 | 20.437 | Inspected | RFI Approved | 560 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1821 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall A1, A2 Second Lift Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 18:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 13:00 | Rushikesh Gunjal | 2025-12-02 15:52 | Work done | 2025-12-02 16:48 | Brajesh Upadhyay | work has been done | 74.7484 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1222 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Raft | 120090 | 120100 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-04 18:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-05 15:30 | Kishori Lal | 2025-09-05 15:57 | Not Ready. |  |  |  | 74.6921 | 20.3344 | Inspected | Inspected - Rejected - Work Not Done | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1219 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Wall | 119850 | 119870 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-04 18:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-05 13:45 | Kishori Lal | 2025-09-05 15:43 | Work done. | 2025-09-06 07:55 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3326 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1220 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 120145 | 120165 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-04 18:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-05 14:30 | Kishori Lal | 2025-09-05 16:09 | Not Ready. |  |  |  | 74.6926 | 20.335 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1221 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 120170 | 120190 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-04 18:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-05 15:00 | Kishori Lal | 2025-09-05 16:23 | Work done. | 2025-09-06 07:55 | Brajesh Upadhyay | work hasa been done | 74.6931 | 20.3353 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1223 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Raft | 119870 | 119890 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-04 18:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-05 16:00 | Kishori Lal | 2025-09-05 15:48 | Work done. | 2025-09-06 07:53 | Brajesh Upadhyay | work has been done | 74.6913 | 20.3326 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1114 | Checking Of Reinforcement Shuttering & Pouring Concrete For Retaining Wall Wall 2nd Lift | 140540 | 140590 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 18:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 16:30 | Rushikesh Gunjal | 2025-08-29 11:33 | Check and OK | 2025-08-29 12:17 | Brajesh Upadhyay | work has been done | 74.7814 | 20.4891 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1236 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119890 | 119910 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-08 17:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-09 15:00 | Kishori Lal | 2025-09-10 15:00 | Work done. | 2025-09-11 08:34 | Brajesh Upadhyay | work has been done | 74.6911 | 20.333 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1240 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120320 | 120340 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-08 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-09 16:20 | Kishori Lal | 2025-09-10 14:47 | Work done. | 2025-09-11 08:36 | Brajesh Upadhyay | work has been done | 74.6938 | 20.3362 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1819 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120050 | 120140 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 18:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 16:00 | Rushikesh Gunjal | 2025-12-02 11:10 | Work done | 2025-12-02 16:49 | Brajesh Upadhyay | work has been done | 74.6919 | 20.3344 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1818 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 129500 | 129540 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 11:00 | Rushikesh Gunjal | 2025-12-02 16:01 | Work done | 2025-12-02 16:49 | Brajesh Upadhyay | work has been done | 74.7475 | 20.3982 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1272 | Checking Layout Marking , Excavation & Laying PCC For Drain | 120360 | 120400 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-15 18:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-16 15:00 | Kishori Lal | 2025-09-16 17:48 | Work done. | 2025-09-16 20:29 | Brajesh Upadhyay | work has been done | 74.6935 | 20.3359 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1273 | Checking Of Laying PQC Top | 122500 | 122550 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-15 18:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-16 10:30 | Rushikesh Gunjal | 2025-09-16 17:18 | Check and OK | 2025-09-16 17:27 | Brajesh Upadhyay | work has been done | 74.7045 | 20.357 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1161 | Checking Of Level & Fdd Test For GSB Top | 139060 | 139900 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-01 18:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-02 10:30 | Rushikesh Gunjal | 2025-09-09 18:00 | Check found OK | 2025-09-14 12:04 | Brajesh Upadhyay | work has been done | 74.7742 | 20.4786 | Inspected | RFI Approved | 840 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1242 | Checking Of Layout Marking , Excavation & Laying PCC For Retaining Wall | 140515 | 140540 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-09 18:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-10 09:53 | Kishori Lal | 2025-09-14 13:52 | Work done. | 2025-09-16 08:23 | Brajesh Upadhyay | work has been done | 74.7811 | 20.4886 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1241 | Checking Of Layout Marking, Excavation & Laying PCC For Drain | 120380 | 120400 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-08 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-09 11:50 | Kishori Lal | 2025-09-10 14:43 | Work not done. |  |  |  | 74.6941 | 20.3361 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1267 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119970 | 120000 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-14 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-15 14:30 | Kishori Lal | 2025-09-16 17:54 | Work done. | 2025-09-16 20:32 | Brajesh Upadhyay | work has been done | 74.6917 | 20.3337 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/4 | FDD AND LEVEL CHECKING OF GSB TOP LAYER | 129280 | 129580 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 17:58 | Sanjay Sharma | 2025-08-01 13:57 | Sanjay Sharma | 2025-09-16 17:58 | Work done successfully. | 2025-09-16 17:58 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 300 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/2 | FDD AND LEVEL CHECKING OF GSB TOP LAYER | 121000 | 123720 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 17:55 | Sanjay Sharma | 2025-07-15 14:52 | Sanjay Sharma | 2025-09-16 17:55 | Work done successfully. | 2025-09-16 17:55 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 2720 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/3 | FDD AND LEVEL CHECKING OF GSB TOP LAYER | 123820 | 125890 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 17:57 | Sanjay Sharma | 2025-07-25 14:55 | Sanjay Sharma | 2025-09-16 17:57 | Work done successfully. | 2025-09-16 17:57 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 2070 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1269 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119940 | 119970 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-14 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-15 15:30 | Kishori Lal | 2025-09-16 17:58 | Work done. | 2025-09-16 20:33 | Brajesh Upadhyay | work has been done | 74.6918 | 20.334 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/5 | FDD AND LEVEL CHECKING OF GSB TOP LAYER | 129720 | 130890 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:00 | Sanjay Sharma | 2025-08-03 16:58 | Sanjay Sharma | 2025-09-16 18:00 | Work done successfully. | 2025-09-16 18:00 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 1170 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/6 | FDD AND LEVEL CHECKING OF GSB TOP LAYER | 131670 | 133200 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:01 | Sanjay Sharma | 2025-08-12 14:59 | Sanjay Sharma | 2025-09-16 18:01 | Work done successfully. | 2025-09-16 18:01 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 1530 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/7 | DLC LAYING | 121020 | 121500 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:05 | Sanjay Sharma | 2025-08-13 13:02 | Sanjay Sharma | 2025-09-16 18:05 | Work done successfully. | 2025-09-16 18:05 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 480 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/8 | DLC LAYING | 132900 | 133210 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:06 | Sanjay Sharma | 2025-08-14 14:05 | Sanjay Sharma | 2025-09-16 18:06 | Work done successfully. | 2025-09-16 18:06 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 310 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1148 | Checking Of Level & FDD Test For GSB Top | 138150 | 139060 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-31 18:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-01 14:30 | Saurabh SE | 2025-09-10 12:39 | Work done | 2025-09-14 12:06 | Brajesh Upadhyay | work has been done | 74.7734 | 20.4773 | Inspected | RFI Approved | 910 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1163 | Checking Of Laying DLC Top | 138150 | 139060 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-01 18:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-02 15:30 | Rushikesh Gunjal | 2025-09-10 12:56 | Check found OK | 2025-09-14 12:04 | Brajesh Upadhyay | work has been done | 74.7725 | 20.4758 | Inspected | RFI Approved | 910 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1137 | Checking Of Level & FDD Test For GSB TOP | 137280 | 138150 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-30 16:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-31 10:30 | Saurabh SE | 2025-09-10 12:47 | Work done | 2025-09-14 12:09 | Brajesh Upadhyay | work has been done | 74.7727 | 20.476 | Inspected | RFI Approved | 870 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/9 | DLC LAYING | 133230 | 137060 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:07 | Sanjay Sharma | 2025-08-17 15:06 | Sanjay Sharma | 2025-09-16 18:07 | Work done successfully. | 2025-09-16 18:07 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 3830 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1268 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119770 | 119800 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-14 18:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-15 15:00 | Kishori Lal | 2025-09-16 18:09 | RHS side already work done. |  |  |  | 74.6908 | 20.3325 | Inspected | Inspected - Fail | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/10 | DLC LAYING | 138480 | 140250 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:08 | Sanjay Sharma | 2025-08-18 15:07 | Sanjay Sharma | 2025-09-16 18:08 | Work done successfully. | 2025-09-16 18:08 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 1770 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/11 | DLC LAYING | 121010 | 123710 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:10 | Sanjay Sharma | 2025-08-19 16:08 | Sanjay Sharma | 2025-09-16 18:10 | Work done successfully. | 2025-09-16 18:10 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 2700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/12 | DLC LAYING | 127170 | 129660 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:11 | Sanjay Sharma | 2025-08-20 15:09 | Sanjay Sharma | 2025-09-16 18:11 | Work done successfully. | 2025-09-16 18:11 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 2490 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/13 | DLC LAYING | 129780 | 131660 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:12 | Sanjay Sharma | 2025-08-21 14:11 | Sanjay Sharma | 2025-09-16 18:12 | Work done successfully. | 2025-09-16 18:12 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 1880 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1275 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119770 | 119790 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-15 18:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-16 17:30 | Kishori Lal | 2025-09-16 18:13 | Work done. | 2025-09-16 20:29 | Brajesh Upadhyay | work has been done | 74.6907 | 20.3326 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1234 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119870 | 119890 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-08 17:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-09 13:30 | Kishori Lal | 2025-09-10 14:58 | Not Ready. |  |  |  | 74.6911 | 20.3329 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/14 | DLC LAYING | 132260 | 133050 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:14 | Sanjay Sharma | 2025-08-22 13:12 | Sanjay Sharma | 2025-09-16 18:14 | Work done successfully. | 2025-09-16 18:14 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 790 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1238 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119910 | 119930 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-08 17:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-09 15:30 | Kishori Lal | 2025-09-10 15:01 | Not Ready. |  |  |  | 74.6912 | 20.3332 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1239 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119970 | 119990 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-08 17:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-09 16:00 | Kishori Lal | 2025-09-10 15:06 | Work done. | 2025-09-11 08:35 | Brajesh Upadhyay | work has been done | 74.6918 | 20.3338 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/15 | PQC LAYING | 123840 | 124470 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:17 | Sanjay Sharma | 2025-08-22 16:15 | Sanjay Sharma | 2025-09-16 18:17 | Work done successfully. | 2025-09-16 18:17 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/16 | PQC LAYING | 129360 | 129610 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:18 | Sanjay Sharma | 2025-08-23 17:17 | Sanjay Sharma | 2025-09-16 18:18 | Work done successfully. | 2025-09-16 18:18 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 250 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/17 | PQC LAYING | 129810 | 132840 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:20 | Sanjay Sharma | 2025-08-24 18:18 | Sanjay Sharma | 2025-09-16 18:20 | Work done successfully. | 2025-09-16 18:20 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 3030 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/18 | PQC LAYING | 131120 | 132050 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:23 | Sanjay Sharma | 2025-08-25 10:21 | Sanjay Sharma | 2025-09-16 18:23 | Work done successfully. | 2025-09-16 20:24 | Brajesh Upadhyay | work has been done | 0 | 0 | Inspected | RFI Approved | 930 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1279 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119800 | 119830 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-17 14:30 | Rushikesh Gunjal | 2025-09-17 12:23 | Not done |  |  |  | 74.6909 | 20.3326 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1280 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119930 | 119940 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-17 15:00 | Rushikesh Gunjal | 2025-09-17 12:14 | OK | 2025-09-17 21:16 | Brajesh Upadhyay | work has been done | 74.6922 | 20.3344 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1277 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119790 | 119800 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-17 09:30 | Rushikesh Gunjal | 2025-09-17 12:19 | OK | 2025-09-17 21:14 | Brajesh Upadhyay | work has been done | 74.691 | 20.3326 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1282 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120380 | 120400 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-17 17:30 | Rushikesh Gunjal | 2025-09-17 12:06 | Not done |  |  |  | 74.6932 | 20.3323 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1278 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120360 | 120400 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-17 10:00 | Rushikesh Gunjal | 2025-09-17 12:07 | Not done |  |  |  | 74.6939 | 20.3364 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1281 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119790 | 119800 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 18:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-17 17:00 | Rushikesh Gunjal | 2025-09-17 12:22 | OK | 2025-09-17 21:16 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3326 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1270 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119770 | 119790 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-15 17:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-16 08:30 | Kishori Lal | 2025-09-16 18:12 | Work done. | 2025-09-16 20:28 | Brajesh Upadhyay | work has been done | 74.691 | 20.3324 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1271 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119950 | 119970 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-15 18:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-16 14:10 | Kishori Lal | 2025-09-16 18:00 | Not Ready. |  |  |  | 74.6922 | 20.3344 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1266 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119910 | 119930 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-14 18:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-15 14:00 | Kishori Lal | 2025-09-16 18:01 | Work done. | 2025-09-16 20:30 | Brajesh Upadhyay | work has been done | 74.6894 | 20.3332 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1243 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall Raft | 140515 | 140540 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-10 17:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-11 10:58 | Rushikesh Gunjal | 2025-09-11 11:54 | Ok | 2025-09-11 21:52 | Brajesh Upadhyay | work has been done | 74.7811 | 20.4886 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1196 | Checking Reinforcement, shuttering and pouring concrete for retaining Wall Final Lift | 118870 | 119060 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 10:30 | Kishori Lal | 2025-09-14 18:10 | Work done. | 2025-09-16 08:29 | Brajesh Upadhyay | work has been done | 74.6902 | 20.3266 | Inspected | RFI Approved | 190 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1237 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119990 | 120000 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-08 17:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-09 15:20 | Kishori Lal | 2025-09-10 15:07 | Work done. | 2025-09-11 08:35 | Brajesh Upadhyay | work has been done | 74.6915 | 20.3338 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1235 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120100 | 120145 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-08 17:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-09 14:15 | Kishori Lal | 2025-09-10 14:51 | Work done. | 2025-09-11 08:38 | Brajesh Upadhyay | work has been done | 74.6917 | 20.3342 | Inspected | RFI Approved | 45 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1233 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall Final Lift | 140540 | 140610 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-07 18:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-08 14:30 | Rushikesh Gunjal | 2025-09-11 11:46 | Check found OK | 2025-09-11 21:55 | Brajesh Upadhyay | work has been done | 74.7813 | 20.489 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1172 | Checking Of Level & FDD test for GSB Top Layer | 123700 | 123870 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 16:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 11:30 | Rushikesh Gunjal | 2025-09-11 13:03 | Check found OK | 2025-09-14 11:54 | Brajesh Upadhyay | work has been done | 74.7748 | 20.4809 | Inspected | RFI Approved | 170 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1816 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 140930 | 141690 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 15:00 | Rushikesh Gunjal | 2025-12-02 15:01 | Check fdd and found satisfactory result | 2025-12-02 16:49 | Brajesh Upadhyay | work has been done | 74.7829 | 20.4958 | Inspected | RFI Approved | 760 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1815 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 129535 | 129590 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-04 16:00 | Rushikesh Gunjal | 2025-12-02 15:55 | Work done | 2025-12-02 16:49 | Brajesh Upadhyay | work has been done | 74.7478 | 20.3985 | Inspected | RFI Approved | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1814 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 129590 | 129650 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 18:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 12:30 | Rushikesh Gunjal | 2025-12-02 15:54 | Work done | 2025-12-02 16:49 | Brajesh Upadhyay | work has been done | 74.7478 | 20.3985 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1244 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall First Lift | 140515 | 140540 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-11 18:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-12 14:30 | Rushikesh Gunjal | 2025-09-12 18:07 | Ok | 2025-09-12 20:36 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4887 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1813 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 137200 | 138040 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 17:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 11:00 | Rushikesh Gunjal | 2025-12-02 15:34 | Check FDD and found satisfactory result | 2025-12-02 16:50 | Brajesh Upadhyay | work has been done | 74.7695 | 20.4702 | Inspected | RFI Approved | 840 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1812 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 141700 | 141800 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 17:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 09:30 | Rushikesh Gunjal | 2025-12-02 15:00 | Check fdd and found satisfactory result | 2025-12-02 16:50 | Brajesh Upadhyay | work has been done | 74.7829 | 20.4958 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2055 | Checking Of Layout Marking, Excavation & Laying PCC For Drain | 119945 | 119970 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-23 18:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-24 10:00 | Rushikesh Gunjal | 2026-01-24 15:31 | Work done | 2026-01-25 11:45 | Brajesh Upadhyay | work has been done | 74.6914 | 20.3337 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1284 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120165 | 120185 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-18 18:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-19 14:45 | Rushikesh Gunjal | 2025-09-19 17:46 | Work not done |  |  |  | 74.6934 | 20.3358 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1287 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119800 | 119830 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-18 18:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-19 10:50 | Rushikesh Gunjal | 2025-09-19 17:33 | Check and work done | 2025-09-20 08:58 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3324 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1288 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119830 | 119840 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-18 18:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-19 22:45 | Rushikesh Gunjal | 2025-09-19 17:35 | Check and found OK | 2025-09-20 08:58 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3325 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1811 | Checking Of Layout Marking , Excavation & Laying PCC For HPC | 122070 | 122070 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 17:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 14:00 | Rushikesh Gunjal | 2025-12-02 11:27 | Work already done | 2025-12-02 16:50 | Brajesh Upadhyay | work has been done | 74.7006 | 20.3498 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1283 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119870 | 119890 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-18 18:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-19 14:00 | Rushikesh Gunjal | 2025-09-19 17:42 | Reinforcement work not done |  |  |  | 74.6915 | 20.3337 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1290 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119940 | 119970 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-18 18:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-19 16:00 | Rushikesh Gunjal | 2025-09-19 17:40 | Check found OK | 2025-09-20 08:46 | Brajesh Upadhyay | work has been done | 74.692 | 20.3343 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1286 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119770 | 119790 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-18 18:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-19 15:30 | Rushikesh Gunjal | 2025-09-19 17:31 | Work done and OK | 2025-09-20 08:57 | Brajesh Upadhyay | work has been done | 74.6907 | 20.3322 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1289 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119930 | 119940 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-18 18:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-19 15:35 | Rushikesh Gunjal | 2025-09-19 17:41 | Ok | 2025-09-20 08:46 | Brajesh Upadhyay | work has been done | 74.6914 | 20.3336 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1292 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120360 | 120400 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-19 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-20 15:30 | Kishori Lal | 2025-09-20 17:13 | Not Ready. |  |  |  | 74.6947 | 20.3373 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1291 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119800 | 119840 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-19 18:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-20 14:00 | Kishori Lal | 2025-09-20 18:14 | Work done. | 2025-09-21 10:11 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3327 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1295 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119930 | 119940 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-19 18:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-20 16:00 | Kishori Lal | 2025-09-20 18:07 | Work done. | 2025-09-21 10:13 | Brajesh Upadhyay | work has been done | 74.6913 | 20.3336 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1297 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120165 | 120185 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-19 18:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-20 10:50 | Kishori Lal | 2025-09-20 17:57 | Work done. | 2025-09-21 10:15 | Brajesh Upadhyay | work has been done | 74.6928 | 20.3351 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1294 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119950 | 119970 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-19 18:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-20 13:30 | Kishori Lal | 2025-09-20 18:05 | Work done. | 2025-09-21 10:13 | Brajesh Upadhyay | work has been done | 74.6915 | 20.3337 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1296 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119870 | 119890 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-19 18:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-20 12:30 | Kishori Lal | 2025-09-20 18:11 | Work done. | 2025-09-21 10:14 | Brajesh Upadhyay | work has been done | 74.691 | 20.3328 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1285 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120360 | 120400 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-18 18:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-19 15:00 | Rushikesh Gunjal | 2025-09-19 16:08 | OK | 2025-09-20 08:57 | Brajesh Upadhyay | work has been done | 74.694 | 20.3364 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/01321 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119745 | 119785 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-29 18:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-30 14:30 | Kishori Lal | 2025-10-01 13:52 | Work done. | 2025-10-02 11:49 | Brajesh Upadhyay | work has been done | 74.6907 | 20.3318 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/01323 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120020 | 120030 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-29 18:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-30 16:15 | Kishori Lal | 2025-10-01 14:05 | Work done. | 2025-10-02 11:49 | Brajesh Upadhyay | work has been done | 74.6916 | 20.334 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1298 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120360 | 120400 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-20 18:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-21 14:30 | Rushikesh Gunjal | 2025-09-23 11:27 | Work not done |  |  |  | 74.6941 | 20.3366 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1299 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119800 | 119840 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-20 18:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-21 15:30 | Rushikesh Gunjal | 2025-09-23 10:43 | Ok | 2025-09-24 08:40 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3327 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1300 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120020 | 120040 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-20 18:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-21 15:15 | Rushikesh Gunjal | 2025-09-23 11:20 | OK | 2025-09-24 08:40 | Brajesh Upadhyay | work has been done | 74.6917 | 20.334 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1301 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119930 | 119950 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-20 18:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-21 16:15 | Rushikesh Gunjal | 2025-09-23 11:18 | Ok | 2025-09-24 08:41 | Brajesh Upadhyay | work has been done | 74.6914 | 20.3336 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1293 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 120330 | 120360 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-19 18:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-20 15:30 | Kishori Lal | 2025-09-20 17:16 | Work done. | 2025-09-21 10:12 | Brajesh Upadhyay | work has been done | 74.6939 | 20.3363 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1302 | Checking Of Layout Marking, Excavation & Laying PCC For Toe Wall | 118870 | 119020 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-21 17:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-22 13:30 | Rushikesh Gunjal | 2025-09-23 10:38 | Work not done |  |  |  | 74.6895 | 20.3255 | Inspected | Inspected - Rejected - Work Not Done | 150 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1434 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120320 | 120340 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-16 18:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 17:00 | Rushikesh Gunjal | 2025-10-31 10:50 | Work was already done | 2025-10-31 20:03 | Brajesh Upadhyay | work has been done | 74.6924 | 20.3347 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1432 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120225 | 120250 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-16 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 17:10 | Rushikesh Gunjal | 2025-10-31 10:50 | Work was already done | 2025-10-31 20:04 | Brajesh Upadhyay | work has been done | 74.6924 | 20.3347 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1430 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120190 | 120230 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-16 18:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 17:30 | Rushikesh Gunjal | 2025-10-31 10:51 | Work was already done | 2025-10-31 20:04 | Brajesh Upadhyay | work has been done | 74.6924 | 20.3348 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1429 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119860 | 119880 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-16 18:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 10:00 | Rushikesh Gunjal | 2025-10-31 10:52 | Work was already done | 2025-10-31 20:04 | Brajesh Upadhyay | work has been done | 74.6924 | 20.3348 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2016 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134723 | 134750 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-03 17:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-04 13:00 | Rushikesh Gunjal | 2026-01-05 16:54 | Work already done | 2026-01-05 18:47 | Brajesh Upadhyay | work has been done | 74.758 | 20.4425 | Inspected | RFI Approved | 27 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1428 | Checking Of Shuttering & Laying PCC For Drain | 120140 | 120190 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-16 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 09:30 | Rushikesh Gunjal | 2025-10-31 10:52 | Work was already done | 2025-10-31 20:05 | Brajesh Upadhyay | work has been done | 74.6924 | 20.3348 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1427 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120230 | 120240 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-16 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 10:15 | Rushikesh Gunjal | 2025-10-31 10:53 | Work was already done | 2025-10-31 20:05 | Brajesh Upadhyay | work has been done | 74.6924 | 20.3348 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1426 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120280 | 120300 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-16 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:10 | Rushikesh Gunjal | 2025-10-31 10:54 | Work was already done | 2025-10-31 20:05 | Brajesh Upadhyay | work has been done | 74.6921 | 20.3344 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1304 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119790 | 119840 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-23 17:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-24 16:00 | Rushikesh Gunjal | 2025-09-25 11:19 | Work done | 2025-09-28 07:05 | Brajesh Upadhyay | work has been done | 74.6907 | 20.3323 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1303 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Wall | 120360 | 120400 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-23 17:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-24 11:30 | Rushikesh Gunjal | 2025-09-25 11:31 | Shuttering work not ready |  |  |  | 74.6939 | 20.3364 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1306 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 120300 | 120330 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-23 17:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-24 14:00 | Rushikesh Gunjal | 2025-02-06 18:18 | Laid the pcc | 2025-09-25 10:05 | Brajesh Upadhyay | work has been done | 74.6936 | 20.336 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1307 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120330 | 120360 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-23 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-24 15:00 | Rushikesh Gunjal | 2025-02-06 18:16 | Work not done |  |  |  | 74.6936 | 20.336 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1308 | Checking Of Layout Marking, Excavation & Laying PCC For Toe Wall | 118870 | 119020 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-23 17:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-24 10:50 | Rushikesh Gunjal | 2025-09-25 11:24 | Work done | 2025-09-28 07:06 | Brajesh Upadhyay | work has been done | 74.6894 | 20.3255 | Inspected | RFI Approved | 150 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1316 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119745 | 119785 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-27 18:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-28 14:00 | Kishori Lal | 2025-09-29 11:36 | Work done. | 2025-10-01 07:47 | Brajesh Upadhyay | work has been done | 74.6907 | 20.3319 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1310 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120330 | 120360 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-24 19:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-25 15:30 | Kishori Lal | 2025-09-29 12:08 | Not ready. |  |  |  | 74.6937 | 20.3362 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1309 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119740 | 119780 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-24 18:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-25 14:30 | Rushikesh Gunjal | 2025-09-25 11:08 | Work not done |  |  |  | 74.6907 | 20.332 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1311 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119740 | 119805 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-26 16:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-27 14:00 | Rushikesh Gunjal | 2025-09-27 15:37 | Work done | 2025-09-28 07:03 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3323 | Inspected | RFI Approved | 65 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1313 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 120020 | 120050 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-26 17:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-27 15:30 | Rushikesh Gunjal | 2025-09-27 15:33 | Work not done |  |  |  | 74.6918 | 20.3343 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1372 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119970 | 120050 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-11 16:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-12 16:30 | Rushikesh Gunjal | 2025-10-13 16:21 | Work done | 2025-10-13 16:48 | Brajesh Upadhyay | work has been done | 74.6914 | 20.3338 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1314 | Checking Of Reinforcement ,Shuttering & Pouring Concrete For Top Haunch With Bracket & Wall A1,A2 Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-26 17:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-27 16:00 | Kishori Lal | 2025-10-01 17:30 | Work done. | 2025-10-02 11:55 | Brajesh Upadhyay | work has been done | 74.7483 | 20.399 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1315 | Checking Of Reinforcement & Shuttering &Pouring Concrete for Mid Wall Final Lift With Top Haunch Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-27 18:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-28 15:30 | Kishori Lal | 2025-10-01 17:44 | Work done. | 2025-10-02 11:53 | Brajesh Upadhyay | work has been done | 74.7482 | 20.3991 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2020 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Wall A1,A2 First Lift Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-05 08:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-05 16:00 | Rushikesh Gunjal | 2026-01-05 17:59 | Work not done |  |  |  | 74.7076 | 20.3635 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1359 | Checking Of Laying PQC Top | 133210 | 133230 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 17:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 10:30 | Rushikesh Gunjal | 2025-10-14 12:21 | Work done | 2025-10-14 13:46 | Brajesh Upadhyay | work has been done | 74.6926 | 20.335 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2018 | Checking Of Layout Marking , Excavation & Laying PCC For Anchor Beam A1,A2 Of BC | 140928 | 140928 | LHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-04 17:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-05 14:00 | Rushikesh Gunjal | 2026-01-05 16:06 | Check found Satisfactory work | 2026-01-05 18:44 | Brajesh Upadhyay | work has been done | 74.7821 | 20.4922 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1699 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119890 | 119930 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-02 18:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-03 14:00 | Rushikesh Gunjal | 2025-11-05 10:55 | Work was already done | 2025-11-05 15:38 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3326 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2019 | Checking Of Reinforcement, shuttering and pouring concrete for Drain Slab | 134723 | 134750 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-04 18:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-05 15:00 | Rushikesh Gunjal | 2026-01-05 16:54 | Work already done | 2026-01-05 18:44 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4424 | Inspected | RFI Approved | 27 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1694 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall A1,A2 Raft of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-02 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-03 15:00 | Rushikesh Gunjal | 2025-11-04 17:15 | Work already done | 2025-11-05 15:39 | Brajesh Upadhyay | work has been done | 74.7828 | 20.4996 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1697 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 120280 | 120400 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-02 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-03 14:30 | Rushikesh Gunjal | 2025-11-05 10:57 | Work was already done | 2025-11-05 15:38 | Brajesh Upadhyay | work has been done | 74.6925 | 20.335 | Inspected | RFI Approved | 120 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1793 | Checking Of Shuttering & Laying PCC For Drain | 134570 | 134600 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 14:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 12:30 | Rushikesh Gunjal | 2025-12-03 15:01 | Work done | 2025-12-04 10:25 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.758 | 20.4422 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1809 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134520 | 134600 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 17:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 10:00 | Rushikesh Gunjal | 2025-12-03 15:04 | Work already done | 2025-12-04 10:26 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.758 | 20.4423 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1368 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119980 | 120000 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-11 16:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-12 10:30 | Rushikesh Gunjal | 2025-10-14 17:56 | Work done | 2025-10-14 17:59 | Brajesh Upadhyay | work has been done | 74.6907 | 20.3322 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1356 | Checking Of Level & FDD test for GSB Top Layer | 123791 | 123820 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 17:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 11:45 | Rushikesh Gunjal | 2025-10-13 18:17 | Work done | 2025-10-13 18:23 | Brajesh Upadhyay | work has been done | 74.6902 | 20.3306 | Inspected | RFI Approved | 29 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1373 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119900 | 119945 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-11 16:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-12 16:45 | Rushikesh Gunjal | 2025-10-13 16:19 | Work done | 2025-10-13 16:47 | Brajesh Upadhyay | work has been done | 74.6911 | 20.3332 | Inspected | RFI Approved | 45 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1375 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 119000 | 119714 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 14:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 14:55 | Rushikesh Gunjal | 2025-10-14 11:56 | Work done | 2025-10-14 13:45 | Brajesh Upadhyay | work has been done | 74.6894 | 20.3287 | Inspected | RFI Approved | 714 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1810 | Checking Of Layout Marking & Excavation for Drain | 134600 | 134740 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 17:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 11:30 | Rushikesh Gunjal | 2025-12-03 15:05 | Work already done | 2025-12-04 10:26 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7579 | 20.442 | Inspected | RFI Approved | 140 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1378 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 119000 | 119714 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 15:20 | Rushikesh Gunjal | 2025-10-14 11:54 | Work done | 2025-10-14 13:45 | Brajesh Upadhyay | work has been done | 74.6895 | 20.3287 | Inspected | RFI Approved | 714 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1377 | Checking Of Level & FDD test for GSB Top Layer | 129380 | 129693 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 14:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 15:10 | Rushikesh Gunjal | 2025-10-14 11:28 | Check found satisfactory result | 2025-10-14 13:45 | Brajesh Upadhyay | work has been done | 74.69 | 20.3301 | Inspected | RFI Approved | 313 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1380 | Checking Of Level & FDD test for GSB Top Layer | 129703 | 129800 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 15:40 | Rushikesh Gunjal | 2025-10-14 11:26 | Work done | 2025-10-14 13:44 | Brajesh Upadhyay | work has been done | 74.69 | 20.3301 | Inspected | RFI Approved | 97 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1381 | Checking Of Laying DLC Top | 123700 | 123781 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 15:50 | Rushikesh Gunjal | 2025-10-14 16:46 | Work done | 2025-10-14 17:03 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3313 | Inspected | RFI Approved | 81 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1383 | Checking Of Level & FDD test for GSB Top Layer | 118350 | 119000 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 16:00 | Rushikesh Gunjal | 2025-10-14 11:21 | Work done | 2025-10-14 13:44 | Brajesh Upadhyay | work has been done | 74.69 | 20.3301 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1384 | Checking Of Laying DLC Top | 123791 | 123870 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 16:10 | Rushikesh Gunjal | 2025-10-14 16:47 | Work done | 2025-10-14 17:03 | Brajesh Upadhyay | work has been done | 74.6905 | 20.3312 | Inspected | RFI Approved | 79 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1385 | Checking Of Laying PQC Top | 129703 | 129810 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 16:20 | Rushikesh Gunjal | 2025-10-15 13:07 | Work done | 2025-10-16 08:40 | Brajesh Upadhyay | work has been done | 74.699 | 20.3433 | Inspected | RFI Approved | 107 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1389 | Checking Of Laying PQC Top | 123700 | 123781 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 17:05 | Rushikesh Gunjal | 2025-10-14 12:17 | Work done | 2025-10-14 13:43 | Brajesh Upadhyay | work has been done | 74.6926 | 20.3351 | Inspected | RFI Approved | 81 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1388 | Checking Of Level & FDD test for GSB Top Layer | 117750 | 118350 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 16:55 | Rushikesh Gunjal | 2025-10-14 11:22 | Work done | 2025-10-14 13:43 | Brajesh Upadhyay | work has been done | 74.69 | 20.3301 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1395 | Checking Of Level & FDD test for GSB Top Layer | 117040 | 117750 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 17:55 | Rushikesh Gunjal | 2025-10-14 11:24 | Check found Satisfactory result | 2025-10-14 13:41 | Brajesh Upadhyay | work has been done | 74.69 | 20.3301 | Inspected | RFI Approved | 710 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1820 | Checking Of Layout Marking & Excavation For Drain | 135260 | 135340 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 18:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 14:00 | Rushikesh Gunjal | 2025-12-03 15:10 | Work already done | 2025-12-04 10:26 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7593 | 20.4469 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1396 | Checking Of Laying PQC Top | 118350 | 119000 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:00 | Rushikesh Gunjal | 2025-10-13 18:44 | Work done | 2025-10-14 13:41 | Brajesh Upadhyay | work has been done | 74.694 | 20.3366 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2025 | Checking Of Layout Marking , Excavation & Laying PCC For Approach Slab A1,A2 Of MNB | 129698 | 129698 | RHS | Bridge | Minor Bridge Reconstruction | Approaches | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-06 17:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-07 12:00 | Rushikesh Gunjal | 2026-01-07 15:21 | Wrong RFI i.e. mention Side is wrong |  |  |  | 74.7483 | 20.3991 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1398 | Checking Of Level & FDD test for GSB Top Layer | 140260 | 141000 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:15 | Rushikesh Gunjal | 2025-10-14 12:04 | Work done | 2025-10-14 13:40 | Brajesh Upadhyay | work has been done | 74.6894 | 20.3287 | Inspected | RFI Approved | 740 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1397 | Checking Of Laying DLC Top | 117050 | 117750 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:10 | Rushikesh Gunjal | 2025-10-14 16:42 | Check found satisfactory result | 2025-10-14 17:02 | Brajesh Upadhyay | work has been done | 74.6905 | 20.3312 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1400 | Checking Of Laying PQC Top | 117750 | 118350 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:30 | Rushikesh Gunjal | 2025-10-14 17:09 | Work done | 2025-10-14 17:24 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1401 | Checking Of Laying PQC Top | 129350 | 129693 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:40 | Rushikesh Gunjal | 2025-10-14 17:06 | Work done | 2025-10-14 17:23 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3326 | Inspected | RFI Approved | 343 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1402 | Checking Of Laying DLC Top | 129703 | 129800 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:30 | Rushikesh Gunjal | 2025-10-14 17:24 | Work done | 2025-10-14 17:24 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 97 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1403 | Checking Of Level & FDD test for GSB Top Layer | 141000 | 141740 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:40 | Rushikesh Gunjal | 2025-10-13 18:11 | Work done | 2025-10-14 08:15 | Brajesh Upadhyay | work has been done | 74.6902 | 20.3305 | Inspected | RFI Approved | 740 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1404 | Checking Of Laying DLC Top | 133210 | 133230 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:50 | Rushikesh Gunjal | 2025-10-14 17:25 | Work done | 2025-10-14 17:31 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1405 | Checking Of Laying PQC Top | 129703 | 129800 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:55 | Rushikesh Gunjal | 2025-10-14 17:04 | Work done | 2025-10-14 17:21 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 97 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1406 | Checking Of Laying PQC Top | 133210 | 133230 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:55 | Rushikesh Gunjal | 2025-10-14 12:23 | Work done | 2025-10-14 13:39 | Brajesh Upadhyay | work has been done | 74.6926 | 20.335 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1370 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120300 | 120330 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-11 16:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-12 15:00 | Rushikesh Gunjal | 2025-10-13 16:29 | Work done | 2025-10-13 16:48 | Brajesh Upadhyay | work has been done | 74.6936 | 20.3361 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1371 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119880 | 119945 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-11 16:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-12 16:00 | Rushikesh Gunjal | 2025-10-13 16:13 | Work done | 2025-10-13 16:52 | Brajesh Upadhyay | work has been done | 74.691 | 20.3331 | Inspected | RFI Approved | 65 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1369 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119860 | 119880 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-11 16:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-12 14:30 | Rushikesh Gunjal | 2025-10-13 16:09 | Work done | 2025-10-13 16:49 | Brajesh Upadhyay | work has been done | 74.691 | 20.3328 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1334 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120000 | 120030 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 15:45 | Kishori Lal | 2025-10-09 17:15 | Work done. | 2025-10-13 16:52 | Brajesh Upadhyay | work has been done | 74.6917 | 20.334 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1338 | Checking Of Laying PQC Top | 141400 | 141720 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 18:30 | Rushikesh Gunjal | 2025-10-09 16:00 | Work done | 2025-10-13 16:50 | Brajesh Upadhyay | work has been done | 74.7827 | 20.4976 | Inspected | RFI Approved | 320 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1823 | Checking Of Level & FDD test for Earthen Shoulder Top Layer | 140930 | 141690 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 17:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 09:00 | Rushikesh Gunjal | 2025-12-03 15:52 | Work done | 2025-12-04 10:27 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7823 | 20.4931 | Inspected | RFI Approved | 760 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1332 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120330 | 120360 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 15:15 | Kishori Lal | 2025-10-09 17:03 | Work done. | 2025-10-13 16:52 | Brajesh Upadhyay | work has been done | 74.6937 | 20.336 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1408 | Checking Of Laying PQC Top | 139790 | 139920 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 19:10 | Rushikesh Gunjal | 2025-10-14 17:20 | Work done | 2025-10-14 17:23 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 130 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1329 | Checking Of Level & FDD test for GSB Top Layer | 133200 | 133240 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 15:30 | Rushikesh Gunjal | 2025-10-09 16:58 | Check FDD and found satisfactory result | 2025-10-13 16:53 | Brajesh Upadhyay | work has been done | 74.6926 | 20.3349 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1323 | Checking Layout Marking , Excavation & Laying PCC For Drain | 119840 | 119945 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 10:10 | Kishori Lal | 2025-10-09 17:36 | Work done. | 2025-10-13 16:55 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3329 | Inspected | RFI Approved | 105 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1409 | Checking Of Laying DLC Top | 140800 | 141400 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 19:15 | Rushikesh Gunjal | 2025-10-14 17:30 | Work done | 2025-10-14 17:30 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1410 | Checking Of Laying PQC Top | 139920 | 140620 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 19:20 | Rushikesh Gunjal | 2025-10-14 17:16 | Work done | 2025-10-14 17:23 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1412 | Checking Of Laying PQC Top | 140620 | 141150 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 19:30 | Rushikesh Gunjal | 2025-10-14 17:13 | Work done | 2025-10-14 17:22 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 530 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1411 | Checking Of Laying DLC Top | 141400 | 141730 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 19:25 | Rushikesh Gunjal | 2025-10-14 17:28 | Work done | 2025-10-14 17:30 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 330 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1702 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119740 | 119770 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-03 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-04 11:00 | Rushikesh Gunjal | 2025-11-06 17:15 | Work already done | 2025-11-07 08:17 | Brajesh Upadhyay | work has been done | 74.6905 | 20.332 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1413 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Toe Wall Final Lift | 119060 | 119120 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 17:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 17:00 | Rushikesh Gunjal | 2025-10-14 17:46 | Work done | 2025-10-14 17:47 | Brajesh Upadhyay | work has been done | 74.6901 | 20.3263 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1414 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Toe Wall Final Lift | 118680 | 118770 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 17:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 17:30 | Rushikesh Gunjal | 2025-10-14 17:48 | Work done | 2025-10-14 17:48 | Brajesh Upadhyay | work has been done | 74.6901 | 20.3263 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1415 | Checking Of Laying PQC Top | 141150 | 141720 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 17:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:10 | Rushikesh Gunjal | 2025-10-14 17:34 | Work done | 2025-10-14 17:46 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 570 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1391 | Checking Of Laying DLC Top | 117750 | 118350 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 17:25 | Rushikesh Gunjal | 2025-10-14 16:41 | Check found Satisfactory result | 2025-10-14 17:02 | Brajesh Upadhyay | work has been done | 74.6905 | 20.3312 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1365 | Checking Of Laying DLC Top | 119000 | 119714 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 11:45 | Rushikesh Gunjal | 2025-10-14 16:38 | Work done | 2025-10-14 17:03 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 714 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1417 | Checking Reinforcement, shuttering and pouring concrete for Final Lift Of Toe Wall | 118650 | 118680 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 17:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 19:00 | Rushikesh Gunjal | 2025-10-14 17:43 | Work done | 2025-10-14 17:45 | Brajesh Upadhyay | work has been done | 74.6901 | 20.3262 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1418 | Checking Of Laying PQC Top | 117060 | 117750 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 17:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 19:15 | Rushikesh Gunjal | 2025-10-14 16:56 | Work done | 2025-10-14 17:02 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3311 | Inspected | RFI Approved | 690 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/01322 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120030 | 120050 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-29 18:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-30 15:15 | Kishori Lal | 2025-10-01 14:09 | Work done. | 2025-10-02 11:49 | Brajesh Upadhyay | work has been done | 74.6918 | 20.3341 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/01320 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120030 | 120050 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-27 18:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-28 16:30 | Kishori Lal | 2025-09-29 11:51 | Work done. | 2025-10-01 07:48 | Brajesh Upadhyay | work has been done | 74.6917 | 20.3342 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/01319 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120320 | 120330 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-27 18:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-28 15:30 | Kishori Lal | 2025-09-29 12:09 | Not ready. |  |  |  | 74.6937 | 20.3362 | Inspected | Inspected - Rejected - Work Not Done | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/01318 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 120020 | 120050 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-27 18:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-28 09:30 | Kishori Lal | 2025-09-29 11:48 | Work done. | 2025-10-01 07:48 | Brajesh Upadhyay | work has been done | 74.6919 | 20.3344 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1318 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119840 | 119860 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 15:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-08 16:20 | Kishori Lal | 2025-10-09 17:45 | Work done. | 2025-10-13 16:56 | Brajesh Upadhyay | work has been done | 74.6911 | 20.3329 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1319 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119840 | 119860 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 16:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 16:30 | Kishori Lal | 2025-10-09 17:46 | Work done. | 2025-10-13 16:56 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3326 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1399 | Checking Of Laying DLC Top | 129350 | 129693 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:20 | Rushikesh Gunjal | 2025-10-14 17:22 | Check found Satisfactory result | 2025-10-14 17:24 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 343 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1320 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119840 | 119860 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 16:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 16:45 | Kishori Lal | 2025-10-09 17:48 | Work done. | 2025-10-13 16:55 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3326 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1407 | Checking Of Laying DLC Top | 140250 | 140800 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 16:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 19:00 | Rushikesh Gunjal | 2025-10-14 17:26 | Work done | 2025-10-14 17:31 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1321 | Checking Of Reinforcement , Shuttering & Pouring concrete For Top Slab Of Minor Bridge | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 16:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 10:30 | Kishori Lal | 2025-10-09 13:28 | Work done. | 2025-10-13 16:55 | Brajesh Upadhyay | work has been done | 74.7484 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1392 | Checking Of Laying PQC Top | 123791 | 123840 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 17:30 | Rushikesh Gunjal | 2025-10-13 18:47 | Work done | 2025-10-14 08:16 | Brajesh Upadhyay | work has been done | 74.6939 | 20.3364 | Inspected | RFI Approved | 49 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1322 | Checking Layout Marking ,Excavation & Laying PCC For Drain | 119970 | 120020 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 10:00 | Kishori Lal | 2025-10-09 17:20 | Work done. | 2025-10-13 16:55 | Brajesh Upadhyay | work has been done | 74.6914 | 20.3338 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1324 | Checking Existing BT dismantling excavation up to embankment top, Level and FDD test after excavation | 141700 | 141750 | BHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 11:00 | Rushikesh Gunjal | 2025-10-09 15:54 | Work done | 2025-10-13 16:54 | Brajesh Upadhyay | work has been done | 74.7827 | 20.4976 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1393 | Checking Of Laying PQC Top | 119000 | 119714 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 17:40 | Rushikesh Gunjal | 2025-10-13 18:42 | Work done | 2025-10-14 13:42 | Brajesh Upadhyay | work has been done | 74.6941 | 20.3366 | Inspected | RFI Approved | 714 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1325 | Checking Layout Marking , Excavation & PCC For Drain | 120190 | 120230 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 11:00 | Kishori Lal | 2025-10-09 16:38 | Work done. | 2025-10-13 16:54 | Brajesh Upadhyay | work has been done | 74.6929 | 20.3353 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1422 | Checking Of Utility Pipe Laying | 138570 | 138570 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 18:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:50 | Rushikesh Gunjal | 2025-10-14 18:36 | Work done | 2025-10-14 18:37 | Brajesh Upadhyay | work has been done | 74.7584 | 20.434 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1421 | Checking Of Utility Pipe Laying | 138540 | 138540 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 18:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:45 | Rushikesh Gunjal | 2025-10-14 18:36 | Work done | 2025-10-14 18:38 | Brajesh Upadhyay | work has been done | 74.7584 | 20.4339 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1327 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119880 | 119945 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 12:30 | Kishori Lal | 2025-10-09 17:38 | Work done. | 2025-10-13 16:53 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3329 | Inspected | RFI Approved | 65 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1419 | Checking Of Utility Pipe Laying | 137200 | 137200 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 18:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:30 | Rushikesh Gunjal | 2025-10-14 18:35 | Work done | 2025-10-14 18:38 | Brajesh Upadhyay | work has been done | 74.7584 | 20.434 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1328 | Checking Of Level & FDD test for GSB Top Layer | 141690 | 141740 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 14:00 | Rushikesh Gunjal | 2025-10-09 17:00 | Work done | 2025-10-13 16:53 | Brajesh Upadhyay | work has been done | 74.6926 | 20.3349 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1326 | Checking Of Level & FDD Test For Subgrade Top | 141700 | 141750 | BHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 11:30 | Rushikesh Gunjal | 2025-10-09 15:56 | Work done | 2025-10-13 16:54 | Brajesh Upadhyay | work has been done | 74.7828 | 20.4976 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1420 | Checking Of Utility Pipe Laying | 138360 | 138360 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:35 | Rushikesh Gunjal | 2025-10-14 18:37 | Work done | 2025-10-14 18:38 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4339 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1333 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119000 | 119040 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 15:40 | Kishori Lal | 2025-10-09 17:51 | Wrong Chainage. |  |  |  | 74.6909 | 20.3326 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1387 | Checking Of Laying DLC Top | 118350 | 119000 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 16:40 | Rushikesh Gunjal | 2025-10-14 16:39 | Work done | 2025-10-14 17:03 | Brajesh Upadhyay | work has been done | 74.6904 | 20.3312 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1337 | Checking Of Laying DLC Top | 140250 | 140260 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 11:00 | Rushikesh Gunjal | 2025-10-09 15:51 | Work done | 2025-10-13 16:51 | Brajesh Upadhyay | work has been done | 74.7828 | 20.4976 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1336 | Checking Of Laying DLC Top | 141650 | 141730 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 08:30 | Rushikesh Gunjal | 2025-10-09 15:52 | Work done | 2025-10-13 16:51 | Brajesh Upadhyay | work has been done | 74.7828 | 20.4976 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1339 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119970 | 120050 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 16:30 | Kishori Lal | 2025-10-09 17:25 | Not ready. |  |  |  | 74.6916 | 20.3334 | Inspected | Inspected - Rejected - Work Not Done | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1343 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120360 | 120380 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 18:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 17:55 | Kishori Lal | 2025-10-09 16:05 | Work done. | 2025-10-13 16:50 | Brajesh Upadhyay | work has been done | 74.694 | 20.3365 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1340 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120320 | 120360 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 15:25 | Kishori Lal | 2025-10-09 16:11 | Not ready. |  |  |  | 74.6935 | 20.336 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1341 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120230 | 120240 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 09:30 | Kishori Lal | 2025-10-09 16:26 | Work done. | 2025-10-13 16:50 | Brajesh Upadhyay | work has been done | 74.6931 | 20.3354 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1342 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120320 | 120360 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 17:50 | Kishori Lal | 2025-10-09 16:14 | Repeat Chainage. |  |  |  | 74.6935 | 20.336 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1416 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Toe Wall Final Lift | 118770 | 118870 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 17:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 18:45 | Rushikesh Gunjal | 2025-10-14 17:45 | Work done | 2025-10-14 17:46 | Brajesh Upadhyay | work has been done | 74.6901 | 20.3263 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1344 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119970 | 119980 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 18:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 18:00 | Rushikesh Gunjal | 2025-10-11 10:16 | Work done | 2025-10-13 16:50 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3328 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1345 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119900 | 119935 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 18:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 18:00 | Kishori Lal | 2025-10-09 18:03 | Not ready. |  |  |  | 74.6912 | 20.3336 | Inspected | Inspected - Rejected - Work Not Done | 35 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1367 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Crash Barrier Of MNB | 129698 | 129698 | RHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 18:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 15:30 | Kishori Lal | 2025-10-13 17:50 | Work done. | 2025-10-13 18:17 | Brajesh Upadhyay | work has been done | 74.7483 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1358 | Checking Of Laying DLC Top | 129703 | 129780 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 17:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 15:00 | Rushikesh Gunjal | 2025-10-13 18:23 | Work done | 2025-10-14 13:46 | Brajesh Upadhyay | work has been done | 74.6903 | 20.3308 | Inspected | RFI Approved | 77 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1346 | Checking Of Laying DLC Top | 133210 | 133230 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 18:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 18:15 | Rushikesh Gunjal | 2025-10-09 15:31 | Check fdd and level and found satisfactory | 2025-10-13 16:50 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4289 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1360 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 117750 | 118350 | BHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 14:00 | Rushikesh Gunjal | 2025-10-13 17:36 | Work not | 2025-10-13 18:23 | Brajesh Upadhyay | work has been done | 74.6895 | 20.3284 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1350 | Checking Of Layout Marking Level & Excavation For Box culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 09:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 15:30 | Kishori Lal | 2025-10-09 12:50 | Work done. | 2025-10-13 16:49 | Brajesh Upadhyay | work has been done | 74.7822 | 20.4991 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1347 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 119000 | 119714 | BHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 14:30 | Rushikesh Gunjal | 2025-10-09 17:19 | RHS side BT dismentaling Work not done |  |  |  | 74.6907 | 20.3322 | Inspected | Inspected - Rejected - Work Not Done | 714 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1330 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Crash Barrier Of MNB | 129698 | 129698 | LHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 15:30 | Kishori Lal | 2025-10-13 17:49 | Work done. | 2025-10-13 18:31 | Brajesh Upadhyay | work has been done | 74.7484 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1335 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120330 | 120360 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 11:45 | Kishori Lal | 2025-10-09 17:05 | Repeat Chainage. |  |  |  | 74.6936 | 20.3361 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1824 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134520 | 134570 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 17:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 10:00 | Rushikesh Gunjal | 2025-12-03 15:00 | Work already done | 2025-12-04 10:27 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7579 | 20.4419 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1374 | Checking Of Shuttering & Laying PCC For Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-11 18:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-12 16:00 | Kishori Lal | 2025-10-13 18:23 | Work done. | 2025-10-14 08:18 | Brajesh Upadhyay | work has been done | 74.7829 | 20.4995 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1348 | Checking Of Level & FDD test for GSB Top Layer | 129703 | 129720 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 18:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 17:00 | Rushikesh Gunjal | 2025-10-09 17:02 | Work done | 2025-10-13 16:49 | Brajesh Upadhyay | work has been done | 74.6926 | 20.3349 | Inspected | RFI Approved | 17 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1331 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 119970 | 120020 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 17:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 14:45 | Kishori Lal | 2025-10-09 17:18 | Work done. | 2025-10-13 16:53 | Brajesh Upadhyay | work has been done | 74.6915 | 20.3338 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1351 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 118350 | 119000 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 17:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 11:30 | Rushikesh Gunjal | 2025-10-13 17:39 | Check found Satisfactory result | 2025-10-13 18:25 | Brajesh Upadhyay | work has been done | 74.6895 | 20.3284 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1352 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 118350 | 119000 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 17:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 11:45 | Rushikesh Gunjal | 2025-10-13 17:38 | Work done | 2025-10-13 18:25 | Brajesh Upadhyay | work has been done | 74.6895 | 20.3284 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1355 | Checking Of Level & FDD test for GSB Top Layer | 123720 | 123781 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 17:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 10:30 | Rushikesh Gunjal | 2025-10-13 18:16 | Work done | 2025-10-13 18:22 | Brajesh Upadhyay | work has been done | 74.6902 | 20.3305 | Inspected | RFI Approved | 61 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1354 | Checking Of Level & FDD test for GSB Top Layer | 129670 | 129693 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 17:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 09:30 | Rushikesh Gunjal | 2025-10-13 18:15 | Work done | 2025-10-13 18:27 | Brajesh Upadhyay | work has been done | 74.6902 | 20.3305 | Inspected | RFI Approved | 23 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1357 | Checking Of Laying DLC Top | 129660 | 129693 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 17:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 14:30 | Rushikesh Gunjal | 2025-10-14 16:44 | Work done | 2025-10-14 17:04 | Brajesh Upadhyay | work has been done | 74.6933 | 20.3322 | Inspected | RFI Approved | 33 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1361 | Checking Of Level & FDD test for GSB Top Layer | 119000 | 119714 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 17:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 11:00 | Rushikesh Gunjal | 2025-10-13 18:09 | Check found satisfactory result | 2025-10-13 18:24 | Brajesh Upadhyay | work has been done | 74.6902 | 20.3305 | Inspected | RFI Approved | 714 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1362 | Checking Of Laying DLC Top | 123710 | 123781 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 17:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 13:00 | Rushikesh Gunjal | 2025-10-13 18:21 | Work done | 2025-10-13 18:24 | Brajesh Upadhyay | work has been done | 74.6902 | 20.3308 | Inspected | RFI Approved | 71 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1364 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 117030 | 117750 | BHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 15:00 | Rushikesh Gunjal | 2025-10-13 17:55 | Work done | 2025-10-13 18:17 | Brajesh Upadhyay | work has been done | 74.6811 | 20.322 | Inspected | RFI Approved | 720 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1363 | Checking Of Laying DLC Top | 123791 | 123840 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 17:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 13:30 | Rushikesh Gunjal | 2025-10-13 18:22 | Work done | 2025-10-13 18:24 | Brajesh Upadhyay | work has been done | 74.6903 | 20.3308 | Inspected | RFI Approved | 49 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1366 | Checking Of Laying PQC Top | 129610 | 129693 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 17:30 | Rushikesh Gunjal | 2025-10-14 12:19 | Work done | 2025-10-14 13:45 | Brajesh Upadhyay | work has been done | 74.6926 | 20.335 | Inspected | RFI Approved | 83 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1808 | Checking Of Layout Marking , Excavation & Laying PCC For HPC | 121840 | 121840 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-01 17:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-02 11:00 | Rushikesh Gunjal | 2025-12-02 17:48 | Work already done | 2025-12-03 09:05 | Brajesh Upadhyay | work has been done | 74.6995 | 20.3481 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1825 | Checking Of Below Pipe PCC & Shuttering & Pouring Concrete Head Wall First Lift | 121840 | 121840 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 17:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 10:00 | Rushikesh Gunjal | 2025-12-03 11:37 | Work already done | 2025-12-04 10:27 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.6995 | 20.348 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1826 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 141700 | 141800 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 17:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 11:00 | Rushikesh Gunjal | 2025-12-03 15:53 | Work done | 2025-12-04 10:27 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7823 | 20.4931 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1827 | Checking Of Layout Marking & Excavation For Drain | 135050 | 135120 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 12:00 | Rushikesh Gunjal | 2025-12-03 15:11 | Work already done | 2025-12-04 10:27 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7593 | 20.4469 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1559 | Checking Of Laying DLC Top | 121020 | 121500 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 11:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 11:06 | Rushikesh Gunjal | 2025-10-28 12:08 | Work already done | 2025-10-28 18:38 | Brajesh Upadhyay | work has been done | 74.6995 | 20.348 | Inspected | RFI Approved | 480 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1560 | Checking Of Laying DLC Top | 129820 | 130250 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 11:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 11:07 | Rushikesh Gunjal | 2025-10-30 11:14 | Work was already done | 2025-10-30 11:30 | Brajesh Upadhyay | work has been done | 74.7508 | 20.4036 | Inspected | RFI Approved | 430 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1563 | Checking Of Laying PQC Top | 123150 | 123781 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 11:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 11:25 | Rushikesh Gunjal | 2025-10-18 15:09 | Work already done | 2025-10-18 19:19 | Brajesh Upadhyay | work has been done | 74.696 | 20.3382 | Inspected | RFI Approved | 631 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1564 | Checking Of Laying PQC Top | 123791 | 123980 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 11:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 11:26 | Rushikesh Gunjal | 2025-10-18 15:07 | Work already done | 2025-10-18 19:19 | Brajesh Upadhyay | work has been done | 74.6961 | 20.3382 | Inspected | RFI Approved | 189 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1561 | Checking Of Laying DLC Top | 130250 | 130870 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 11:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 11:09 | Rushikesh Gunjal | 2025-10-30 11:41 | Work already done | 2025-10-31 07:54 | Brajesh Upadhyay | work has been done | 74.7528 | 20.4086 | Inspected | RFI Approved | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1565 | Checking Of Laying PQC Top | 127670 | 127950 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 11:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 11:27 | Rushikesh Gunjal | 2025-10-18 15:06 | Work already done | 2025-10-18 19:20 | Brajesh Upadhyay | work has been done | 74.6961 | 20.3382 | Inspected | RFI Approved | 280 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1570 | Checking Reinforcement, shuttering and pouring concrete for retaining Wall Final Lift | 132910 | 133030 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 12:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 11:59 | Rushikesh Gunjal | 2025-10-30 15:12 | Work already done | 2025-10-31 07:53 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4265 | Inspected | RFI Approved | 120 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1828 | Checking Of Layout Marking , Excavation & Laying Head Wall PCC For HPC | 121908 | 121908 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 13:00 | Rushikesh Gunjal | 2025-12-03 11:38 | Work already done | 2025-12-04 10:28 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.6995 | 20.348 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1469 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 125200 | 125500 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:29 | Rushikesh Gunjal | 2025-10-29 15:33 | Work already done | 2025-10-30 11:32 | Brajesh Upadhyay | work has been done | 74.7171 | 20.3736 | Inspected | RFI Approved | 300 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1830 | Checking Of Shuttering & Laying PCC For Drain | 134700 | 134740 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 17:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 14:00 | Rushikesh Gunjal | 2025-12-03 15:02 | Work already done | 2025-12-04 10:28 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.758 | 20.4422 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2031 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Anchor Beam A1,A2 Casting Of BC | 133216 | 133216 | LHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-10 16:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-11 17:00 | Rushikesh Gunjal | 2026-01-12 16:32 | Work done | 2026-01-13 09:09 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4288 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2030 | Checking Of Layout Marking , Excavation & Laying Anchor Beam A1,A2 PCC Of BC | 133216 | 133216 | LHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-09 18:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-10 16:00 | Rushikesh Gunjal | 2026-01-12 16:30 | Work already done | 2026-01-13 09:11 | Brajesh Upadhyay | work has been done | 74.7582 | 20.4288 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1832 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Retaining Wall A1,A2 1st Lift Of Box Culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 18:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 14:00 | Rushikesh Gunjal | 2025-12-03 15:36 | Work done | 2025-12-04 10:28 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.782 | 20.4923 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1703 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120230 | 120280 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-03 18:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-04 14:00 | Rushikesh Gunjal | 2025-11-04 14:09 | Work Done | 2025-11-05 15:37 | Brajesh Upadhyay | work has been done | 74.6926 | 20.3351 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1704 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall A1,A2 1st Lift Of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-04 16:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-05 15:00 | Kishori Lal | 2025-11-13 13:40 | Work done. | 2025-11-13 20:08 | Brajesh Upadhyay | work has been done | 74.7827 | 20.4995 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1424 | Checking pouring concrete for Raft Of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-15 18:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-16 16:30 | Rushikesh Gunjal | 2025-11-04 17:04 | Work already done | 2025-11-05 15:39 | Brajesh Upadhyay | work has been done | 74.7827 | 20.4996 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1693 | Checking of layout Marking, Excavation & Laying PCC For Retaining Wall A1,A2 of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-01 17:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-02 11:00 | Rushikesh Gunjal | 2025-11-04 17:08 | Work done | 2025-11-05 15:39 | Brajesh Upadhyay | work has been done | 74.7826 | 20.4996 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1433 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119860 | 119900 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-16 18:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 18:00 | Rushikesh Gunjal | 2025-10-31 10:47 | Work was already done | 2025-10-31 20:03 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3329 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1431 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120290 | 120360 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-16 18:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 17:45 | Rushikesh Gunjal | 2025-10-31 10:51 | Work was already done | 2025-10-31 20:04 | Brajesh Upadhyay | work has been done | 74.6924 | 20.3347 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1721 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120140 | 120320 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-06 18:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-07 09:30 | Kishori Lal | 2025-11-13 16:14 | Wrong RFI. |  |  |  | 74.6931 | 20.3356 | Inspected | Inspected - Rejected - Work Not Done | 180 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1717 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119970 | 119980 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-06 18:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-07 15:00 | Kishori Lal | 2025-11-13 16:44 | Work already done. | 2025-11-13 20:05 | Brajesh Upadhyay | work has been done | 74.6916 | 20.3339 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1720 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120080 | 120100 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-06 18:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-07 11:00 | Kishori Lal | 2025-11-13 16:24 | Work already done. | 2025-11-13 20:04 | Brajesh Upadhyay | work has been done | 74.6922 | 20.3344 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1716 | Checking Of Layout Marking, Excavation & Laying PCC For Drain | 120070 | 120080 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-06 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-07 15:30 | Kishori Lal | 2025-11-13 16:23 | Work done. | 2025-11-13 20:05 | Brajesh Upadhyay | work has been done | 74.6922 | 20.3344 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1715 | Checking Of Reinforcement ,Shuttering & pouring Concrete For Retaining Wall A1,A2 Second Lift of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-06 18:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-07 14:30 | Kishori Lal | 2025-11-13 13:43 | Work done. | 2025-11-13 20:05 | Brajesh Upadhyay | work has been done | 74.7827 | 20.4995 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1695 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 119740 | 119770 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-02 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-03 11:00 | Rushikesh Gunjal | 2025-11-06 17:17 | Work already done | 2025-11-07 08:17 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3326 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1436 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 121500 | 121600 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 10:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 10:53 | Rushikesh Gunjal | 2025-10-28 11:53 | Work was already done | 2025-10-28 18:56 | Brajesh Upadhyay | work has been done | 74.6984 | 20.3413 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1435 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 121020 | 121500 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 10:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 10:51 | Rushikesh Gunjal | 2025-10-28 11:52 | Work was already done | 2025-10-28 18:56 | Brajesh Upadhyay | work has been done | 74.6984 | 20.3413 | Inspected | RFI Approved | 480 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1449 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 127850 | 128440 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:07 | Rushikesh Gunjal | 2025-10-28 15:15 | Work already done | 2025-10-28 18:49 | Brajesh Upadhyay | work has been done | 74.7328 | 20.3873 | Inspected | RFI Approved | 590 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1450 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 128440 | 128900 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:08 | Rushikesh Gunjal | 2025-10-28 15:16 | Work already done | 2025-10-28 18:49 | Brajesh Upadhyay | work has been done | 74.7328 | 20.3873 | Inspected | RFI Approved | 460 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1454 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 130700 | 131000 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:12 | Rushikesh Gunjal | 2025-10-30 11:28 | Work was already done | 2025-10-30 11:32 | Brajesh Upadhyay | work has been done | 74.7528 | 20.4086 | Inspected | RFI Approved | 300 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1452 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 129800 | 130300 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:10 | Rushikesh Gunjal | 2025-10-28 15:47 | Work already done | 2025-10-28 18:49 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1451 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 128900 | 129400 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:08 | Rushikesh Gunjal | 2025-10-28 15:36 | Work already done | 2025-10-28 18:49 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1453 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 130300 | 130700 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:11 | Rushikesh Gunjal | 2025-10-28 15:52 | Work already done | 2025-10-28 18:48 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1459 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 133250 | 133550 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:16 | Rushikesh Gunjal | 2025-10-30 16:06 | Work was already done | 2025-10-31 08:05 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4252 | Inspected | RFI Approved | 300 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1458 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 132550 | 133180 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:15 | Rushikesh Gunjal | 2025-10-30 16:06 | Work was already done | 2025-10-31 08:05 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4252 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1457 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 132000 | 132550 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:14 | Rushikesh Gunjal | 2025-10-30 16:20 | Work was already done | 2025-10-31 08:06 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1456 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 131500 | 132000 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:13 | Rushikesh Gunjal | 2025-10-30 16:19 | Work was already done | 2025-10-31 08:06 | Brajesh Upadhyay | work has been done | 74.754 | 20.4114 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1455 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 131000 | 131500 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:12 | Rushikesh Gunjal | 2025-10-30 16:29 | Work was already done | 2025-10-31 08:06 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1470 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 125500 | 126000 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:30 | Rushikesh Gunjal | 2025-10-28 15:58 | Work already done | 2025-10-28 18:48 | Brajesh Upadhyay | work has been done | 74.7248 | 20.3817 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1465 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 122000 | 123150 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:23 | Rushikesh Gunjal | 2025-10-28 12:30 | Work was already done | 2025-10-28 18:48 | Brajesh Upadhyay | work has been done | 74.7034 | 20.3548 | Inspected | RFI Approved | 1150 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1833 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall A1,A2 Final Lift Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 15:00 | Rushikesh Gunjal | 2025-12-03 16:45 | Work done | 2025-12-04 10:28 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7484 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1468 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 124500 | 125200 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:28 | Rushikesh Gunjal | 2025-10-30 17:01 | Work was already done | 2025-10-31 08:04 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1467 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 123850 | 124500 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:25 | Rushikesh Gunjal | 2025-10-30 17:00 | Work was already done | 2025-10-31 08:04 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1466 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 123150 | 123750 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:24 | Rushikesh Gunjal | 2025-10-30 16:55 | Work was already done | 2025-10-31 08:05 | Brajesh Upadhyay | work has been done | 74.7382 | 20.3911 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1477 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 128440 | 128900 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:36 | Rushikesh Gunjal | 2025-10-28 15:38 | Work was already done | 2025-10-28 18:46 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 460 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1478 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 128900 | 129400 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:37 | Rushikesh Gunjal | 2025-10-28 15:38 | Work was already done | 2025-10-28 18:46 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1476 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 128000 | 128440 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:36 | Rushikesh Gunjal | 2025-10-28 15:37 | Work was already done | 2025-10-28 18:46 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 440 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1474 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 127300 | 127700 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:34 | Rushikesh Gunjal | 2025-10-28 15:17 | Work already done | 2025-10-28 18:47 | Brajesh Upadhyay | work has been done | 74.7328 | 20.3873 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1487 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 134000 | 134490 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:47 | Rushikesh Gunjal | 2025-10-30 15:59 | Work was already done | 2025-10-31 08:03 | Brajesh Upadhyay | work has been done | 74.7587 | 20.437 | Inspected | RFI Approved | 490 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1479 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 129800 | 130300 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:39 | Rushikesh Gunjal | 2025-10-30 11:12 | Work was already done | 2025-10-30 11:32 | Brajesh Upadhyay | work has been done | 74.7508 | 20.4037 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1484 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 132600 | 133180 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:43 | Rushikesh Gunjal | 2025-10-30 16:07 | Work was already done | 2025-10-31 08:04 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4252 | Inspected | RFI Approved | 580 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1481 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 130800 | 131450 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:41 | Rushikesh Gunjal | 2025-10-30 11:30 | Work was already done | 2025-10-30 11:31 | Brajesh Upadhyay | work has been done | 74.7527 | 20.4087 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1480 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 130300 | 130800 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:40 | Rushikesh Gunjal | 2025-10-30 11:29 | Work was already done | 2025-10-30 11:32 | Brajesh Upadhyay | work has been done | 74.7528 | 20.4086 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1834 | Checking Of Below Pipe PCC & Shuttering & Pouring Concrete Head Wall First Lift | 124418 | 124418 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 16:00 | Rushikesh Gunjal | 2025-12-03 11:47 | Work already done | 2025-12-04 10:29 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7109 | 20.3682 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1543 | Checking Of Level & FDD Test For GSB Top | 127850 | 128400 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 14:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 14:16 | Rushikesh Gunjal | 2025-10-28 15:27 | Work was already done | 2025-10-28 18:39 | Brajesh Upadhyay | work has been done | 74.7327 | 20.3872 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1550 | Checking Of Level & FDD Test For GSB Top | 132600 | 132950 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 14:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 14:28 | Rushikesh Gunjal | 2025-10-30 16:26 | Work was already done | 2025-10-31 07:54 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 350 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1836 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 129590 | 129650 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 13:00 | Rushikesh Gunjal | 2025-12-03 16:49 | Work done | 2025-12-04 10:29 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7478 | 20.3985 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1548 | Checking Of Level & FDD Test For GSB Top | 131450 | 132000 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 14:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 14:26 | Rushikesh Gunjal | 2025-10-30 16:25 | Work was already done | 2025-10-31 07:55 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1551 | Checking Of Layout Marking , Excavation & Laying PCC For HPC | 117008 | 117008 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 08:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 12:30 | Rushikesh Gunjal | 2025-10-28 11:31 | Work done | 2025-10-28 18:38 | Brajesh Upadhyay | work has been done | 74.6729 | 20.3179 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1705 | Checking Of Shuttering & Pouring Concrete Head Wall First Lift & Below Pipe PCC | 120400 | 120400 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-05 10:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-05 14:00 | Kishori Lal | 2025-11-13 15:41 | Work done | 2025-11-13 20:07 | Brajesh Upadhyay | work has been done | 74.6942 | 20.3366 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1554 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 135890 | 136360 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 10:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 10:21 | Rushikesh Gunjal | 2025-10-30 15:40 | Work was already done | 2025-10-31 07:54 | Brajesh Upadhyay | work has been done | 74.7612 | 20.4519 | Inspected | RFI Approved | 470 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1558 | Checking Of Level & FDD Test For GSB Top | 137990 | 138580 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 10:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 10:40 | Rushikesh Gunjal | 2025-10-30 15:41 | Work was already done | 2025-10-31 07:54 | Brajesh Upadhyay | work has been done | 74.7612 | 20.4519 | Inspected | RFI Approved | 590 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1552 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 139350 | 139950 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 10:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 10:07 | Rushikesh Gunjal | 2025-10-27 15:23 | Work already done | 2025-10-28 08:27 | Brajesh Upadhyay | work has been done | 74.7819 | 20.4915 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1553 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 134960 | 135890 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 10:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 10:16 | Rushikesh Gunjal | 2025-10-30 15:44 | Work already done | 2025-10-31 07:54 | Brajesh Upadhyay | work has been done | 74.7596 | 20.4477 | Inspected | RFI Approved | 930 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1555 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 137150 | 137900 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 10:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 10:22 | Rushikesh Gunjal | 2025-10-30 15:40 | Work was already done | 2025-10-31 07:54 | Brajesh Upadhyay | work has been done | 74.7612 | 20.4519 | Inspected | RFI Approved | 750 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1556 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 139950 | 140680 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 10:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 10:24 | Rushikesh Gunjal | 2025-10-27 15:19 | Work already done | 2025-10-28 08:27 | Brajesh Upadhyay | work has been done | 74.7819 | 20.4915 | Inspected | RFI Approved | 730 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1571 | Checking Reinforcement, shuttering and pouring concrete for retaining Wall Final Lift | 140450 | 140595 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 12:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 12:00 | Rushikesh Gunjal | 2025-10-27 15:09 | Work already done | 2025-10-28 08:27 | Brajesh Upadhyay | work has been done | 74.7812 | 20.489 | Inspected | RFI Approved | 145 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1569 | Checking Reinforcement, shuttering and pouring concrete for retaining Wall Final Lift | 130080 | 130140 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 11:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 11:58 | Rushikesh Gunjal | 2025-10-30 15:13 | Work already done | 2025-10-31 07:53 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4265 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1544 | Checking Of Level & FDD Test For GSB Top | 128400 | 128950 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 14:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 14:17 | Rushikesh Gunjal | 2025-10-28 15:43 | Work was already done | 2025-10-28 18:38 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1568 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Retaining Wall Final Lift | 130040 | 130080 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 11:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 11:56 | Rushikesh Gunjal | 2025-10-30 15:08 | Work already done | 2025-10-31 07:53 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4265 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1566 | Checking Shuttering and pouring concrete for Head Wall final lift. | 135020 | 135020 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 11:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 11:28 | Rushikesh Gunjal | 2025-10-30 15:48 | Work already done | 2025-10-31 07:53 | Brajesh Upadhyay | work has been done | 74.7594 | 20.4469 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1546 | Checking Of Level & FDD Test For GSB Top | 130800 | 131000 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 14:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 14:24 | Rushikesh Gunjal | 2025-10-30 16:30 | Work was already done | 2025-10-31 07:55 | Brajesh Upadhyay | work has been done | 74.754 | 20.4114 | Inspected | RFI Approved | 200 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1545 | Checking Of Level & FDD Test For GSB Top | 128950 | 129380 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 14:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 14:18 | Rushikesh Gunjal | 2025-10-28 15:44 | Work already done | 2025-10-28 18:38 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 430 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1549 | Checking Of Level & FDD Test For GSB Top | 132000 | 132600 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 14:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 14:27 | Rushikesh Gunjal | 2025-10-30 16:25 | Work was already done | 2025-10-31 07:55 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1547 | Checking Of Level & FDD Test For GSB Top | 131000 | 131450 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 14:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 14:25 | Rushikesh Gunjal | 2025-10-30 16:31 | Work was already done | 2025-10-31 07:55 | Brajesh Upadhyay | work has been done | 74.754 | 20.4114 | Inspected | RFI Approved | 450 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1538 | Checking Of Level & FDD Test For GSB Top | 124700 | 125500 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 13:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 13:03 | Rushikesh Gunjal | 2025-10-30 16:59 | Work was already done | 2025-10-31 07:56 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 800 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1537 | Checking Of Level & FDD Test For GSB Top | 123870 | 124700 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 13:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 13:02 | Rushikesh Gunjal | 2025-10-30 17:02 | Work was already done | 2025-10-31 07:56 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 830 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1536 | Checking Of Level & FDD Test For GSB Top | 123150 | 123700 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 13:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 13:01 | Rushikesh Gunjal | 2025-10-30 17:00 | Work was already done | 2025-10-31 07:56 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1572 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134780 | 134820 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 15:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 15:02 | Rushikesh Gunjal | 2025-10-27 15:49 | Work already done | 2025-10-28 08:27 | Brajesh Upadhyay | work has been done | 74.758 | 20.4427 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1562 | Checking Of Laying PQC Top | 122500 | 123150 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 11:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 11:24 | Rushikesh Gunjal | 2025-10-18 15:08 | Work done | 2025-10-18 19:18 | Brajesh Upadhyay | work has been done | 74.696 | 20.3382 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1573 | Checking Reinforcement & pouring concrete for box culvert bottom hunch | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 17:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 12:30 | Rushikesh Gunjal | 2025-10-27 15:34 | Work already done | 2025-10-28 08:26 | Brajesh Upadhyay | work has been done | 74.7827 | 20.4996 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1574 | Checking Of shuttering & pouring concrete for head wall 01st lift of HPC | 117008 | 117008 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 17:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 12:40 | Rushikesh Gunjal | 2025-10-28 11:30 | Work done | 2025-10-28 18:37 | Brajesh Upadhyay | work has been done | 74.6729 | 20.3179 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1567 | Checking shuttering and pouring concrete for Head Wall final lift | 128318 | 128318 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 11:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 11:50 | Rushikesh Gunjal | 2025-10-30 16:41 | Work was already done | 2025-10-31 07:53 | Brajesh Upadhyay | work has been done | 74.7382 | 20.3912 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1471 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 126000 | 126440 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:31 | Rushikesh Gunjal | 2025-10-28 12:56 | Work already done | 2025-10-28 18:48 | Brajesh Upadhyay | work has been done | 74.7204 | 20.3757 | Inspected | RFI Approved | 440 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1472 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 126440 | 126900 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:32 | Rushikesh Gunjal | 2025-10-28 15:59 | Work was already done | 2025-10-28 18:47 | Brajesh Upadhyay | work has been done | 74.7247 | 20.3817 | Inspected | RFI Approved | 460 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1486 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 133550 | 134000 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:46 | Rushikesh Gunjal | 2025-10-30 15:58 | Work was already done | 2025-10-31 08:04 | Brajesh Upadhyay | work has been done | 74.7587 | 20.437 | Inspected | RFI Approved | 450 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1485 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 133250 | 133550 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:45 | Rushikesh Gunjal | 2025-10-30 16:08 | Work was already done | 2025-10-31 08:04 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4252 | Inspected | RFI Approved | 300 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1483 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 132000 | 132600 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:42 | Rushikesh Gunjal | 2025-10-30 16:22 | Work was already done | 2025-10-31 08:04 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1482 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 131450 | 132000 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:41 | Rushikesh Gunjal | 2025-10-30 16:21 | Work was already done | 2025-10-31 08:04 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1475 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 127700 | 128000 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:35 | Rushikesh Gunjal | 2025-10-28 15:18 | Work already done | 2025-10-28 18:46 | Brajesh Upadhyay | work has been done | 74.7327 | 20.3873 | Inspected | RFI Approved | 300 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1464 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 121950 | 122000 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:22 | Rushikesh Gunjal | 2025-10-28 12:14 | Work was already done | 2025-10-28 18:48 | Brajesh Upadhyay | work has been done | 74.6995 | 20.348 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1463 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 121450 | 121950 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:21 | Rushikesh Gunjal | 2025-10-28 12:13 | Work was already done | 2025-10-28 18:48 | Brajesh Upadhyay | work has been done | 74.6995 | 20.348 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1438 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 122000 | 122800 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 10:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 10:56 | Rushikesh Gunjal | 2025-10-28 12:22 | Work was already done | 2025-10-28 18:55 | Brajesh Upadhyay | work has been done | 74.7026 | 20.3533 | Inspected | RFI Approved | 800 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1462 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 121020 | 121450 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:20 | Rushikesh Gunjal | 2025-10-30 16:53 | Work was already done | 2025-10-31 08:05 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 430 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1460 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 133550 | 134000 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:17 | Rushikesh Gunjal | 2025-10-30 15:57 | Work already done | 2025-10-31 08:05 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4372 | Inspected | RFI Approved | 450 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1423 | Checking Of Reinforcement & Shuttering For Raft Of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-15 08:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-15 17:30 | Kishori Lal | 2025-10-18 11:55 | Checking of Reinforcement and Shuttering found satisfactory. | 2025-10-18 19:54 | Brajesh Upadhyay | work has been done | 74.7828 | 20.4995 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1446 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 126080 | 126600 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:04 | Rushikesh Gunjal | 2025-10-28 12:58 | Work already done | 2025-10-28 18:54 | Brajesh Upadhyay | work has been done | 74.721 | 20.3767 | Inspected | RFI Approved | 520 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1445 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 125500 | 126080 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:04 | Rushikesh Gunjal | 2025-10-28 15:50 | Work already done | 2025-10-28 18:54 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 580 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1444 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 125100 | 125500 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:03 | Rushikesh Gunjal | 2025-10-28 12:54 | Work already done | 2025-10-28 18:54 | Brajesh Upadhyay | work has been done | 74.715 | 20.3724 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1443 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 124700 | 125100 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:02 | Rushikesh Gunjal | 2025-10-28 12:52 | Work was already done | 2025-10-28 18:55 | Brajesh Upadhyay | work has been done | 74.7103 | 20.3675 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1441 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 123150 | 123750 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 10:59 | Rushikesh Gunjal | 2025-10-28 12:40 | Work was already done | 2025-10-28 18:55 | Brajesh Upadhyay | work has been done | 74.7071 | 20.3607 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1440 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 123000 | 123150 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 10:58 | Rushikesh Gunjal | 2025-10-28 15:48 | Work was already done | 2025-10-28 18:55 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 150 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1447 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 126600 | 127200 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:05 | Rushikesh Gunjal | 2025-10-30 16:47 | Work was already done | 2025-10-31 08:06 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1448 | Checking Of Exiting BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 127200 | 127850 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 11:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 11:06 | Rushikesh Gunjal | 2025-10-28 15:14 | Work was already done | 2025-10-28 18:49 | Brajesh Upadhyay | work has been done | 74.7327 | 20.3872 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1585 | Checking Of Laying DLC Top | 131310 | 131730 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:39 | Rushikesh Gunjal | 2025-10-30 16:32 | Work was already done | 2025-10-31 07:52 | Brajesh Upadhyay | work has been done | 74.7539 | 20.4114 | Inspected | RFI Approved | 420 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1602 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 120737 | 120737 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:23 | Rushikesh Gunjal | 2025-10-30 16:45 | Work was already done | 2025-10-31 07:49 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1601 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 120723 | 120723 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:21 | Rushikesh Gunjal | 2025-10-30 16:42 | Work was already done | 2025-10-31 07:50 | Brajesh Upadhyay | work has been done | 74.7382 | 20.3912 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1611 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 135178 | 135178 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:32 | Rushikesh Gunjal | 2025-10-30 15:47 | Work was already done | 2025-10-31 07:47 | Brajesh Upadhyay | work has been done | 74.7594 | 20.4469 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1610 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 138728 | 138728 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:31 | Rushikesh Gunjal | 2025-10-30 16:41 | Work was already done | 2025-10-31 07:47 | Brajesh Upadhyay | work has been done | 74.7382 | 20.3912 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1609 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 124043 | 124043 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:30 | Rushikesh Gunjal | 2025-10-30 16:44 | Work was already done | 2025-10-31 07:48 | Brajesh Upadhyay | work has been done | 74.7382 | 20.3912 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1621 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134980 | 135030 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:51 | Rushikesh Gunjal | 2025-10-27 15:52 | Work already done | 2025-10-28 08:17 | Brajesh Upadhyay | work has been done | 74.758 | 20.4426 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1625 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134520 | 134560 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:54 | Rushikesh Gunjal | 2025-10-27 15:56 | Work already done | 2025-10-28 08:17 | Brajesh Upadhyay | work has been done | 74.758 | 20.4426 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1623 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134700 | 134740 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:53 | Rushikesh Gunjal | 2025-10-27 15:54 | Work already done | 2025-10-28 08:17 | Brajesh Upadhyay | work has been done | 74.758 | 20.4426 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1626 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134710 | 134750 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:55 | Rushikesh Gunjal | 2025-10-27 15:57 | Work already done | 2025-10-28 08:24 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4426 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1624 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135210 | 135260 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:53 | Rushikesh Gunjal | 2025-10-27 15:55 | Work already done | 2025-10-28 08:24 | Brajesh Upadhyay | work has been done | 74.758 | 20.4426 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1622 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135170 | 135210 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:52 | Rushikesh Gunjal | 2025-10-27 15:53 | Work already done | 2025-10-28 08:25 | Brajesh Upadhyay | work has been done | 74.758 | 20.4426 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1636 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134600 | 134650 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 16:03 | Rushikesh Gunjal | 2025-10-27 16:08 | Work already done | 2025-10-28 08:14 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4425 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1634 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134650 | 134700 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 16:02 | Rushikesh Gunjal | 2025-10-27 16:06 | Work already done | 2025-10-28 08:14 | Brajesh Upadhyay | work has been done | 74.758 | 20.4423 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1656 | Checking Of Laying PQC Top | 131260 | 131830 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 17:10 | Rushikesh Gunjal | 2025-10-27 14:47 | Work already done | 2025-10-28 08:22 | Brajesh Upadhyay | work has been done | 74.7557 | 20.4169 | Inspected | RFI Approved | 570 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1635 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134780 | 134820 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 16:02 | Rushikesh Gunjal | 2025-10-27 16:07 | Work already done | 2025-10-28 08:23 | Brajesh Upadhyay | work has been done | 74.758 | 20.4423 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1659 | Checking Reinforcement, shuttering and pouring concrete for Final Lift Of Retaining Wall | 132630 | 132710 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 17:17 | Rushikesh Gunjal | 2025-10-30 15:07 | Work was already done | 2025-10-31 07:43 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4265 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1649 | Checking Of Laying DLC Top | 138480 | 139150 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 16:42 | Rushikesh Gunjal | 2025-10-27 15:43 | Work already done | 2025-10-28 08:19 | Brajesh Upadhyay | work has been done | 74.7727 | 20.4761 | Inspected | RFI Approved | 670 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1661 | Checking Reinforcement, shuttering and pouring concrete for Final Lift Of Retaining Wall | 140600 | 140650 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 17:20 | Rushikesh Gunjal | 2025-10-27 15:14 | Work already done | 2025-10-28 08:22 | Brajesh Upadhyay | work has been done | 74.7812 | 20.489 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1657 | Checking Of Laying PQC Top | 131830 | 132500 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 17:11 | Rushikesh Gunjal | 2025-10-27 14:48 | Work already done | 2025-10-28 08:22 | Brajesh Upadhyay | work has been done | 74.7573 | 20.4194 | Inspected | RFI Approved | 670 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1664 | Checking Existing BT dismantling excavation up to embankment top, Level and FDD test after excavation | 119750 | 120400 | BHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 17:30 | Rushikesh Gunjal | 2025-10-30 16:56 | Work was already done | 2025-10-31 07:42 | Brajesh Upadhyay | work has been done | 74.7382 | 20.3912 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1662 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120280 | 120380 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 17:26 | Rushikesh Gunjal | 2025-10-30 19:46 | Work already done | 2025-10-31 07:43 | Brajesh Upadhyay | work has been done | 74.6938 | 20.3361 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1660 | Checking Reinforcement, shuttering and pouring concrete for Final Lift Of Retaining Wall | 132910 | 132970 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 17:19 | Rushikesh Gunjal | 2025-10-30 15:06 | Work already done | 2025-10-31 07:43 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4265 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1658 | Checking Of Laying PQC Top | 132500 | 132840 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 17:12 | Rushikesh Gunjal | 2025-10-30 16:19 | Work done | 2025-10-31 07:43 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 340 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1648 | Checking Of Laying DLC Top | 136320 | 137060 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 16:41 | Rushikesh Gunjal | 2025-10-30 15:39 | Work already done | 2025-10-31 07:44 | Brajesh Upadhyay | work has been done | 74.7612 | 20.4519 | Inspected | RFI Approved | 740 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1663 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134700 | 134710 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 17:27 | Rushikesh Gunjal | 2025-10-31 10:48 | Work was already done | 2025-10-31 20:03 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3329 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1650 | Checking Of Laying DLC Top | 139150 | 140250 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 16:43 | Rushikesh Gunjal | 2025-10-27 15:20 | Work already done | 2025-10-28 08:19 | Brajesh Upadhyay | work has been done | 74.7819 | 20.4915 | Inspected | RFI Approved | 1100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1652 | Checking Of Laying PQC Top | 135340 | 135680 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 17:00 | Rushikesh Gunjal | 2025-10-27 14:57 | Work already done | 2025-10-28 08:20 | Brajesh Upadhyay | work has been done | 74.7596 | 20.448 | Inspected | RFI Approved | 340 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1642 | Checking Of Level & FDD Test For GSB Top | 132320 | 132900 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 16:15 | Rushikesh Gunjal | 2025-10-30 16:21 | Work was already done | 2025-10-31 07:45 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 580 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1627 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135210 | 135260 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:56 | Rushikesh Gunjal | 2025-10-27 15:59 | Work already done | 2025-10-28 08:17 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4426 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1655 | Checking Of Laying PQC Top | 130610 | 131260 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 17:10 | Rushikesh Gunjal | 2025-10-27 14:45 | Work already done | 2025-10-28 08:23 | Brajesh Upadhyay | work has been done | 74.7527 | 20.4082 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1628 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135020 | 135045 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:57 | Rushikesh Gunjal | 2025-10-27 16:00 | Work already done | 2025-10-28 08:24 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4426 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1646 | Checking Of Laying DLC Top | 135160 | 135690 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 16:40 | Rushikesh Gunjal | 2025-10-30 15:45 | Work was already done | 2025-10-31 07:44 | Brajesh Upadhyay | work has been done | 74.7596 | 20.4478 | Inspected | RFI Approved | 530 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1644 | Checking Of Laying DLC Top | 133840 | 134540 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 16:37 | Rushikesh Gunjal | 2025-10-30 16:03 | Work was already done | 2025-10-31 07:45 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4371 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1641 | Checking Of Level & FDD Test For GSB Top | 130210 | 130890 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 16:00 | Rushikesh Gunjal | 2025-10-30 11:41 | Work was already done | 2025-10-31 07:46 | Brajesh Upadhyay | work has been done | 74.7528 | 20.4086 | Inspected | RFI Approved | 680 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1640 | Checking Of Level & FDD Test For GSB Top | 131670 | 132320 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 16:33 | Rushikesh Gunjal | 2025-10-30 16:29 | Work was already done | 2025-10-31 07:46 | Brajesh Upadhyay | work has been done | 74.754 | 20.4116 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1639 | Checking Of Level & FDD Test For GSB Top | 132900 | 133200 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 16:32 | Rushikesh Gunjal | 2025-10-30 16:11 | Work was already done | 2025-10-31 07:46 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4251 | Inspected | RFI Approved | 300 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1629 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134600 | 134650 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:57 | Rushikesh Gunjal | 2025-10-27 16:01 | Work already done | 2025-10-28 08:16 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4426 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1619 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135140 | 135170 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:50 | Rushikesh Gunjal | 2025-10-27 15:51 | Work already done | 2025-10-28 08:18 | Brajesh Upadhyay | work has been done | 74.758 | 20.4426 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1633 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135030 | 135080 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 16:01 | Rushikesh Gunjal | 2025-10-27 16:05 | Work already done | 2025-10-28 08:23 | Brajesh Upadhyay | work has been done | 74.7579 | 20.4423 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1620 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134560 | 134600 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:50 | Rushikesh Gunjal | 2025-10-27 15:51 | Work already done | 2025-10-28 08:25 | Brajesh Upadhyay | work has been done | 74.758 | 20.4426 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1618 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134570 | 134600 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:45 | Rushikesh Gunjal | 2025-10-27 15:50 | Work already done | 2025-10-28 08:25 | Brajesh Upadhyay | work has been done | 74.758 | 20.4426 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1612 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 122640 | 122640 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:33 | Rushikesh Gunjal | 2025-10-28 12:27 | Work was already done | 2025-10-28 18:34 | Brajesh Upadhyay | work has been done | 74.7035 | 20.3547 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1608 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 135368 | 135368 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:29 | Rushikesh Gunjal | 2025-10-30 15:50 | Work was already done | 2025-10-31 07:48 | Brajesh Upadhyay | work has been done | 74.7593 | 20.4469 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1607 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 137018 | 137018 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:28 | Rushikesh Gunjal | 2025-10-30 15:37 | Work was already done | 2025-10-31 07:48 | Brajesh Upadhyay | work has been done | 74.7611 | 20.4519 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1616 | Checking Reinforcement, shuttering and pouring concrete for Final Lift Of Retaining Wall | 140643 | 140710 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:42 | Rushikesh Gunjal | 2025-10-27 15:12 | Work already done | 2025-10-28 08:25 | Brajesh Upadhyay | work has been done | 74.7812 | 20.489 | Inspected | RFI Approved | 67 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1615 | Checking Reinforcement, shuttering and pouring concrete for Final Lift Of Retaining Wall | 140710 | 140800 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:41 | Rushikesh Gunjal | 2025-10-27 15:10 | Work already done | 2025-10-28 08:26 | Brajesh Upadhyay | work has been done | 74.7812 | 20.489 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1614 | Checking Reinforcement, shuttering and pouring concrete for Final Lift Of Retaining Wall | 140595 | 140634 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:39 | Rushikesh Gunjal | 2025-10-27 15:09 | Work already done | 2025-10-28 08:26 | Brajesh Upadhyay | work has been done | 74.7812 | 20.4891 | Inspected | RFI Approved | 39 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1605 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 129250 | 129250 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:25 | Rushikesh Gunjal | 2025-10-30 16:46 | Work was already done | 2025-10-31 07:49 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1603 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 138983 | 138983 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:24 | Rushikesh Gunjal | 2025-10-30 16:43 | Work was already done | 2025-10-31 07:49 | Brajesh Upadhyay | work has been done | 74.7382 | 20.3912 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1599 | Checking Of Laying PQC Top | 123840 | 124470 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:10 | Rushikesh Gunjal | 2025-10-30 16:51 | Work was already done | 2025-10-31 07:50 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1597 | Checking Of Laying DLC Top | 130680 | 131660 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:58 | Rushikesh Gunjal | 2025-10-30 11:42 | Work was already done | 2025-10-31 07:50 | Brajesh Upadhyay | work has been done | 74.7528 | 20.4086 | Inspected | RFI Approved | 980 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1588 | Checking Of Laying DLC Top | 132420 | 132900 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:42 | Rushikesh Gunjal | 2025-10-30 16:28 | Work was already done | 2025-10-31 07:51 | Brajesh Upadhyay | work has been done | 74.7541 | 20.4116 | Inspected | RFI Approved | 480 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1587 | Checking Of Laying DLC Top | 132080 | 132420 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:41 | Rushikesh Gunjal | 2025-10-30 16:27 | Work was already done | 2025-10-31 07:51 | Brajesh Upadhyay | work has been done | 74.754 | 20.4116 | Inspected | RFI Approved | 340 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1598 | Checking Of Laying PQC Top | 127950 | 128500 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:00 | Rushikesh Gunjal | 2025-10-27 14:34 | Work already done | 2025-10-28 08:26 | Brajesh Upadhyay | work has been done | 74.7353 | 20.3892 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1591 | Checking Of Laying DLC Top | 122280 | 123140 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:48 | Rushikesh Gunjal | 2025-10-28 12:18 | Work was already done | 2025-10-28 18:36 | Brajesh Upadhyay | work has been done | 74.7026 | 20.3532 | Inspected | RFI Approved | 860 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1606 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 125737 | 125737 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:27 | Rushikesh Gunjal | 2025-10-30 16:47 | Work was already done | 2025-10-31 07:49 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1604 | Checking Shuttering & Pouring Concrete For Head Wall Final Lift Of HPC | 135821 | 135821 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:25 | Rushikesh Gunjal | 2025-10-30 15:49 | Work already done | 2025-10-31 07:49 | Brajesh Upadhyay | work has been done | 74.7593 | 20.4469 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1595 | Checking Of Laying DLC Top | 128720 | 129360 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:56 | Rushikesh Gunjal | 2025-10-28 15:45 | Work already done | 2025-10-28 18:34 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 640 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1594 | Checking Of Laying DLC Top | 127870 | 128720 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:55 | Rushikesh Gunjal | 2025-10-28 15:29 | Work was already done | 2025-10-28 18:34 | Brajesh Upadhyay | work has been done | 74.7327 | 20.3872 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1593 | Checking Of Laying DLC Top | 127170 | 127870 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:53 | Rushikesh Gunjal | 2025-10-28 15:28 | Work was already done | 2025-10-28 18:36 | Brajesh Upadhyay | work has been done | 74.7327 | 20.3872 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1596 | Checking Of Laying DLC Top | 129780 | 130680 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:57 | Rushikesh Gunjal | 2025-10-30 11:15 | Work was already done | 2025-10-30 11:30 | Brajesh Upadhyay | work has been done | 74.7509 | 20.4036 | Inspected | RFI Approved | 900 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1592 | Checking Of Laying DLC Top | 123140 | 123710 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:49 | Rushikesh Gunjal | 2025-10-30 16:52 | Work was already done | 2025-10-31 07:50 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 570 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1579 | Checking Of Level & FDD Test For GSB Top | 123140 | 123720 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:25 | Rushikesh Gunjal | 2025-10-30 16:58 | Work was already done | 2025-10-31 07:52 | Brajesh Upadhyay | work has been done | 74.7382 | 20.3911 | Inspected | RFI Approved | 580 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1575 | Checking Of Level & FDD Test For GSB Top | 129810 | 130800 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 12:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 12:48 | Rushikesh Gunjal | 2025-10-30 11:15 | Work was already done | 2025-10-30 11:30 | Brajesh Upadhyay | work has been done | 74.7508 | 20.4035 | Inspected | RFI Approved | 990 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1583 | Checking Of Level & FDD Test For GSB Top | 128720 | 129580 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:29 | Rushikesh Gunjal | 2025-10-28 15:45 | Work already done | 2025-10-28 18:37 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 860 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1586 | Checking Of Laying DLC Top | 131730 | 132080 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:40 | Rushikesh Gunjal | 2025-10-30 16:27 | Work was already done | 2025-10-31 07:51 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 350 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1582 | Checking Of Level & FDD Test For GSB Top | 125100 | 125890 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:28 | Rushikesh Gunjal | 2025-10-30 16:53 | Work was already done | 2025-10-31 07:52 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 790 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1581 | Checking Of Level & FDD Test For GSB Top | 124340 | 125100 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:27 | Rushikesh Gunjal | 2025-10-30 16:57 | Work was already done | 2025-10-31 07:52 | Brajesh Upadhyay | work has been done | 74.7382 | 20.3911 | Inspected | RFI Approved | 760 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1580 | Checking Of Level & FDD Test For GSB Top | 123820 | 124340 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 14:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 14:26 | Rushikesh Gunjal | 2025-10-30 16:58 | Work was already done | 2025-10-31 07:52 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 520 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1667 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 123791 | 123850 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 12:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 12:39 | Rushikesh Gunjal | 2025-10-30 16:50 | Work was already done | 2025-10-31 07:42 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 59 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1666 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 123750 | 123781 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 12:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 12:37 | Rushikesh Gunjal | 2025-10-30 16:51 | Work was already done | 2025-10-31 07:42 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 31 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1689 | Checking OF Reinforcement , Shuttering & Pouring Concrete For Retaining Wall Final lift | 132970 | 132981 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 17:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 17:07 | Rushikesh Gunjal | 2025-10-30 15:05 | Work already done | 2025-10-31 07:39 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4265 | Inspected | RFI Approved | 11 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1701 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120080 | 120100 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-02 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-03 09:30 | Rushikesh Gunjal | 2025-11-04 14:13 | Work already done | 2025-11-05 15:37 | Brajesh Upadhyay | work has been done | 74.6922 | 20.3346 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1700 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120020 | 120030 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-02 18:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-03 10:00 | Rushikesh Gunjal | 2025-11-04 14:14 | Work already done | 2025-11-05 15:38 | Brajesh Upadhyay | work has been done | 74.6922 | 20.3345 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1698 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120140 | 120190 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-02 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-03 15:00 | Rushikesh Gunjal | 2025-11-05 10:59 | Work was already done | 2025-11-05 15:38 | Brajesh Upadhyay | work has been done | 74.6927 | 20.335 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1696 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 120230 | 120300 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-02 18:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-03 18:12 | Rushikesh Gunjal | 2025-11-05 10:58 | Work was already done | 2025-11-05 15:38 | Brajesh Upadhyay | work has been done | 74.6926 | 20.3351 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1688 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 120229 | 120229 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 17:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 17:03 | Rushikesh Gunjal | 2025-10-30 16:40 | Work already done | 2025-10-31 07:40 | Brajesh Upadhyay | work has been done | 74.7381 | 20.3911 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1687 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 127176 | 127176 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 17:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:56 | Rushikesh Gunjal | 2025-10-27 14:36 | Work already done | 2025-10-28 08:21 | Brajesh Upadhyay | work has been done | 74.7352 | 20.3891 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1685 | Checking Of Laying DLC Top | 129800 | 129820 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 16:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:54 | Rushikesh Gunjal | 2025-10-30 11:23 | Work was already done | 2025-10-30 11:29 | Brajesh Upadhyay | work has been done | 74.7508 | 20.4036 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1686 | Checking Of Laying DLC Top | 137280 | 138150 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 16:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:55 | Rushikesh Gunjal | 2025-10-30 15:42 | Work was already done | 2025-10-31 07:40 | Brajesh Upadhyay | work has been done | 74.7612 | 20.4519 | Inspected | RFI Approved | 870 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1671 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 123791 | 123850 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 12:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 12:45 | Rushikesh Gunjal | 2025-10-30 16:49 | Work was already done | 2025-10-31 07:41 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 59 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1670 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 123750 | 123781 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 12:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 12:44 | Rushikesh Gunjal | 2025-10-30 16:49 | Work was already done | 2025-10-31 07:41 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 31 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1668 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 129400 | 129693 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 12:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 12:40 | Rushikesh Gunjal | 2025-10-30 16:48 | Work was already done | 2025-10-31 07:41 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 293 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1673 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 129703 | 129800 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 12:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 12:47 | Rushikesh Gunjal | 2025-10-28 15:48 | Work already done | 2025-10-28 18:33 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 97 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1707 | Checking Of Pipe Laying & shuttering & Pouring Concrete For Head Wall Second Lift Of HPC | 120400 | 120400 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-05 17:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-06 09:00 | Kishori Lal | 2025-11-13 15:43 | Work done. | 2025-11-13 20:07 | Brajesh Upadhyay | work has been done | 74.6942 | 20.3366 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1706 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120170 | 120190 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-05 17:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-06 09:30 | Kishori Lal | 2025-11-13 16:19 | Work already done. | 2025-11-13 20:07 | Brajesh Upadhyay | work has been done | 74.6922 | 20.3346 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1711 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120280 | 120340 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-05 17:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-06 11:00 | Kishori Lal | 2025-11-13 16:09 | Work already done. | 2025-11-13 20:06 | Brajesh Upadhyay | work has been done | 74.6936 | 20.336 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1713 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120340 | 120350 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-05 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-06 11:45 | Kishori Lal | 2025-11-13 16:02 | Work already done. | 2025-11-13 20:06 | Brajesh Upadhyay | work has been done | 74.6937 | 20.3364 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1714 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120140 | 120190 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-05 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-06 13:00 | Kishori Lal | 2025-11-13 16:17 | Work done. | 2025-11-13 20:06 | Brajesh Upadhyay | work has been done | 74.6932 | 20.3353 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1835 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 129535 | 129590 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 16:00 | Rushikesh Gunjal | 2025-12-03 16:51 | Work done | 2025-12-04 10:29 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7475 | 20.3982 | Inspected | RFI Approved | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1690 | Checking Of Reinforcement , Shuttering & Pouring Concrete For A1,A2 Wall First Lift Of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-24 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-25 18:01 | Rushikesh Gunjal | 2025-10-27 15:32 | Work already done | 2025-10-28 08:21 | Brajesh Upadhyay | work has been done | 74.7827 | 20.4996 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1837 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 129500 | 129540 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 18:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 14:00 | Rushikesh Gunjal | 2025-12-03 16:48 | Work done | 2025-12-04 10:29 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7478 | 20.3985 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1708 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120280 | 120320 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-05 17:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-06 10:00 | Kishori Lal | 2025-11-13 16:06 | Work already done. | 2025-11-13 20:07 | Brajesh Upadhyay | work has been done | 74.6936 | 20.336 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/01838 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 133220 | 133270 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 18:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 16:00 | Rushikesh Gunjal | 2025-12-03 14:54 | Check FDD and found satisfactory result | 2025-12-04 10:29 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7586 | 20.4311 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1637 | Checking Of Laying PQC Top | 132500 | 132850 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 16:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 16:06 | Rushikesh Gunjal | 2025-10-27 14:56 | Work already done | 2025-10-28 08:13 | Brajesh Upadhyay | work has been done | 74.7596 | 20.448 | Inspected | RFI Approved | 350 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1653 | Checking Of Laying PQC Top | 129160 | 129610 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 17:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-20 17:03 | Rushikesh Gunjal | 2025-10-27 14:40 | Work already done | 2025-10-28 08:20 | Brajesh Upadhyay | work has been done | 74.7448 | 20.3962 | Inspected | RFI Approved | 450 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1600 | Checking Of Laying PQC Top | 128460 | 129160 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-19 15:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-19 15:11 | Rushikesh Gunjal | 2025-10-27 14:39 | Work already done | 2025-10-28 08:26 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3932 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1723 | Checking Of Reinforcement, Shuttering & pouring Concrete For Retaining Wall A1,A2 Final Lift Of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-07 17:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-08 16:00 | Kishori Lal | 2025-11-13 13:45 | Work done. | 2025-11-13 20:04 | Brajesh Upadhyay | work has been done | 74.7827 | 20.4995 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1724 | Checking Of Layout Marking ,Excavation & Laying PCC For Box culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-07 17:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-08 15:00 | Kishori Lal | 2025-11-13 14:02 | Work already done. | 2025-11-13 20:04 | Brajesh Upadhyay | work has been done | 74.782 | 20.4922 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1831 | Checking Of Below Pipe PCC & Shuttering & Pouring Concrete Head Wall First Lift | 122070 | 122070 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 15:00 | Rushikesh Gunjal | 2025-12-03 11:40 | Work already done | 2025-12-04 10:28 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.6997 | 20.3485 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2080 | Checking Of Reinforcement, Shuttering & Pouring concrete For R. Wall A1,A2 Final Lift Of MNB | 123800 | 123800 | LHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-09 17:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-10 12:15 | Kishori Lal | 2026-02-14 13:18 | Work done. | 2026-02-16 09:20 | Brajesh Upadhyay | work has been done | 74.7074 | 20.3635 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2022 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Wall A1,A2 First Lift Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-06 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-07 10:00 | Rushikesh Gunjal | 2026-01-07 11:12 | Work done | 2026-01-08 15:55 | Brajesh Upadhyay | work has been done | 74.7075 | 20.3636 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2021 | Checking Of Reinforcement , shuttering & Pouring Concrete For Anchor Beam A1,A2 Of BC | 140928 | 140928 | LHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-05 18:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-06 14:00 | Rushikesh Gunjal | 2026-01-06 16:42 | Work done | 2026-01-07 08:36 | Brajesh Upadhyay | work has been done. | 74.7821 | 20.4923 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1729 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 141750 | 141800 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-11 18:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-12 16:00 | Rushikesh Gunjal | 2025-11-12 15:24 | Work done | 2025-11-12 18:31 | Brajesh Upadhyay | work has been done | 74.7826 | 20.4989 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1728 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 141750 | 141800 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-11 18:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-12 13:00 | Rushikesh Gunjal | 2025-11-12 15:25 | Work done | 2025-11-12 18:31 | Brajesh Upadhyay | work has been done | 74.7826 | 20.499 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1727 | Checking Of shuttering & Pouring concrete For Head Wall second Lift & Pipe Laying | 117008 | 117008 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-11 18:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-12 13:00 | Rushikesh Gunjal | 2025-11-13 12:54 | Work done | 2025-11-13 20:03 | Brajesh Upadhyay | work has been done | 74.6931 | 20.3355 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1726 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 120070 | 120080 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-11 17:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-12 11:00 | Rushikesh Gunjal | 2025-11-13 12:52 | Work done | 2025-11-13 20:03 | Brajesh Upadhyay | work has been done | 74.6921 | 20.3343 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1725 | Checking Of Reinforcement , Shuttering & pouring concreting For Raft Of Box Culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-08 17:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-09 15:00 | Rushikesh Gunjal | 2025-11-11 12:41 | Work done | 2025-11-12 09:37 | Brajesh Upadhyay | work has been done | 74.782 | 20.4922 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1733 | Checking Of Level & FDD Test For GSB Top | 141740 | 141800 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-13 08:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-13 17:00 | Rushikesh Gunjal | 2025-11-15 13:50 | Work done | 2025-11-15 14:09 | Brajesh Upadhyay | work has been done | 74.7829 | 20.4998 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1732 | Checking Of Level & FDD Test For GSB Top | 141740 | 141800 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-13 08:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-13 16:00 | Rushikesh Gunjal | 2025-11-15 13:49 | Work done | 2025-11-15 14:09 | Brajesh Upadhyay | work has been done | 74.7828 | 20.4999 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1735 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120070 | 120080 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-13 09:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-13 13:00 | Rushikesh Gunjal | 2025-11-15 13:13 | Work done | 2025-11-15 13:14 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3326 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1734 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 117008 | 117008 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-13 08:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-13 15:00 | Rushikesh Gunjal | 2025-11-15 13:17 | Work done | 2025-11-15 13:24 | Brajesh Upadhyay | work has been done | 74.6942 | 20.3369 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1712 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120360 | 120380 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-05 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-06 11:30 | Kishori Lal | 2025-11-13 15:55 | Work Already done. | 2025-11-13 20:06 | Brajesh Upadhyay | work has been done | 74.6941 | 20.3365 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1740 | Checking Of Level & FDD Test For Subgrade Top | 117000 | 117030 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-13 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 16:00 | Rushikesh Gunjal | 2025-11-15 12:07 | Work done | 2025-11-15 13:07 | Brajesh Upadhyay | work has been done | 74.6729 | 20.3179 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1737 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 117000 | 117030 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-13 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 11:00 | Rushikesh Gunjal | 2025-11-15 11:57 | Work done | 2025-11-15 13:08 | Brajesh Upadhyay | work has been done | 74.6728 | 20.3179 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1736 | Checking Of Reinforcement, Shuttering & Pouring concrete For Crash Barrier Of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-13 18:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 15:00 | Rushikesh Gunjal | 2025-11-15 13:56 | Work done | 2025-11-15 14:09 | Brajesh Upadhyay | work has been done | 74.7828 | 20.4995 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1738 | Checking Of Existing BT Dismantling , Excavation Up To Embankment Top, Level & FDD Test | 117000 | 117030 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-13 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 12:30 | Rushikesh Gunjal | 2025-11-15 11:59 | Work done | 2025-11-15 13:07 | Brajesh Upadhyay | work has been done | 74.6729 | 20.3179 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1722 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120340 | 120360 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-06 18:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-07 09:15 | Kishori Lal | 2025-11-13 16:04 | Work done. | 2025-11-13 20:04 | Brajesh Upadhyay | work has been done | 74.6939 | 20.3362 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1719 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119740 | 119745 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-06 18:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-07 11:00 | Kishori Lal | 2025-11-13 16:51 | Work already done. | 2025-11-13 20:04 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3319 | Inspected | RFI Approved | 5 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1718 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120230 | 120290 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-06 18:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-07 10:30 | Kishori Lal | 2025-11-13 16:12 | Work already done. | 2025-11-13 20:05 | Brajesh Upadhyay | work has been done | 74.6935 | 20.3357 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1710 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120080 | 120100 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-05 17:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-06 10:45 | Kishori Lal | 2025-11-13 16:21 | Work done. | 2025-11-13 20:07 | Brajesh Upadhyay | work has been done | 74.6922 | 20.3344 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1709 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119740 | 119745 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-05 17:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-06 10:30 | Kishori Lal | 2025-11-13 16:50 | Work already done. | 2025-11-13 20:07 | Brajesh Upadhyay | work has been done | 74.6908 | 20.332 | Inspected | RFI Approved | 5 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1745 | Checking Of Level & FDD test for GSB Top layer | 119120 | 119714 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 13:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 14:30 | Rushikesh Gunjal | 2025-11-15 13:06 | Work done | 2025-11-15 13:06 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3328 | Inspected | RFI Approved | 594 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1742 | Checking Of Level & FDD test for GSB Top Layer | 119750 | 120420 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 13:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 14:00 | Rushikesh Gunjal | 2025-11-15 13:03 | Work done | 2025-11-15 13:07 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3328 | Inspected | RFI Approved | 670 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1743 | Checking of Layout Marking & Excavation & Laying PCC For Toe Wall | 118400 | 118460 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 13:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 13:30 | Rushikesh Gunjal | 2025-11-15 12:35 | Work done | 2025-11-15 13:06 | Brajesh Upadhyay | work has been done | 74.688 | 20.3246 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1744 | Checking Of Laying DLC Top Layer | 141730 | 141800 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 13:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 13:28 | Rushikesh Gunjal | 2025-11-15 13:53 | Work done | 2025-11-15 14:08 | Brajesh Upadhyay | work has been done | 74.7829 | 20.4998 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1751 | Checking Of Laying DLC Top Layer | 117020 | 117050 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 13:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 15:50 | Rushikesh Gunjal | 2025-11-15 12:12 | Work done | 2025-11-15 13:06 | Brajesh Upadhyay | work has been done | 74.6728 | 20.3179 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1757 | Checking of Laying of PQC Top | 120410 | 121040 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 16:30 | Rushikesh Gunjal | 2025-11-15 13:11 | Work done | 2025-11-15 13:13 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3326 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1765 | Checking Of Laying DLC Top Layer | 117030 | 117580 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 17:00 | Rushikesh Gunjal | 2025-11-15 12:18 | Work done | 2025-11-15 13:03 | Brajesh Upadhyay | work has been done | 74.6727 | 20.3179 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1768 | Checking Of Level & FDD Test For Earthen Shoulder | 128100 | 129350 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 17:10 | Rushikesh Gunjal | 2025-11-14 18:05 | Work done | 2025-11-15 08:41 | Brajesh Upadhyay | work has been done | 74.2259 | 19.564 | Inspected | RFI Approved | 1250 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1770 | Checking of Level & FDD Test & Filling of Earthen Shoulder | 131200 | 133210 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 17:20 | Rushikesh Gunjal | 2025-11-14 18:02 | Work done | 2025-11-15 08:41 | Brajesh Upadhyay | work has been done | 74.2259 | 19.564 | Inspected | RFI Approved | 2010 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1767 | Checking Of Shuttering & laying PCC For Drain | 120050 | 120140 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-15 14:00 | Rushikesh Gunjal | 2025-11-15 12:45 | Work done | 2025-11-15 13:02 | Brajesh Upadhyay | work has been done | 74.6921 | 20.3346 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1752 | Checking Of Laying PQC Top Layer | 141720 | 141800 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 13:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 15:55 | Rushikesh Gunjal | 2025-11-15 14:02 | Work done | 2025-11-15 14:07 | Brajesh Upadhyay | work has been done | 74.7826 | 20.4987 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1760 | Checking Of Laying DLC Top Layer | 118630 | 119000 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 16:35 | Rushikesh Gunjal | 2025-11-15 12:33 | Work done | 2025-11-15 13:05 | Brajesh Upadhyay | work has been done | 74.6883 | 20.3248 | Inspected | RFI Approved | 370 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1753 | Checking Of Level & FDD test for GSB Top Layer | 117870 | 118530 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 16:00 | Rushikesh Gunjal | 2025-11-15 12:10 | Work done | 2025-11-15 13:05 | Brajesh Upadhyay | work has been done | 74.6728 | 20.3179 | Inspected | RFI Approved | 660 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1755 | Checking Of Laying DLC Top Layer | 119750 | 120430 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 16:15 | Rushikesh Gunjal | 2025-11-15 13:10 | Work done | 2025-11-15 13:14 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3326 | Inspected | RFI Approved | 680 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1754 | Checking Of Laying DLC Top Layer | 120430 | 121020 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 16:10 | Rushikesh Gunjal | 2025-11-15 13:14 | Work done | 2025-11-15 13:14 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3328 | Inspected | RFI Approved | 590 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1756 | Checking Of Level & FDD test for GSB Top Layer | 117230 | 117870 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 16:25 | Rushikesh Gunjal | 2025-11-15 12:14 | Work done | 2025-11-15 13:05 | Brajesh Upadhyay | work has been done | 74.6728 | 20.318 | Inspected | RFI Approved | 640 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1758 | Checking Of Laying DLC Top Layer | 119000 | 119714 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 16:35 | Rushikesh Gunjal | 2025-11-15 13:09 | Work done | 2025-11-15 13:13 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3328 | Inspected | RFI Approved | 714 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1759 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Final lift OF Toe Wall | 118400 | 118460 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 16:35 | Rushikesh Gunjal | 2025-11-15 12:36 | Work done | 2025-11-15 13:05 | Brajesh Upadhyay | work has been done | 74.688 | 20.3246 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1750 | Checking Of Level & FDD test for GSB Top Layer | 118530 | 119120 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 13:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 15:45 | Rushikesh Gunjal | 2025-11-15 12:30 | Work done | 2025-11-15 13:06 | Brajesh Upadhyay | work has been done | 74.6882 | 20.3248 | Inspected | RFI Approved | 590 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1747 | Checking Of Level & FDD test for GSB Top Layer | 117000 | 117040 | RHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 13:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 15:00 | Rushikesh Gunjal | 2025-11-15 12:08 | Work done | 2025-11-15 13:06 | Brajesh Upadhyay | work has been done | 74.6727 | 20.3178 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1746 | Checking Of Laying DLC Top Layer | 141730 | 141800 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 13:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 14:55 | Rushikesh Gunjal | 2025-11-15 13:54 | Work done | 2025-11-15 14:08 | Brajesh Upadhyay | work has been done | 74.7829 | 20.4998 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1748 | Checking Of Laying PQC Top Layer | 141720 | 141800 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 13:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 15:30 | Rushikesh Gunjal | 2025-11-15 14:03 | Work done | 2025-11-15 14:08 | Brajesh Upadhyay | work has been done | 74.7827 | 20.4987 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1766 | Checking Of Level & FDD Test For Earthen Shoulder | 126500 | 128100 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 17:05 | Rushikesh Gunjal | 2025-11-14 18:07 | Work done | 2025-11-15 08:41 | Brajesh Upadhyay | work has been done | 74.2259 | 19.564 | Inspected | RFI Approved | 1600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1771 | Checking of Level & FDD Test & Filling of Earthen Shoulder | 136000 | 137200 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 15:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 17:30 | Rushikesh Gunjal | 2025-11-14 17:57 | Work done | 2025-11-15 08:40 | Brajesh Upadhyay | work has been done | 74.2258 | 19.564 | Inspected | RFI Approved | 1200 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1769 | Checking of Level & FDD Test & Filling of Earthen Shoulder | 129800 | 131200 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 17:15 | Rushikesh Gunjal | 2025-11-14 18:04 | Work done | 2025-11-15 08:41 | Brajesh Upadhyay | work has been done | 74.2259 | 19.564 | Inspected | RFI Approved | 1400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1761 | Checking Of Level & FDD test for GSB Top Layer | 117020 | 117230 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 16:40 | Rushikesh Gunjal | 2025-11-15 12:17 | Work done | 2025-11-15 13:05 | Brajesh Upadhyay | work has been done | 74.6725 | 20.3177 | Inspected | RFI Approved | 210 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1764 | Checking Of Laying DLC Top Layer | 117580 | 118000 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 16:55 | Rushikesh Gunjal | 2025-11-15 12:19 | Work done | 2025-11-15 13:04 | Brajesh Upadhyay | work has been done | 74.6728 | 20.3179 | Inspected | RFI Approved | 420 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1763 | Checking Of Laying PQC Top Layer | 119750 | 120410 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 16:50 | Rushikesh Gunjal | 2025-11-15 13:01 | Work done | 2025-11-15 13:04 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3328 | Inspected | RFI Approved | 660 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1762 | Checking Of Laying DLC Top Layer | 118000 | 118630 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 14:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 16:50 | Rushikesh Gunjal | 2025-11-15 12:32 | Work done | 2025-11-15 13:04 | Brajesh Upadhyay | work has been done | 74.6883 | 20.3248 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1749 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Toe Wall First Lift | 118400 | 118460 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 13:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 14:30 | Rushikesh Gunjal | 2025-11-15 12:37 | Work done | 2025-11-15 13:06 | Brajesh Upadhyay | work has been done | 74.6881 | 20.3246 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1741 | Checking Of Level & FDD test for GSB Top Layer | 120420 | 121030 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-14 13:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 13:10 | Rushikesh Gunjal | 2025-11-15 13:05 | Work done | 2025-11-15 13:07 | Brajesh Upadhyay | work has been done | 74.6909 | 20.3326 | Inspected | RFI Approved | 610 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1927 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 129650 | 129690 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 17:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 12:00 | Kishori Lal | 2025-12-10 14:03 | Work not done. |  |  |  | 74.7481 | 20.3989 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1794 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Raft | 134520 | 134600 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 15:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 17:00 | Rushikesh Gunjal | 2025-12-03 15:02 | Work already done | 2025-12-04 10:26 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7579 | 20.4422 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1773 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 120070 | 120080 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-26 12:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-26 13:00 | Rushikesh Gunjal | 2025-11-28 18:07 | Work done | 2025-11-29 20:12 | Brajesh Upadhyay | work has been done | 74.692 | 20.3344 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1829 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 139810 | 140925 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-02 17:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-03 14:00 | Rushikesh Gunjal | 2025-12-03 15:22 | Work done | 2025-12-04 10:28 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7755 | 20.4844 | Inspected | RFI Approved | 1115 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1845 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 139810 | 140925 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-03 17:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-04 16:00 | Rushikesh Gunjal | 2025-12-04 11:34 | Work done | 2025-12-05 08:15 | Brajesh Upadhyay | work has been done | 74.7746 | 20.4796 | Inspected | RFI Approved | 1115 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1841 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 133220 | 133270 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-03 17:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-04 11:00 | Rushikesh Gunjal | 2025-12-04 11:36 | Work done | 2025-12-05 08:15 | Brajesh Upadhyay | work has been done | 74.7746 | 20.4796 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1843 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Retaining Wall A1,A2 2nd Lift Of Box Culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-03 17:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-04 13:00 | Rushikesh Gunjal | 2025-12-04 11:51 | Work done | 2025-12-05 08:15 | Brajesh Upadhyay | work has been done | 74.7821 | 20.4924 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1775 | Checking Of reinforcement , Shuttering & Pouring Concrete For Drain Raft | 120050 | 120140 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-26 17:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-27 11:30 | Rushikesh Gunjal | 2025-11-28 17:58 | Work already done | 2025-11-28 18:01 | Brajesh Upadhyay | work has been done | 74.6921 | 20.3344 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1776 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119740 | 119770 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-26 17:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-27 13:00 | Rushikesh Gunjal | 2025-11-28 18:03 | Work done | 2025-11-29 20:12 | Brajesh Upadhyay | work has been done | 74.6907 | 20.332 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1777 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120140 | 120320 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-26 17:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-27 14:00 | Rushikesh Gunjal | 2025-11-28 17:56 | Wrong Chainage In mention Chainage HP culvert exists |  |  |  | 74.6932 | 20.3356 | Inspected | Inspected - Rejected - Work Not Done | 180 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1842 | Checking Of Pipe Laying , Shuttering & Pouring Concrete For Head Wall Second Lift Of HPC | 124418 | 124418 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-03 17:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-04 12:00 | Rushikesh Gunjal | 2025-12-04 15:18 | Work already done | 2025-12-05 08:15 | Brajesh Upadhyay | work has been done | 74.7109 | 20.3682 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1846 | Checking Of Below Pipe PCC, Shuttering & Pouring Concrete For Head Wall First Lift Of HPC | 121908 | 121908 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-03 18:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-04 17:00 | Rushikesh Gunjal | 2025-12-04 15:25 | Work already done | 2025-12-05 08:14 | Brajesh Upadhyay | work has been done | 74.6998 | 20.3485 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1844 | Checking Of Pipe Laying ,Shuttering & Pouring Concrete Head Wall Second Lift Of HPC | 122070 | 122070 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-03 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-04 14:00 | Rushikesh Gunjal | 2025-12-04 15:26 | Work already done | 2025-12-05 08:15 | Brajesh Upadhyay | work has been done | 74.6997 | 20.3485 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1839 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 129500 | 129540 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-03 17:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-04 09:00 | Rushikesh Gunjal | 2025-12-04 15:32 | Work done | 2025-12-05 08:15 | Brajesh Upadhyay | work has been done | 74.6934 | 20.3357 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1772 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Bottom Haunch Of Box Culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-26 12:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-26 16:00 | Rushikesh Gunjal | 2025-11-28 15:36 | Work already done | 2025-11-28 18:01 | Brajesh Upadhyay | work has been done | 74.7821 | 20.4922 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1840 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 129590 | 129650 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-03 17:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-04 10:00 | Rushikesh Gunjal | 2025-12-04 15:33 | Work done | 2025-12-05 08:15 | Brajesh Upadhyay | work has been done | 74.6932 | 20.3357 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1782 | Checking Of layout Marking , Excavation & Laying PCC For Retaining Wall A1,A2 Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-28 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-29 16:00 | Rushikesh Gunjal | 2025-11-29 13:18 | Work done | 2025-11-29 20:00 | Brajesh Upadhyay | work has been done | 74.7484 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1882 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 129650 | 129700 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 17:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 09:00 | Kishori Lal | 2025-12-07 14:13 | Work not done. |  |  |  | 74.7476 | 20.398 | Inspected | Inspected - Rejected - Work Not Done | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1847 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 129500 | 129540 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 17:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 09:00 | Rushikesh Gunjal | 2025-12-05 17:00 | Work done | 2025-12-06 09:55 | Brajesh Upadhyay | work has been done | 74.7478 | 20.3985 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1852 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 129650 | 129700 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 17:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 12:00 | Rushikesh Gunjal | 2025-12-05 17:00 | Work done | 2025-12-06 09:54 | Brajesh Upadhyay | work has been done | 74.7478 | 20.3985 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1853 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134780 | 134820 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 17:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 13:00 | Rushikesh Gunjal | 2025-12-05 17:03 | Work already done | 2025-12-06 09:54 | Brajesh Upadhyay | work has been done | 74.7478 | 20.3984 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1856 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 138820 | 139810 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 18:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 11:00 | Rushikesh Gunjal | 2025-12-05 16:50 | Check fdd test and found satisfactory result | 2025-12-06 09:54 | Brajesh Upadhyay | work has been done | 74.7586 | 20.432 | Inspected | RFI Approved | 990 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1858 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 135210 | 135220 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 13:00 | Rushikesh Gunjal | 2025-12-05 16:42 | Work already done | 2025-12-06 09:53 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4452 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1893 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 134825 | 134980 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 18:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 09:00 | Rushikesh Gunjal | 2025-12-08 16:54 | Work done | 2025-12-09 09:19 | Brajesh Upadhyay | work has been done | 74.758 | 20.4436 | Inspected | RFI Approved | 155 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1860 | Checking Of Layout Marking ,Excavation & Laying PCC For HPC | 125275 | 125275 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 18:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 11:00 | Rushikesh Gunjal | 2025-12-05 13:39 | Work already done | 2025-12-06 09:53 | Brajesh Upadhyay | work has been done | 74.7169 | 20.3734 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1886 | Checking Of Below pipe PCC & Shuttering & Pouring Concrete For Head Wall First Lift Of HPC | 120229 | 120229 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 17:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 13:00 | Kishori Lal | 2025-12-07 16:40 | Work not as per design. |  |  |  | 74.6942 | 20.3354 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1874 | Checking Of Below pipe PCC & Shuttering & Pouring Concrete For Head Wall First Lift Of HPC | 125275 | 125275 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 18:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 17:00 | Rushikesh Gunjal | 2025-12-06 15:09 | Work already done | 2025-12-06 21:27 | Brajesh Upadhyay | work has been done | 74.6931 | 20.3357 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1870 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134980 | 135040 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 18:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 14:00 | Rushikesh Gunjal | 2025-12-06 13:18 | Work already done | 2025-12-06 21:28 | Brajesh Upadhyay | work has been done | 74.7596 | 20.4478 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1864 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134700 | 134740 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 17:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 11:00 | Rushikesh Gunjal | 2025-12-06 13:21 | Work already done | 2025-12-06 21:29 | Brajesh Upadhyay | work has been done | 74.7595 | 20.4478 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1868 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 135340 | 135400 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 17:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 14:00 | Rushikesh Gunjal | 2025-12-06 13:19 | Work done | 2025-12-06 21:28 | Brajesh Upadhyay | work has been done | 74.7596 | 20.4478 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1863 | Checking Of Layout Marking, Excavation & Laying PCC For Drain | 129600 | 129650 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 17:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 10:00 | Rushikesh Gunjal | 2025-12-06 13:30 | Work already done | 2025-12-06 21:29 | Brajesh Upadhyay | work has been done | 74.7479 | 20.3984 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1779 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 129500 | 129560 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-27 18:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-28 14:00 | Rushikesh Gunjal | 2025-11-28 16:13 | Work not done |  |  |  | 74.747 | 20.3977 | Inspected | Inspected - Rejected - Work Not Done | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1778 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Wall A1,A2 First lift Of Box Culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-27 17:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-28 10:30 | Rushikesh Gunjal | 2025-11-28 15:38 | Work already done | 2025-11-28 18:01 | Brajesh Upadhyay | work has been done | 74.782 | 20.4922 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1850 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134700 | 134740 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 17:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 11:00 | Rushikesh Gunjal | 2025-12-05 17:02 | Work already done | 2025-12-06 09:55 | Brajesh Upadhyay | work has been done | 74.7478 | 20.3984 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1848 | Checking Of Pipe Laying , Shuttering & pouring Concrete For Head Wall Second Lift | 121840 | 121840 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 17:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 09:00 | Rushikesh Gunjal | 2025-12-05 13:26 | Work already done | 2025-12-06 09:55 | Brajesh Upadhyay | work has been done | 74.6996 | 20.3479 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1854 | Checking Of Pipe Laying , Shuttering & pouring Concrete For Head Wall Second Lift Of HPC | 121908 | 121908 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 18:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 13:00 | Rushikesh Gunjal | 2025-12-05 13:27 | Work already done | 2025-12-06 09:54 | Brajesh Upadhyay | work has been done | 74.6996 | 20.3479 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1851 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 129540 | 129600 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 17:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 11:00 | Rushikesh Gunjal | 2025-12-05 17:01 | Work done | 2025-12-06 09:54 | Brajesh Upadhyay | work has been done | 74.7478 | 20.3985 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1855 | Checking Of Below Pipe PCC & Shuttering & Pouring Concrete Head Wall First Lift Of HPC | 120895 | 120895 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 18:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 14:00 | Rushikesh Gunjal | 2025-12-06 11:27 | Work already done | 2025-12-06 21:29 | Brajesh Upadhyay | work has been done | 74.6997 | 20.3486 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1880 | Checking Of Reinforcement, Shuttering & Pouring Concrete For First lift Of Toe Wall | 119060 | 119120 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 15:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 14:00 | Kishori Lal | 2025-12-07 16:20 | Work done. | 2025-12-08 08:39 | Brajesh Upadhyay | work has been done | 74.6895 | 20.3252 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1781 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Wall A1,A2 Second lift Of Box Culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-28 16:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-29 14:00 | Rushikesh Gunjal | 2025-11-29 12:43 | Work done | 2025-11-29 20:11 | Brajesh Upadhyay | work has been done | 74.782 | 20.4923 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1885 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 124418 | 124418 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 17:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 12:00 | Kishori Lal | 2025-12-07 16:58 | Work already done. | 2025-12-08 08:38 | Brajesh Upadhyay | work has been done | 74.7127 | 20.3678 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1872 | Checking Of Layout Marking , Excavation & Laying PCC For HPC | 120229 | 120229 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 18:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 16:00 | Rushikesh Gunjal | 2025-12-06 11:20 | Work already done | 2025-12-06 21:28 | Brajesh Upadhyay | work has been done | 74.6932 | 20.3356 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1774 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119740 | 119770 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-26 12:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-26 14:00 | Rushikesh Gunjal | 2025-11-28 18:02 | Work done | 2025-11-29 20:12 | Brajesh Upadhyay | work has been done | 74.6906 | 20.332 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1780 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 120230 | 120290 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-28 11:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-28 17:30 | Rushikesh Gunjal | 2025-11-28 18:08 | Work done | 2025-11-29 20:12 | Brajesh Upadhyay | work has been done | 74.6934 | 20.3357 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1783 | Checking Of Reinforcement , shuttering & Pouring Concrete For Wall Final lift , Top Haunch & Slab Of Box Culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-29 14:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-30 13:00 | Rushikesh Gunjal | 2025-12-01 16:56 | Work already done | 2025-12-02 09:10 | Brajesh Upadhyay | work has been done | 74.782 | 20.4922 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1785 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 129650 | 129700 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-29 14:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-30 14:00 | Rushikesh Gunjal | 2025-12-01 16:11 | Work done | 2025-12-02 09:10 | Brajesh Upadhyay | work has been done | 74.7479 | 20.3984 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1786 | Checking Reinforcement, shuttering and pouring concrete for Drain wall | 120050 | 120140 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-29 14:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-30 16:00 | Rushikesh Gunjal | 2025-12-02 10:14 | Work already done | 2025-12-02 16:51 | Brajesh Upadhyay | work has been done | 74.6923 | 20.3345 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1787 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 120400 | 121020 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-29 15:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-30 11:00 | Rushikesh Gunjal | 2025-12-01 15:29 | Work not done |  |  |  | 74.6956 | 20.338 | Inspected | Inspected - Rejected - Work Not Done | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1919 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 123791 | 123880 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 16:00 | Rushikesh Gunjal | 2025-12-08 16:02 | Work not done |  |  |  | 74.7074 | 20.3639 | Inspected | Inspected - Rejected - Work Not Done | 89 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1916 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 125900 | 126500 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 13:00 | Rushikesh Gunjal | 2025-12-08 16:12 | Check fdd and found satisfactory result | 2025-12-09 09:16 | Brajesh Upadhyay | work has been done | 74.7241 | 20.3814 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1918 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 134520 | 134600 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 15:00 | Rushikesh Gunjal | 2025-12-08 16:59 | Work already done | 2025-12-09 09:12 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4435 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1789 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall A1,A2 Raft Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-29 18:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-30 15:00 | Rushikesh Gunjal | 2025-12-01 16:17 | Work done | 2025-12-02 09:10 | Brajesh Upadhyay | work has been done | 74.7484 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1917 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 129350 | 129500 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 14:00 | Rushikesh Gunjal | 2025-12-08 17:23 | Work done | 2025-12-09 09:11 | Brajesh Upadhyay | work has been done | 74.7738 | 20.4778 | Inspected | RFI Approved | 150 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1862 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 129650 | 129700 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 17:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 09:00 | Rushikesh Gunjal | 2025-12-06 13:31 | Work done | 2025-12-06 21:29 | Brajesh Upadhyay | work has been done | 74.7479 | 20.3985 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1907 | Checking Of Shuttering & Laying PCC For HPC | 133023 | 133023 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 14:00 | Rushikesh Gunjal | 2025-12-08 17:04 | Work already done | 2025-12-09 09:13 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4449 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1867 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 138820 | 139810 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 17:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 12:00 | Rushikesh Gunjal | 2025-12-06 13:09 | Work done | 2025-12-06 21:29 | Brajesh Upadhyay | work has been done | 74.7714 | 20.4742 | Inspected | RFI Approved | 990 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1900 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Toe Wall First lift | 118770 | 118870 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 17:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 08:00 | Rushikesh Gunjal | 2025-12-08 15:12 | Work already done | 2025-12-09 09:16 | Brajesh Upadhyay | work has been done | 74.688 | 20.3245 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1869 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 129540 | 129600 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 18:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 13:00 | Rushikesh Gunjal | 2025-12-06 13:30 | Work done | 2025-12-06 21:28 | Brajesh Upadhyay | work has been done | 74.7479 | 20.3984 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1871 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 121840 | 121840 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 15:00 | Rushikesh Gunjal | 2025-12-06 11:28 | Work already done | 2025-12-06 21:28 | Brajesh Upadhyay | work has been done | 74.6997 | 20.3486 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1875 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 138040 | 138820 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 18:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 15:00 | Rushikesh Gunjal | 2025-12-06 13:10 | Work done | 2025-12-06 21:27 | Brajesh Upadhyay | work has been done | 74.7714 | 20.4743 | Inspected | RFI Approved | 780 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1877 | Checking Of Shuttering & Laying PCC For HPC | 127176 | 127176 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 18:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 16:00 | Rushikesh Gunjal | 2025-12-06 15:07 | Work already done | 2025-12-06 21:27 | Brajesh Upadhyay | work has been done | 74.6934 | 20.3357 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1906 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 125275 | 125275 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 13:00 | Rushikesh Gunjal | 2025-12-08 16:05 | Work already done | 2025-12-09 09:18 | Brajesh Upadhyay | work has been done | 74.7204 | 20.3758 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1905 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135210 | 135240 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 17:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 13:00 | Rushikesh Gunjal | 2025-12-08 17:07 | Work already done | 2025-12-09 09:17 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4449 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1902 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Toe Wall First Lift | 118680 | 118770 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 10:00 | Rushikesh Gunjal | 2025-12-08 15:06 | Work not done |  |  |  | 74.6875 | 20.3243 | Inspected | Inspected - Rejected - Work Not Done | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1904 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135100 | 135110 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 17:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 12:00 | Rushikesh Gunjal | 2025-12-08 17:06 | Work already done | 2025-12-09 09:17 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4449 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1881 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 138040 | 138820 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 17:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 08:00 | Rushikesh Gunjal | 2025-12-08 17:20 | Check fdd found satisfactory result | 2025-12-09 09:19 | Brajesh Upadhyay | work has been done | 74.7737 | 20.4778 | Inspected | RFI Approved | 780 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1790 | Checking Of Layout Marking & Excavation For HPC | 132386 | 132386 | BHS | Culvert | Hume Pipe Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 13:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 11:00 | Rushikesh Gunjal | 2025-12-01 16:26 | Work already done | 2025-12-02 09:09 | Brajesh Upadhyay | work has been done | 74.7555 | 20.4161 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1792 | Checking Of pipe Laying & Shuttering & pouring Concrete For Head Wall Second Lift For HPC | 120723 | 120723 | RHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 14:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 17:00 | Rushikesh Gunjal | 2025-12-02 11:18 | Work already done | 2025-12-02 16:51 | Brajesh Upadhyay | work has been done | 74.6964 | 20.3388 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1791 | Checking Of Below pipe PCC & Shuttering & Pouring Concrete For Head Wall First Lift Of HPC | 120723 | 120723 | RHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 14:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 10:00 | Rushikesh Gunjal | 2025-12-02 11:17 | Work already done | 2025-12-02 16:51 | Brajesh Upadhyay | work has been done | 74.6964 | 20.3388 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1795 | Checking Of pipe Laying & Shuttering & pouring Concrete For Head Wall Second Lift For HPC | 120737 | 120737 | RHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 15:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 09:00 | Rushikesh Gunjal | 2025-12-02 11:20 | Work already done | 2025-12-02 16:50 | Brajesh Upadhyay | work has been done | 74.6966 | 20.3389 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1798 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 120400 | 121020 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 15:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 14:00 | Rushikesh Gunjal | 2025-12-02 11:14 | Work not done |  |  |  | 74.6948 | 20.3373 | Inspected | Inspected - Rejected - Work Not Done | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1797 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 137200 | 138040 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 15:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 10:00 | Rushikesh Gunjal | 2025-12-01 16:42 | Work done | 2025-12-02 09:09 | Brajesh Upadhyay | work has been done | 74.7694 | 20.4701 | Inspected | RFI Approved | 840 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1799 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 135010 | 135050 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 15:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 10:00 | Rushikesh Gunjal | 2025-12-01 17:23 | Work already done | 2025-12-02 09:09 | Brajesh Upadhyay | work has been done | 74.7591 | 20.446 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1800 | Checking Of Shuttering & Pouring Concrete For Head Wall First Lift For HPC | 125737 | 125737 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 15:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 09:00 | Rushikesh Gunjal | 2025-12-01 15:59 | Work done | 2025-12-02 09:09 | Brajesh Upadhyay | work has been done | 74.7204 | 20.3759 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1887 | Checking Of Shuttering & Laying PCC For Drain | 135020 | 135090 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 17:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 14:00 | Kishori Lal | 2025-12-07 13:42 | Work already done. | 2025-12-08 08:38 | Brajesh Upadhyay | work has been done | 74.7585 | 20.445 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1903 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135020 | 135090 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 17:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 11:00 | Rushikesh Gunjal | 2025-12-08 17:02 | Work already done | 2025-12-09 09:17 | Brajesh Upadhyay | work has been done | 74.7585 | 20.4446 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1803 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 129540 | 129590 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 17:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 13:00 | Rushikesh Gunjal | 2025-12-01 16:13 | Work done | 2025-12-02 09:08 | Brajesh Upadhyay | work has been done | 74.7478 | 20.3985 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1889 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall second Lift Of HPC | 127176 | 127176 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 16:00 | Kishori Lal | 2025-12-07 14:28 | Work already done. | 2025-12-08 08:37 | Brajesh Upadhyay | work has been done | 74.7295 | 20.3845 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1908 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 134825 | 134980 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 15:00 | Rushikesh Gunjal | 2025-12-08 16:55 | Check fdd found satisfactory result | 2025-12-09 09:13 | Brajesh Upadhyay | work has been done | 74.758 | 20.4436 | Inspected | RFI Approved | 155 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1901 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 129650 | 129690 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 17:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 09:00 | Rushikesh Gunjal | 2025-12-08 17:55 | Work not done |  |  |  | 74.7482 | 20.3988 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1892 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall A1,A2 Third Lift For Box Culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 18:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 14:00 | Kishori Lal | 2025-12-07 13:06 | Not ready. |  |  |  | 74.782 | 20.4923 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1806 | Checking Of Reinforcement , Shuttering & pouring Concrete For retaining Wall A1, A2 First lift Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 16:00 | Rushikesh Gunjal | 2025-12-01 16:19 | Work done | 2025-12-02 09:08 | Brajesh Upadhyay | work has been done | 74.7484 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1807 | Checking Of Layout Marking , Excavation & Laying PCC For Retaining Wall Of Box culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 14:00 | Rushikesh Gunjal | 2025-12-01 16:54 | Work done | 2025-12-02 09:08 | Brajesh Upadhyay | work has been done | 74.782 | 20.4922 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1805 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 129590 | 129650 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 17:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 16:00 | Rushikesh Gunjal | 2025-12-02 15:59 | Work already done | 2025-12-02 16:50 | Brajesh Upadhyay | work has been done | 74.7477 | 20.3984 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1804 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 129650 | 129700 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 17:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 15:00 | Rushikesh Gunjal | 2025-12-03 16:53 | Work done | 2025-12-04 10:26 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7475 | 20.3981 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1912 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 129540 | 129600 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 09:00 | Rushikesh Gunjal | 2025-12-08 17:57 | Work done | 2025-12-09 09:15 | Brajesh Upadhyay | work has been done | 74.7471 | 20.3978 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1915 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 134600 | 134700 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 12:00 | Rushikesh Gunjal | 2025-12-08 16:59 | Work already done | 2025-12-09 09:15 | Brajesh Upadhyay | work has been done | 74.758 | 20.4434 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1897 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall second Lift Of HPC | 125275 | 125275 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 13:00 | Kishori Lal | 2025-12-07 17:05 | Work already done. | 2025-12-08 08:34 | Brajesh Upadhyay | work has been done | 74.7167 | 20.3734 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1910 | Checking Of Layout Marking , Excavation & Laying Pcc For Retaining Wall | 140735 | 140770 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 17:00 | Rushikesh Gunjal | 2025-12-08 17:35 | Work already done | 2025-12-09 09:14 | Brajesh Upadhyay | work has been done | 74.7817 | 20.4912 | Inspected | RFI Approved | 35 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1896 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135130 | 135150 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 12:00 | Kishori Lal | 2025-12-07 13:46 | Work already done. | 2025-12-08 08:35 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4459 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1890 | Checking Of Layout Marking , Excavation & Laying PCC For Toe Wall | 118770 | 118870 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 17:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 10:00 | Kishori Lal | 2025-12-07 16:14 | Work already done. | 2025-12-08 08:37 | Brajesh Upadhyay | work has been done | 74.6883 | 20.3246 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1911 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 134450 | 134520 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 08:00 | Rushikesh Gunjal | 2025-12-08 16:57 | Work done | 2025-12-09 09:14 | Brajesh Upadhyay | work has been done | 74.758 | 20.4436 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1796 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall second Lift Of HPC | 122640 | 122640 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-30 15:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-01 13:00 | Rushikesh Gunjal | 2025-12-02 11:30 | Work already done | 2025-12-02 16:50 | Brajesh Upadhyay | work has been done | 74.7035 | 20.3548 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1894 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 134450 | 134520 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 18:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 10:00 | Rushikesh Gunjal | 2025-12-08 16:53 | Work done | 2025-12-09 09:19 | Brajesh Upadhyay | work has been done | 74.758 | 20.4436 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1891 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall A1,A2 Crash Barrier Of MNB | 129698 | 129698 | BHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 17:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 17:00 | Kishori Lal | 2025-12-07 14:09 | Work done. | 2025-12-08 08:36 | Brajesh Upadhyay | work has been done | 74.7481 | 20.3996 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1913 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 129703 | 129800 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 10:00 | Rushikesh Gunjal | 2025-12-08 16:40 | Work not done |  |  |  | 74.7487 | 20.3999 | Inspected | Inspected - Rejected - Work Not Done | 97 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1888 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Toe Wall First Lift | 118650 | 118680 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 17:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 15:00 | Kishori Lal | 2025-12-07 16:08 | Work already done. | 2025-12-08 08:37 | Brajesh Upadhyay | work has been done | 74.6877 | 20.3245 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1914 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135240 | 135340 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 11:00 | Rushikesh Gunjal | 2025-12-08 17:05 | Work already done | 2025-12-09 09:15 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4449 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1849 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 122070 | 122070 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 10:00 | Rushikesh Gunjal | 2025-12-05 13:29 | Work already done | 2025-12-06 09:55 | Brajesh Upadhyay | work has been done | 74.7006 | 20.3498 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1873 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134780 | 134820 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 18:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 15:00 | Rushikesh Gunjal | 2025-12-06 13:20 | Work already done | 2025-12-06 21:28 | Brajesh Upadhyay | work has been done | 74.7595 | 20.4478 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2057 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119945 | 119970 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-25 14:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-26 11:00 | Rushikesh Gunjal | 2026-01-27 14:14 | No approved below the Drain wall work |  |  |  | 74.6913 | 20.3337 | Inspected | Inspected - Rejected - Work Not Done | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1876 | Checking Of Shuttering & Laying PCC For Drain | 135240 | 135265 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 18:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 16:00 | Rushikesh Gunjal | 2025-12-06 13:17 | Work already done | 2025-12-06 21:27 | Brajesh Upadhyay | work has been done | 74.7595 | 20.4477 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1879 | Checking Of Layout Marking , Excavation & Laying PCC For Toe Wall | 118650 | 118680 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 09:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 17:00 | Kishori Lal | 2025-12-07 16:05 | Work already done. | 2025-12-08 08:40 | Brajesh Upadhyay | work has been done | 74.6876 | 20.3244 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1865 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall second Lift Of HPC | 120895 | 120895 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 17:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 10:00 | Rushikesh Gunjal | 2025-12-06 14:40 | Work already done | 2025-12-06 21:29 | Brajesh Upadhyay | work has been done | 74.6996 | 20.348 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1895 | Checking Of Layout Marking , Excavation & Laying PCC For Toe Wall | 118680 | 118770 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 11:00 | Kishori Lal | 2025-12-07 16:11 | Work done. | 2025-12-08 08:35 | Brajesh Upadhyay | work has been done | 74.6876 | 20.3251 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1884 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 129540 | 129600 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 17:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 11:00 | Kishori Lal | 2025-12-07 14:17 | Work done. | 2025-12-08 08:38 | Brajesh Upadhyay | work has been done | 74.7473 | 20.3982 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1898 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 135210 | 135240 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 14:00 | Rushikesh Gunjal | 2025-12-08 17:03 | Work already done | 2025-12-09 09:19 | Brajesh Upadhyay | work has been done | 74.7585 | 20.4449 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2058 | Checking Reinforcement, shuttering and pouring concrete for Drain wall | 119945 | 119970 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-25 17:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-26 15:00 | Rushikesh Gunjal | 2026-01-27 14:14 | Repeated RFI |  |  |  | 74.6913 | 20.3337 | Inspected | Inspected - Rejected - Work Not Done | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1861 | Checking Of Layout Marking & Excavation For Drain | 135100 | 135170 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 18:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 17:00 | Rushikesh Gunjal | 2025-12-05 16:41 | Work already done | 2025-12-06 09:53 | Brajesh Upadhyay | work has been done | 74.7585 | 20.4452 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1859 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 135340 | 135400 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 16:00 | Rushikesh Gunjal | 2025-12-05 16:35 | Work done | 2025-12-06 09:53 | Brajesh Upadhyay | work has been done | 74.7602 | 20.4498 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1857 | Checking Of Layout Marking & Excavation For Drain | 135020 | 135045 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-04 18:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-05 15:00 | Rushikesh Gunjal | 2025-12-05 16:40 | Work already done | 2025-12-06 09:54 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4452 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1883 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 129600 | 129650 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 17:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 10:00 | Kishori Lal | 2025-12-07 14:15 | Work already done. | 2025-12-08 08:39 | Brajesh Upadhyay | work has been done | 74.7479 | 20.3986 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1878 | Checking Of Layout Marking , Excavation & Laying PCC For Toe Wall | 119060 | 119120 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 09:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 16:00 | Kishori Lal | 2025-12-07 16:19 | Work already done. | 2025-12-08 08:41 | Brajesh Upadhyay | work has been done | 74.6891 | 20.3253 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1866 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 121908 | 121908 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-05 17:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-06 11:00 | Kishori Lal | 2025-12-07 16:48 | Work already done. | 2025-12-08 08:42 | Brajesh Upadhyay | work has been done | 74.7003 | 20.3482 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1899 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 129703 | 129800 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-06 18:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-07 15:00 | Rushikesh Gunjal | 2025-12-08 16:39 | Work not done |  |  |  | 74.7486 | 20.3997 | Inspected | Inspected - Rejected - Work Not Done | 97 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1909 | Checking Of Layout Marking , Excavation & Laying Pcc For Retaining Wall | 140810 | 140840 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-07 18:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-08 16:00 | Rushikesh Gunjal | 2025-12-08 17:40 | Work not done upto mention Chainage |  |  |  | 74.7819 | 20.4913 | Inspected | Inspected - Rejected - Work Not Done | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1931 | Checking Of Layout Marking , Excavation & Laying Pcc For Retaining Wall | 140634 | 140643 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 17:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 13:00 | Kishori Lal | 2025-12-10 12:18 | Work already done. | 2025-12-10 19:00 | Brajesh Upadhyay | work has been done | 74.7814 | 20.4895 | Inspected | RFI Approved | 9 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1934 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall second Lift Of HPC | 135821 | 135821 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 18:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 14:00 | Kishori Lal | 2025-12-19 16:45 | Alignment not sa per drawing. |  |  |  | 74.7612 | 20.4518 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1932 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 133023 | 133023 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 18:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 14:00 | Kishori Lal | 2025-12-10 13:51 | Alignment of HPC Head Wall not as per design and drawing. |  |  |  | 74.7585 | 20.4271 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1930 | Checking Of Layout Marking , Excavation & Laying Pcc For Retaining Wall | 140515 | 140600 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 16:00 | Kishori Lal | 2025-12-10 12:13 | Work already done. | 2025-12-10 19:00 | Brajesh Upadhyay | work has been done | 74.7791 | 20.4869 | Inspected | RFI Approved | 85 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1928 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 140930 | 141690 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 17:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 13:00 | Rushikesh Gunjal | 2025-12-09 15:51 | Work not done |  |  |  | 74.7823 | 20.4929 | Inspected | Inspected - Rejected - Work Not Done | 760 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1936 | Checking Of Laying DLC Top | 117000 | 117030 | LHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-09 17:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-10 12:00 | Rushikesh Gunjal | 2025-12-10 16:30 | Work done | 2025-12-10 18:59 | Brajesh Upadhyay | work has been done | 74.6728 | 20.318 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1939 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 140120 | 140928 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-09 18:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-10 10:00 | Rushikesh Gunjal | 2025-12-10 17:14 | Work done | 2025-12-10 18:59 | Brajesh Upadhyay | work has been done | 74.7753 | 20.4834 | Inspected | RFI Approved | 808 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1943 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall second Lift Of HPC | 138780 | 138780 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-09 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-10 13:00 | Kishori Lal | 2025-12-10 12:28 | Work done. | 2025-12-10 18:58 | Brajesh Upadhyay | work has been done | 74.7735 | 20.4763 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1940 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 129650 | 129690 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-09 18:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-10 11:00 | Kishori Lal | 2025-12-10 14:05 | Work not done. |  |  |  | 74.7482 | 20.3986 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1944 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134520 | 134600 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-09 18:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-10 14:00 | Kishori Lal | 2025-12-10 13:02 | Only 40 Meter work done from chainage 134+520 to 134+560 RHS. | 2025-12-10 18:57 | Brajesh Upadhyay | work has been done | 74.758 | 20.4404 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1942 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135020 | 135045 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-09 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-10 15:00 | Kishori Lal | 2025-12-10 12:46 | Work already done. | 2025-12-10 18:58 | Brajesh Upadhyay | work has been done | 74.7586 | 20.445 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1941 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 137850 | 138720 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-09 18:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-10 13:00 | Rushikesh Gunjal | 2025-12-10 17:13 | Check FDD found Satisfactory result | 2025-12-10 18:58 | Brajesh Upadhyay | work has been done | 74.7753 | 20.4834 | Inspected | RFI Approved | 870 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1938 | Checking Reinforcement, shuttering and pouring concrete for Raft Of Retaining Wall | 140515 | 140600 | RHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-09 17:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-10 09:00 | Kishori Lal | 2025-12-10 12:15 | Work already done. | 2025-12-10 18:59 | Brajesh Upadhyay | work has been done | 74.781 | 20.4884 | Inspected | RFI Approved | 85 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1937 | Checking Reinforcement, shuttering and pouring concrete for Raft Of Retaining Wall | 140634 | 140643 | LHS | Drain | Drainage and Protective Works | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-09 17:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-10 08:00 | Kishori Lal | 2025-12-10 12:19 | Work already done. | 2025-12-10 18:59 | Brajesh Upadhyay | work has been done | 74.7814 | 20.4896 | Inspected | RFI Approved | 9 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1922 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120232 | 120320 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 17:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 10:00 | Kishori Lal | 2025-12-10 15:29 | Work already done. | 2025-12-10 19:00 | Brajesh Upadhyay | work has been done | 74.6917 | 20.3354 | Inspected | RFI Approved | 88 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1924 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 125900 | 126500 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 17:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 09:00 | Rushikesh Gunjal | 2025-12-10 16:52 | Check FDD and found satisfactory result | 2025-12-10 19:00 | Brajesh Upadhyay | work has been done | 74.7241 | 20.3815 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1923 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 129350 | 129500 | LHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 17:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 08:00 | Rushikesh Gunjal | 2025-12-10 17:13 | Work done | 2025-12-10 19:00 | Brajesh Upadhyay | work has been done | 74.7753 | 20.4834 | Inspected | RFI Approved | 150 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1920 | Checking Reinforcement, shuttering and pouring concrete for Retailing Wall Final Lift | 132960 | 133000 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 16:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 13:00 | Kishori Lal | 2025-12-10 13:57 | Work already done. | 2025-12-10 19:01 | Brajesh Upadhyay | work has been done | 74.758 | 20.427 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1929 | Checking Of Laying DLC Top | 117000 | 117020 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 17:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 15:00 | Rushikesh Gunjal | 2025-12-09 17:41 | Work done | 2025-12-09 18:59 | Brajesh Upadhyay | work has been done. | 74.6729 | 20.3178 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1925 | Checking Of Laying PQC Top | 119000 | 119714 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 17:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 10:00 | Rushikesh Gunjal | 2025-12-09 11:57 | Work done | 2025-12-09 19:00 | Brajesh Upadhyay | work has been done. | 74.6863 | 20.3235 | Inspected | RFI Approved | 714 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1921 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120140 | 120225 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 17:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 09:00 | Kishori Lal | 2025-12-10 15:29 | Work already done. | 2025-12-10 19:00 | Brajesh Upadhyay | work has been done | 74.6911 | 20.3361 | Inspected | RFI Approved | 85 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1926 | Checking Of Level & FDD test for GSB Top Layer | 117000 | 117020 | LHS | Road | Rigid Road | GSB | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 17:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 11:00 | Rushikesh Gunjal | 2025-12-09 17:35 | Work already done | 2025-12-09 19:01 | Brajesh Upadhyay | work has been done. | 74.6729 | 20.3179 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2060 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 119945 | 119970 | LHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-27 18:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-28 11:30 | Rushikesh Gunjal | 2026-01-28 11:49 | Work done | 2026-01-29 11:07 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.6914 | 20.3338 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1935 | Checking Of Laying PQC Top | 118340 | 119000 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-09 17:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-10 14:00 | Rushikesh Gunjal | 2025-12-10 12:28 | Work done | 2025-12-10 18:59 | Brajesh Upadhyay | work has been done | 74.6835 | 20.3226 | Inspected | RFI Approved | 660 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1945 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134600 | 134700 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-09 18:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-10 17:00 | Kishori Lal | 2025-12-10 12:57 | Only 60 Meter work done from chainage 134+640 to 134+700 RHS. | 2025-12-10 18:57 | Brajesh Upadhyay | work has been done | 74.7578 | 20.4414 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1946 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 140120 | 140925 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-10 17:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-11 10:00 | Rushikesh Gunjal | 2025-12-11 16:41 | Compaction not achieve |  |  |  | 74.7813 | 20.4892 | Inspected | Inspected - Fail | 805 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1948 | Checking Of Level & FDD Test For Earthen Shoulder Top Layer | 137850 | 138720 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-10 17:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-11 13:00 | Rushikesh Gunjal | 2025-12-11 16:20 | Compaction not achieved and design slope also doesn t maintain |  |  |  | 74.7724 | 20.4757 | Inspected | Inspected - Fail | 870 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1950 | Checking Of Shuttering & Pouring Concrete For Head Wall Final Lift of HPC | 138780 | 138780 | BHS | Culvert | Hume Pipe Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-10 18:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-11 14:00 | Rushikesh Gunjal | 2025-12-11 16:14 | Work already done | 2025-12-12 08:24 | Brajesh Upadhyay | work has been done | 74.7725 | 20.4758 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1952 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 136980 | 137850 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-10 18:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-11 11:00 | Rushikesh Gunjal | 2025-12-11 16:10 | Camber and compaction not maintain |  |  |  | 74.7659 | 20.4621 | Inspected | Inspected - Fail | 870 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1951 | Checking Of Level & FDD Test For Earthen Shoulder 1st Layer | 139560 | 140120 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-10 18:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-11 09:00 | Rushikesh Gunjal | 2025-12-11 16:46 | Compaction not achieved Shoulder is not in desirable camber |  |  |  | 74.7814 | 20.4893 | Inspected | Inspected - Fail | 560 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1949 | Checking Reinforcement, shuttering and pouring concrete for Retaining Wall First lift | 140634 | 140643 | LHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-10 17:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-11 15:00 | Rushikesh Gunjal | 2025-12-11 16:37 | Work already done | 2025-12-12 08:24 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4895 | Inspected | RFI Approved | 9 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1947 | Checking Of Reinforcement , Shuttering & Pouring Concrete For First lift Of Retaining Wall | 140515 | 140600 | RHS | Drain | Drainage and Protective Works | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-10 17:56 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-11 11:00 | Rushikesh Gunjal | 2025-12-11 16:39 | Work already done | 2025-12-12 08:24 | Brajesh Upadhyay | work has been done | 74.7814 | 20.4891 | Inspected | RFI Approved | 85 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1953 | Checking Of Layout Marking , Excavation & Laying PCC For Toe Wall | 132675 | 132755 | LHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-11 08:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-12 16:00 | Rushikesh Gunjal | 2025-12-11 15:57 | Pcc Work not done |  |  |  | 74.7585 | 20.424 | Inspected | Inspected - Rejected - Work Not Done | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1954 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall A1,A2 Third Lift For Box Culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-11 08:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-11 16:00 | Rushikesh Gunjal | 2025-12-11 16:32 | Work done | 2025-12-12 08:23 | Brajesh Upadhyay | work has been done | 74.7821 | 20.4921 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1956 | Checking Reinforcement, shuttering and pouring concrete for retaining Wall Final Lift | 140515 | 140600 | RHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-11 17:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-12 11:00 | Kishori Lal | 2025-12-12 11:42 | Work already done. | 2025-12-18 09:23 | Brajesh Upadhyay | work has been done | 74.7814 | 20.4892 | Inspected | RFI Approved | 85 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1957 | Checking Reinforcement, shuttering and pouring concrete for retaining Wall Final Lift | 140634 | 140643 | LHS | Drain | Drainage and Protective Works | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-11 18:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-12 13:00 | Kishori Lal | 2025-12-12 11:44 | Work already done. | 2025-12-18 09:23 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4893 | Inspected | RFI Approved | 9 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1955 | Checking Of Laying PQC Top | 117750 | 118340 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-11 17:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-12 14:00 | Rushikesh Gunjal | 2025-12-13 15:07 | Work done | 2025-12-18 09:24 | Brajesh Upadhyay | work has been done | 74.6788 | 20.3213 | Inspected | RFI Approved | 590 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1958 | Checking Of Layout Marking , Excavation & Laying PCC For Toe Wall | 132675 | 132755 | LHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-12 08:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-12 14:00 | Rushikesh Gunjal | 2025-12-20 13:43 | Work already done | 2025-12-20 21:03 | Brajesh Upadhyay | work has been done | 74.7585 | 20.4246 | Inspected | RFI Approved | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1959 | Checking Of Laying PQC Top | 117180 | 117750 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-13 08:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-13 16:00 | Rushikesh Gunjal | 2025-12-18 11:09 | Work done | 2025-12-18 20:25 | Brajesh Upadhyay | work has been done | 74.6731 | 20.3181 | Inspected | RFI Approved | 570 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1961 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 134980 | 135040 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-13 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-14 10:00 | Rushikesh Gunjal | 2025-12-18 16:49 | Wrong Chainage In mention Chainage HP culvert exists |  |  |  | 74.7587 | 20.4449 | Inspected | Inspected - Rejected - Work Not Done | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2028 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Approach Slab Casting A1,A2 Of MNB | 129698 | 129698 | RHS | Bridge | Minor Bridge Reconstruction | Approaches | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-08 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-09 14:00 | Kishori Lal | 2026-01-16 12:17 | Work done. | 2026-01-17 08:52 | Brajesh Upadhyay | work has been done | 74.7482 | 20.3992 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2034 | Checking of Layout Marking , Excavation & Laying PCC for Anchor beam A1,A2 of BC | 140928 | 140928 | RHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-13 17:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-14 10:00 | Kishori Lal | 2026-01-16 11:41 | Work done. | 2026-01-17 08:53 | Brajesh Upadhyay | work has been done | 74.7817 | 20.491 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2036 | Checking Of reinforcement , Shutterting & Pouring Concrete For Anchor beam A1,A2 Of BC | 140928 | 140928 | RHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-13 17:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-14 18:00 | Kishori Lal | 2026-01-16 11:42 | Work done. | 2026-01-17 08:54 | Brajesh Upadhyay | work has been done | 74.7822 | 20.4921 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1986 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120380 | 120400 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-22 17:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-23 14:00 | Rushikesh Gunjal | 2025-12-24 10:08 | Found honeycombing & stone as a clear cover |  |  |  | 74.6941 | 20.3364 | Inspected | Inspected - Fail | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1987 | Checking Of Layout Marking , Excavation & Laying PCC For Toe Wall | 129620 | 129675 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-23 09:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-23 16:00 | Rushikesh Gunjal | 2025-12-24 16:54 | Work not done |  |  |  | 74.7481 | 20.3987 | Inspected | Inspected - Rejected - Work Not Done | 55 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1965 | Checking Of Reinforcement, Shuttering & Pouring concrete For Retaining Wall A1,A2 Final Lift Of Box Culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-15 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-16 14:00 | Kishori Lal | 2025-12-19 16:53 | Satisfactory. | 2025-12-19 20:25 | Brajesh Upadhyay | work has been done | 74.7821 | 20.492 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1967 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Crash Barrier Of Box Culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-15 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-16 17:00 | Kishori Lal | 2025-12-19 16:55 | Satisfactory. | 2025-12-19 20:25 | Brajesh Upadhyay | work has been done | 74.7821 | 20.4921 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2042 | Checking of Reinforcement, Shuttering & Pouring Concrete for Anchor Beam A1,A2 of BC | 133216 | 133216 | RHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-17 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-18 11:00 | Kishori Lal | 2026-01-20 12:21 | Work already done. | 2026-01-21 11:13 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4287 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2029 | Checking Reinforcement, shuttering and pouring concrete for Mid Wall 2nd Lift Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-08 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-09 11:00 | Kishori Lal | 2026-01-16 14:49 | Work done. | 2026-01-17 08:52 | Brajesh Upadhyay | work has been done | 74.7076 | 20.3636 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1969 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Retaining Wall Crash Barrier Of Box Culvert | 140928 | 140928 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-16 17:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-17 14:00 | Rushikesh Gunjal | 2025-12-18 17:18 | Work done | 2025-12-18 20:24 | Brajesh Upadhyay | work has been done | 74.7582 | 20.429 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1970 | Checking Reinforcement, shuttering and pouring concrete for Anchor Beam For Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-16 17:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-17 16:00 | Rushikesh Gunjal | 2025-12-18 12:57 | Work done without inspection |  |  |  | 74.7827 | 20.4995 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1973 | Checking Of Reinforcement, shuttering and pouring concrete for Drain Raft | 135140 | 135170 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-16 17:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-17 15:00 | Rushikesh Gunjal | 2025-12-18 16:45 | Work already done | 2025-12-18 20:23 | Brajesh Upadhyay | work has been done | 74.7588 | 20.4453 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1972 | Checking Of Laying DLC Top | 134460 | 134650 | RHS | Road | Rigid Road | DLC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-16 17:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-17 12:00 | Rushikesh Gunjal | 2025-12-18 13:45 | Work done | 2025-12-18 20:24 | Brajesh Upadhyay | work has been done | 74.7582 | 20.4285 | Inspected | RFI Approved | 190 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1964 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 135140 | 135170 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-15 16:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-16 14:00 | Rushikesh Gunjal | 2025-12-18 16:46 | Work already done | 2025-12-18 20:25 | Brajesh Upadhyay | work has been done | 74.7588 | 20.4453 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1962 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 135210 | 135250 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-15 16:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-16 11:00 | Kishori Lal | 2025-12-19 16:43 | Wrong RFI |  |  |  | 74.7601 | 20.4493 | Inspected | Inspected - Fail | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1966 | Checking Of Layout Marking , Excavation & Laying PCC For Anchor Beam Of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-15 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-16 15:00 | Kishori Lal | 2025-12-19 17:07 | Work already done. | 2025-12-19 20:25 | Brajesh Upadhyay | work has been done | 74.7828 | 20.4995 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1960 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 134640 | 134700 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-13 15:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-14 13:00 | Rushikesh Gunjal | 2025-12-18 16:53 | Work already done | 2025-12-18 20:25 | Brajesh Upadhyay | work has been done | 74.758 | 20.4423 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1975 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 134710 | 134750 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-17 18:00 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-18 13:00 | Rushikesh Gunjal | 2025-12-18 16:55 | Wrong Chainage In mention Chainage HP culvert is exist |  |  |  | 74.758 | 20.4423 | Inspected | Inspected - Rejected - Work Not Done | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1971 | Checking Of Laying PQC Top | 117000 | 117060 | RHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-16 17:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-17 14:00 | Rushikesh Gunjal | 2025-12-18 11:11 | Work done | 2025-12-18 20:24 | Brajesh Upadhyay | work has been done | 74.6732 | 20.3181 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1988 | Checking Of Layout Marking , Excavation & Laying PCC For MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-23 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-24 10:00 | Kishori Lal | 2025-12-24 16:38 | PCC work not done. |  |  |  | 74.7286 | 20.384 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1976 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 120380 | 120400 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-18 17:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-19 13:00 | Rushikesh Gunjal | 2025-12-19 10:37 | Work done | 2025-12-19 20:25 | Brajesh Upadhyay | work has been done | 74.6941 | 20.3366 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2040 | Checking Of Layout marking, excavation & Laying PCC for ANCHOR Beam A1,A2 of BC | 133216 | 133216 | RHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-16 17:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-17 13:00 | Rushikesh Gunjal | 2026-01-20 11:34 | Work already done | 2026-01-21 11:14 | Brajesh Upadhyay | work has been done | 74.7583 | 20.429 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1974 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135140 | 135150 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-17 14:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-18 14:00 | Rushikesh Gunjal | 2025-12-18 16:50 | Work already done | 2025-12-18 20:23 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4451 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1968 | Checking Of Laying PQC Top | 117000 | 117180 | LHS | Road | Rigid Road | PQC | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-16 09:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-16 15:00 | Rushikesh Gunjal | 2025-12-18 11:10 | Work done | 2025-12-18 20:25 | Brajesh Upadhyay | work has been done | 74.6732 | 20.3181 | Inspected | RFI Approved | 180 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1963 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 135100 | 135130 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-15 16:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-16 13:00 | Rushikesh Gunjal | 2025-12-18 16:47 | Work already done | 2025-12-18 20:25 | Brajesh Upadhyay | work has been done | 74.7588 | 20.4453 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1977 | Checking Of Reinforcement, shuttering and pouring concrete for Anchor Beam Of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-19 12:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-19 16:00 | Rushikesh Gunjal | 2025-12-20 13:22 | Work done without inspection |  |  |  | 74.7828 | 20.4996 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1933 | Checking Of Pipe Laying & Shuttering , Pouring Concrete For Head Wall second Lift Of HPC | 136078 | 136078 | BHS | Culvert | Hume Pipe Culvert | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-08 18:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-09 17:00 | Kishori Lal | 2025-12-19 16:47 | Work already done without checking. |  |  |  | 74.7623 | 20.4539 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1978 | Checking Of Layout Marking & Laying PCC For Terminal Slab Of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-19 17:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-20 14:00 | Rushikesh Gunjal | 2025-12-20 13:23 | Work done | 2025-12-20 21:03 | Brajesh Upadhyay | work has been done | 74.7828 | 20.4996 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1979 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 120380 | 120400 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-19 18:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-20 11:00 | Rushikesh Gunjal | 2025-12-20 11:14 | Work done | 2025-12-20 21:03 | Brajesh Upadhyay | work has been done | 74.6942 | 20.3366 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1980 | Checking Of Layout Marking , Excavation & Laying PCC For Toe Wall | 120400 | 120415 | RHS | Wall | Retaining Wall/Toe Wall | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-19 18:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-20 15:00 | Rushikesh Gunjal | 2025-12-20 11:12 | Work done | 2025-12-20 21:03 | Brajesh Upadhyay | work has been done | 74.6943 | 20.3367 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1981 | Checking Of Reinforcement , Shuttering & Pouring Concrete For Terminal Slab Of Box Culvert | 141753 | 141753 | BHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-20 18:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-21 14:00 | Kishori Lal | 2025-12-24 16:57 | Work already done. | 2025-12-25 09:14 | Brajesh Upadhyay | work has been done | 74.7827 | 20.4995 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1982 | Checking of Reinforcement, shuttering & pouring concrete for Drain Raft | 120380 | 120400 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-20 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-21 15:00 | Rushikesh Gunjal | 2025-12-22 13:43 | Work done | 2025-12-22 21:03 | Brajesh Upadhyay | work has been done | 74.6941 | 20.3365 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1983 | Checking Reinforcement, shuttering and pouring concrete for Toe Wall First Lift | 120400 | 120415 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-20 18:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-21 11:00 | Rushikesh Gunjal | 2025-12-24 10:05 | Wrong RFI There is only one lift i.e. final lift |  |  |  | 74.6942 | 20.3366 | Inspected | Inspected - Rejected - Work Not Done | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2038 | Checking of reinforcement Shuttering & Pouring concrete for Drain Raft | 129650 | 129690 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-16 17:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-17 10:00 | Rushikesh Gunjal | 2026-01-19 17:28 | Work done | 2026-01-20 09:23 | Brajesh Upadhyay | work has been done | 74.7482 | 20.399 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2033 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Terminal slab A1,A2 of BC | 133216 | 133216 | LHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-12 17:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-13 15:00 | Kishori Lal | 2026-01-16 12:05 | Work done. | 2026-01-17 08:53 | Brajesh Upadhyay | work has been done | 74.7582 | 20.429 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2035 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 129650 | 129690 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-13 17:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-14 13:00 | Kishori Lal | 2026-01-16 12:19 | Work done. | 2026-01-17 08:53 | Brajesh Upadhyay | work has been done | 74.7483 | 20.3992 | Inspected | RFI Approved | 40 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1984 | Checking Of Reinforcement, shuttering and pouring concrete for Toe Wall Final Lift | 120400 | 120415 | RHS | Wall | Retaining Wall/Toe Wall | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-21 17:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-22 13:00 | Rushikesh Gunjal | 2025-12-24 10:03 | Work done | 2025-12-25 09:13 | Brajesh Upadhyay | work has been done | 74.6942 | 20.3365 | Inspected | RFI Approved | 15 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2037 | Checking Of Layout Marking , Excavation & Laying PCC For terminal Slab A1,A2 Of BC | 140928 | 140928 | RHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-16 08:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-16 17:00 | Kishori Lal | 2026-01-16 17:08 | Work done. | 2026-01-17 08:54 | Brajesh Upadhyay | work has been done | 74.7821 | 20.4923 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1985 | Checking Of Reinforcement, shuttering and pouring concrete for Drain Wall | 120380 | 120400 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-12-21 17:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-12-22 14:00 | Rushikesh Gunjal | 2025-12-22 13:44 | Work done | 2025-12-22 21:03 | Brajesh Upadhyay | work has been done | 74.6941 | 20.3365 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1490 | Checking Of Level & FDD Test For Subgrade Top | 122500 | 123150 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:07 | Rushikesh Gunjal | 2025-10-28 12:24 | Work was already done | 2025-10-28 18:45 | Brajesh Upadhyay | work has been done | 74.7026 | 20.3532 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1521 | Checking Of Level & FDD Test For Subgrade Top | 127000 | 127800 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:38 | Rushikesh Gunjal | 2025-10-28 15:23 | Work was already done | 2025-10-28 18:41 | Brajesh Upadhyay | work has been done | 74.7327 | 20.3873 | Inspected | RFI Approved | 800 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1525 | Checking Of Level & FDD Test For Subgrade Top | 128900 | 129380 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:40 | Rushikesh Gunjal | 2025-10-28 15:42 | Work already done | 2025-10-28 18:41 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 480 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1522 | Checking Of Level & FDD Test For Subgrade Top | 127800 | 128000 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:38 | Rushikesh Gunjal | 2025-10-28 15:24 | Work was already done | 2025-10-28 18:41 | Brajesh Upadhyay | work has been done | 74.7327 | 20.3873 | Inspected | RFI Approved | 200 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1513 | Checking Of Level & FDD Test For Subgrade Top | 121800 | 122500 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:30 | Rushikesh Gunjal | 2025-10-28 12:09 | Work was already done | 2025-10-28 18:43 | Brajesh Upadhyay | work has been done | 74.6994 | 20.348 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1501 | Checking Of Level & FDD Test For Subgrade Top | 128900 | 129400 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:19 | Rushikesh Gunjal | 2025-10-28 15:40 | Work was already done | 2025-10-28 18:44 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1499 | Checking Of Level & FDD Test For Subgrade Top | 127850 | 128440 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:17 | Rushikesh Gunjal | 2025-10-28 15:21 | Work was already done | 2025-10-28 18:44 | Brajesh Upadhyay | work has been done | 74.7327 | 20.3873 | Inspected | RFI Approved | 590 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1489 | Checking Of Level & FDD Test For Subgrade Top | 122000 | 122500 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:06 | Rushikesh Gunjal | 2025-10-28 12:31 | Work was already done | 2025-10-28 18:45 | Brajesh Upadhyay | work has been done | 74.7033 | 20.3548 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1147 | Checking Of Level & FDD Test For Subgrade Top | 129400 | 129800 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-31 18:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-01 16:00 | Saurabh SE | 2025-09-01 16:19 | Work done | 2025-09-01 20:49 | Brajesh Upadhyay | work has been done | 74.7476 | 20.3983 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1198 | Checking Of Level & FDD test for Subgrade Top Layer | 119750 | 120400 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 10:30 | Rushikesh Gunjal | 2025-09-13 16:51 | OK | 2025-09-14 11:07 | Brajesh Upadhyay | work has been done | 74.6961 | 20.338 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1200 | Checking Of Level & FDD Test For Subgrade Top | 119750 | 120400 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 12:30 | Rushikesh Gunjal | 2025-09-13 16:53 | Ok | 2025-09-14 11:09 | Brajesh Upadhyay | work has been done | 74.696 | 20.3381 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1124 | Checking Of Level & FDD Test For Subgrade Top | 138600 | 139160 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-29 16:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-30 10:30 | Rushikesh Gunjal | 2025-09-10 17:59 | Check found OK | 2025-09-14 12:11 | Brajesh Upadhyay | work has been done | 74.7753 | 20.4828 | Inspected | RFI Approved | 560 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1125 | Checking Of Level & FDD Test For Subgrade Top | 139160 | 139900 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-29 16:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-30 16:30 | Rushikesh Gunjal | 2025-09-10 18:01 | Check found OK | 2025-09-14 12:11 | Brajesh Upadhyay | work has been done | 74.7754 | 20.4828 | Inspected | RFI Approved | 740 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/485 | Checking Level and FDD test for Subgrade Top | 134480 | 135230 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 14:00 | Rushikesh Gunjal | 2025-05-21 11:59 | Checked and ok | 2025-05-21 17:04 | Brajesh Upadhyay | Work has been done | 74.7547 | 20.4143 | Inspected | RFI Approved | 750 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1146 | Checking Of Level & FDD Test For Subgrade Top | 120400 | 121020 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-31 18:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-01 09:15 | Saurabh SE | 2025-09-01 12:13 | BT not dismantle |  |  |  | 74.6942 | 20.3368 | Inspected | Inspected - Fail | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/484 | Checking Level and FDD test for Subgrade Top | 137870 | 138380 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 13:00 | Saurabh SE | 2025-05-16 17:13 | Checked and found ok | 2025-05-16 19:28 | Brajesh Upadhyay | work has been done | 74.7683 | 20.4677 | Inspected | RFI Approved | 510 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/441 | Checking Level and FDD test for Subgrade Top | 134490 | 135230 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 19:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 17:30 | Rushikesh Gunjal | 2025-05-17 11:41 | Ok | 2025-05-17 18:05 | Brajesh Upadhyay | Work has been done | 74.7579 | 20.4413 | Inspected | RFI Approved | 740 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/478 | Checking Level and FDD test for Subgrade Top | 135230 | 135750 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 17:30 | Rushikesh Gunjal | 2025-05-17 11:49 | Checked and found ok | 2025-05-17 18:03 | Brajesh Upadhyay | Work has been done | 74.7601 | 20.4495 | Inspected | RFI Approved | 520 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/480 | Checking Level and FDD test for Subgrade Top | 137100 | 137870 | BHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 23:15 | Rushikesh Gunjal | 2025-05-16 17:01 | Checked and found ok | 2025-05-17 18:02 | Brajesh Upadhyay | Work has been done | 74.766 | 20.4631 | Inspected | RFI Approved | 770 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/442 | Checking Level and FDD test for Subgrade Top | 135750 | 136380 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 08:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 18:00 | Rushikesh Gunjal | 2025-05-16 16:50 | Checked and found ok | 2025-05-17 18:04 | Brajesh Upadhyay | Work has been done | 74.7631 | 20.4557 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/486 | Checking Level and FDD test for Subgrade Top | 135750 | 136380 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 15:00 | Saurabh SE | 2025-05-16 16:52 | Level and FDD found ok | 2025-05-17 18:01 | Brajesh Upadhyay | Work has been done | 74.7631 | 20.4556 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/439 | Checking FDD test for Subgrade 1st layer | 134480 | 135230 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 19:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 16:00 | Rushikesh Gunjal | 2025-05-17 11:36 | Ok | 2025-05-17 18:07 | Brajesh Upadhyay | Work has been done | 74.758 | 20.4407 | Inspected | RFI Approved | 750 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/436 | Checking FDD test for Subgrade 1st layer | 135230 | 135750 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 19:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 13:00 | Rushikesh Gunjal | 2025-05-17 11:47 | Ok | 2025-05-17 18:08 | Brajesh Upadhyay | Work has been done | 74.76 | 20.4491 | Inspected | RFI Approved | 520 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/440 | Checking FDD test for Subgrade 1st layer | 135750 | 136380 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 19:53 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 17:00 | Rushikesh Gunjal | 2025-05-16 16:42 | Checked and found ok | 2025-05-17 18:06 | Brajesh Upadhyay | Work has been done | 74.7631 | 20.4556 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/514 | Checking Level and FDD test for Subgrade Top | 138950 | 139590 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 12:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-13 17:30 | Rushikesh Gunjal | 2025-05-19 16:04 | Checked and found ok | 2025-05-19 18:16 | Brajesh Upadhyay | Work done | 74.7741 | 20.4783 | Inspected | RFI Approved | 640 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/100 | FDD and Leval Checking of Subgrade 1st Top | 133260 | 134600 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:41 | Brajesh Upadhyay | 2025-02-08 11:30 | Brajesh Upadhyay | 2025-03-07 14:41 | Work done successfully. | 2025-03-07 14:41 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 1340 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/018 | Checking FDD test for Subgrade 1st layer | 122000 | 122500 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-17 20:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-18 12:00 | Rushikesh Gunjal | 2025-02-19 12:56 | Work not done Subgrade 1st layer completed upto 122+200 and FDD result not yet | 2025-02-19 17:29 | Brajesh Upadhyay | ITF staff available at site | 74.7006 | 20.3499 | Inspected | RFI Not Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/025 | Checking FDD test for Subgrade 1st layer | 121350 | 121900 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-20 08:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-20 12:30 | Rushikesh Gunjal | 2025-02-20 15:04 | Completed | 2025-02-20 18:24 | Brajesh Upadhyay | work has been done | 74.699 | 20.3466 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/023 | Checking FDD test for Subgrade 1st layer | 121020 | 121350 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-18 20:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-19 12:04 |  | 2025-02-24 12:41 | Check and found ok | 2025-02-24 19:19 | Brajesh Upadhyay | FDD Check found Satisfactory | 74.6995 | 20.3436 | Inspected | RFI Approved | 330 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/022 | Checking FDD test for Subgrade 1st layer | 121450 | 121800 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-18 20:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-19 14:00 | Rushikesh Gunjal | 2025-02-20 15:13 | Over size material used in bed | 2025-02-20 18:54 | Brajesh Upadhyay | instructed for removal of oversize bolders | 74.6991 | 20.3466 | Inspected | RFI Not Approved | 350 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/030 | Checking FDD test for Subgrade 1st layer | 121900 | 122000 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-02-21 08:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-02-21 11:19 |  | 2025-02-23 11:39 | Oversized material used in subgrade bed. | 2025-02-24 10:27 | Brajesh Upadhyay | due to oversize boulders RFI not done | 74.7007 | 20.3504 | Inspected | RFI Not Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/050 | Checking FDD test for Subgrade 1st layer | 121020 | 121580 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-02 11:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-02 12:00 | Rushikesh Gunjal | 2025-03-03 15:30 | Completed | 2025-03-04 11:29 | Brajesh Upadhyay | work done | 74.6984 | 20.3412 | Inspected | RFI Approved | 560 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/091 | FDD and Leval Checking of Subgrade Top | 129800 | 133170 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:24 | Brajesh Upadhyay | 2025-02-14 10:15 | Brajesh Upadhyay | 2025-03-07 14:24 | Work done successfully. | 2025-03-07 14:24 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 3370 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/092 | FDD and Leval Checking of Subgrade Top | 133270 | 134800 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:25 | Brajesh Upadhyay | 2025-02-13 11:15 | Brajesh Upadhyay | 2025-03-07 14:25 | Work done successfully. | 2025-03-07 14:25 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 1530 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/096 | FDD and Leval Checking of Subgrade 1st Top | 133260 | 134700 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:33 | Brajesh Upadhyay | 2025-02-11 10:45 | Brajesh Upadhyay | 2025-03-07 14:33 | Work done successfully. | 2025-03-07 14:33 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 1440 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/099 | FDD and Leval Checking of Subgrade 1st Top | 129800 | 133180 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:39 | Brajesh Upadhyay | 2025-02-12 10:10 | Brajesh Upadhyay | 2025-03-07 14:39 | Work done successfully. | 2025-03-07 14:39 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 3380 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/053 | Checking Level and FDD test for Subgrade Top | 121020 | 121500 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-06 22:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 10:30 | Rushikesh Gunjal | 2025-03-07 15:23 | Checked found ok | 2025-03-08 10:37 | Brajesh Upadhyay | work done | 74.6984 | 20.3408 | Inspected | RFI Approved | 480 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/088 | FDD and Leval Checking of Subgrade Top | 133260 | 135500 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 14:17 | Brajesh Upadhyay | 2025-02-12 11:00 | Brajesh Upadhyay | 2025-03-07 14:17 | Work done successfully. | 2025-03-07 14:17 | Brajesh Upadhyay | Approved | 0 | 0 | Inspected | RFI Approved | 2240 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/054 | Checking Level and FDD test for Subgrade Top | 122000 | 122500 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-06 22:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 11:38 | Rushikesh Gunjal | 2025-04-05 16:10 | Checked and found ok | 2025-04-07 17:16 | Brajesh Upadhyay | work done | 74.7574 | 20.4197 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/064 | Checking FDD test for Subgrade 1st layer | 131500 | 132000 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-06 23:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 13:17 | Rushikesh Gunjal | 2025-03-07 12:28 | Work done and found satisfactory result | 2025-04-07 17:15 | Brajesh Upadhyay | work done | 74.7548 | 20.4144 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/065 | Checking FDD test for Subgrade 1st layer | 121020 | 121350 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 12:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 15:00 | Rushikesh Gunjal | 2025-03-11 16:42 | Checked and ok | 2025-04-07 17:17 | Brajesh Upadhyay | work done | 74.6984 | 20.3411 | Inspected | RFI Approved | 330 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/066 | Checking FDD test for Subgrade 1st layer | 122000 | 122500 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 12:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 15:30 | Rushikesh Gunjal | 2025-03-11 16:27 | Checked and found ok | 2025-04-07 17:18 | Brajesh Upadhyay | work done | 74.7013 | 20.351 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/068 | Checking FDD test for Subgrade 1st layer | 123850 | 124700 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 12:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 16:19 | Rushikesh Gunjal | 2025-03-11 16:12 | Checked and found satisfactory | 2025-04-07 17:20 | Brajesh Upadhyay | work done | 74.7107 | 20.3679 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/069 | Checking FDD test for Subgrade 1st layer | 125750 | 126080 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 12:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 13:19 | Rushikesh Gunjal | 2025-03-07 14:40 | Checked and found ok | 2025-04-07 17:21 | Brajesh Upadhyay | work done | 74.7183 | 20.3742 | Inspected | RFI Approved | 330 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/070 | Checking FDD test for Subgrade 1st layer | 126080 | 126600 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 12:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 14:30 | Rushikesh Gunjal | 2025-03-07 13:15 | Work done & satisfactory result | 2025-04-07 17:22 | Brajesh Upadhyay | work done | 74.7263 | 20.3826 | Inspected | RFI Approved | 520 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/071 | Checking FDD test for Subgrade 1st layer | 126600 | 127000 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 12:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 17:21 | Rushikesh Gunjal | 2025-03-07 13:07 | Checked and found ok | 2025-04-07 17:23 | Brajesh Upadhyay | work done | 74.7349 | 20.3888 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/056 | Checking Level and FDD test for Subgrade Top | 127000 | 127850 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-06 22:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 15:30 | Rushikesh Gunjal | 2025-03-07 14:42 | Work done and found satisfactory | 2025-04-07 17:28 | Brajesh Upadhyay | approved | 74.7183 | 20.3742 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/055 | Checking Level and FDD test for Subgrade Top | 123850 | 124700 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-06 22:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 01:30 | Rushikesh Gunjal | 2025-03-07 14:49 | Work done and found satisfactory | 2025-04-07 17:27 | Brajesh Upadhyay | work done | 74.7143 | 20.3719 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/059 | Checking FDD test for Subgrade 1st layer | 129800 | 130300 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-06 23:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 16:05 | Rushikesh Gunjal | 2025-03-07 13:16 | Work done & satisfactory result | 2025-04-07 17:34 | Brajesh Upadhyay | work has been done | 74.7263 | 20.3826 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/060 | Checking FDD test for Subgrade 1st layer | 132000 | 132600 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-06 23:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 15:06 | Rushikesh Gunjal | 2025-03-07 12:27 | Work done & satisfactory result | 2025-04-07 17:36 | Brajesh Upadhyay | done | 74.7548 | 20.4144 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/063 | Checking FDD test for Subgrade 1st layer | 121800 | 122500 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-06 23:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 23:13 | Rushikesh Gunjal | 2025-03-07 15:25 | Checked and found ok | 2025-04-07 17:39 | Brajesh Upadhyay | work done | 74.6984 | 20.3408 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/080 | Checking FDD test for Subgrade 1st layer | 134000 | 134490 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 12:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 13:27 | Rushikesh Gunjal | 2025-03-11 15:36 | Checked and found ok | 2025-04-07 17:40 | Brajesh Upadhyay | Work has been done | 74.7578 | 20.4205 | Inspected | RFI Approved | 490 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/079 | Checking FDD test for Subgrade 1st layer | 133540 | 134000 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 12:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 17:26 | Rushikesh Gunjal | 2025-03-11 15:34 | Checked and found satisfactory | 2025-04-07 17:41 | Brajesh Upadhyay | work done | 74.7578 | 20.4205 | Inspected | RFI Approved | 460 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/078 | Checking FDD test for Subgrade 1st layer | 133260 | 133540 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 12:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 17:26 | Rushikesh Gunjal | 2025-03-07 12:38 | Work done & satisfactory result | 2025-04-07 17:43 | Brajesh Upadhyay | Work has been done | 74.7537 | 20.4107 | Inspected | RFI Approved | 280 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/077 | Checking FDD test for Subgrade 1st layer | 132600 | 133180 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-03-07 12:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-03-07 13:25 | Rushikesh Gunjal | 2025-03-07 12:38 | Work done & satisfactory result | 2025-04-07 17:44 | Brajesh Upadhyay | Work done | 74.7537 | 20.4107 | Inspected | RFI Approved | 580 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/488 | Checking FDD test for Subgrade 1st layer | 139590 | 140090 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 17:00 | Saurabh SE | 2025-05-15 12:59 | Checked and found ok | 2025-05-15 16:31 | Brajesh Upadhyay | Work has been done | 74.7752 | 20.4835 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/482 | Checking FDD test for Subgrade 1st layer | 138950 | 139590 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-11 18:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 11:30 | Saurabh SE | 2025-05-15 13:46 | Checked and found ok | 2025-05-15 16:32 | Brajesh Upadhyay | Work has been done | 74.7743 | 20.4792 | Inspected | RFI Approved | 640 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/479 | Checking Level and FDD test for Subgrade Top | 136380 | 137100 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 00:14 | Rushikesh Gunjal | 2025-05-15 12:23 | Checked and found ok | 2025-05-15 16:33 | Brajesh Upadhyay | Work has been done | 74.7628 | 20.455 | Inspected | RFI Approved | 720 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/477 | Checking FDD test for Subgrade 1st layer | 138380 | 138950 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-10 23:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-11 17:30 | Saurabh SE | 2025-05-15 14:08 | Checked and found ok | 2025-05-15 16:34 | Brajesh Upadhyay | Work has been done | 74.7661 | 20.4634 | Inspected | RFI Approved | 570 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/438 | Checking FDD test for Subgrade 1st layer | 137870 | 138380 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 19:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 15:00 | Rushikesh Gunjal | 2025-05-15 14:01 | Checked and found ok | 2025-05-15 16:36 | Brajesh Upadhyay | Work has been done | 74.7693 | 20.4699 | Inspected | RFI Approved | 510 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/437 | Checking FDD test for Subgrade 1st layer | 136380 | 137100 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-09 19:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-10 14:00 | Rushikesh Gunjal | 2025-05-15 14:08 | Checked and found ok | 2025-05-15 16:37 | Brajesh Upadhyay | Work has been done | 74.7667 | 20.4648 | Inspected | RFI Approved | 720 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/409 | Checking FDD test for Subgrade 1st layer | 137100 | 137870 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 17:33 | Rushikesh Gunjal | 2025-05-15 14:10 | Checked and found ok | 2025-05-15 16:38 | Brajesh Upadhyay | Work has been done | 74.7667 | 20.4648 | Inspected | RFI Approved | 770 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/408 | Checking FDD test for Subgrade 1st layer | 135750 | 136380 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 16:32 | Rushikesh Gunjal | 2025-05-15 14:16 | Checked and found ok | 2025-05-15 16:39 | Brajesh Upadhyay | Work has been done | 74.7654 | 20.4601 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/503 | Checking FDD and Level for Subgrade top Layer | 140090 | 140210 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-12 09:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-12 18:00 | Saurabh SE | 2025-05-13 12:51 | Level and FDD found ok | 2025-05-13 17:42 | Brajesh Upadhyay | Work has been done | 74.7774 | 20.4864 | Inspected | RFI Approved | 120 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/407 | Checking FDD test for Subgrade 1st layer | 134490 | 135230 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-08 22:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-09 15:00 | Rushikesh Gunjal | 2025-05-17 11:38 | Ok | 2025-05-17 18:11 | Brajesh Upadhyay | Work has been done | 74.758 | 20.4406 | Inspected | RFI Approved | 740 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/513 | Checking FDD & Level for Subgrade Top layer | 138380 | 138950 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 12:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-13 16:00 | Rushikesh Gunjal | 2025-05-19 15:53 | Checked and found ok | 2025-05-19 18:18 | Brajesh Upadhyay | Work done | 74.7697 | 20.4705 | Inspected | RFI Approved | 570 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/507 | Checking Level and FDD test for Subgrade Top | 135750 | 136380 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-05-13 09:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-05-13 13:00 | Rushikesh Gunjal | 2025-05-16 16:46 | Checked and found ok | 2025-05-16 19:21 | Brajesh Upadhyay | work has been done | 74.7631 | 20.4556 | Inspected | RFI Approved | 630 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1681 | Checking Of Level & FDD Test For Subgrade Top | 129703 | 129800 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 16:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:48 | Rushikesh Gunjal | 2025-10-30 11:23 | Work was already done | 2025-10-30 11:24 | Brajesh Upadhyay | work has been done | 74.7508 | 20.4036 | Inspected | RFI Approved | 97 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1493 | Checking Of Level & FDD Test For Subgrade Top | 124700 | 125100 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:11 | Rushikesh Gunjal | 2025-10-29 15:34 | Work was already done | 2025-10-30 11:31 | Brajesh Upadhyay | work has been done | 74.7171 | 20.3736 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1678 | Checking Of Level & FDD Test For Subgrade Top | 123750 | 123781 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 16:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:46 | Rushikesh Gunjal | 2025-10-28 12:42 | Work was already done | 2025-10-28 18:32 | Brajesh Upadhyay | work has been done | 74.7071 | 20.3607 | Inspected | RFI Approved | 31 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1677 | Checking Of Level & FDD Test For Subgrade Top | 129703 | 129800 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 16:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:45 | Rushikesh Gunjal | 2025-10-30 11:25 | Work was already done | 2025-10-30 11:29 | Brajesh Upadhyay | work has been done | 74.7508 | 20.4036 | Inspected | RFI Approved | 97 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1528 | Checking Of Level & FDD Test For Subgrade Top | 130800 | 131450 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:44 | Rushikesh Gunjal | 2025-10-30 11:37 | Work was already done | 2025-10-31 07:57 | Brajesh Upadhyay | work has been done | 74.7528 | 20.4086 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1504 | Checking Of Level & FDD Test For Subgrade Top | 130800 | 131450 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:22 | Rushikesh Gunjal | 2025-10-30 11:35 | Work was already done | 2025-10-31 07:59 | Brajesh Upadhyay | work has been done | 74.7528 | 20.4086 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1679 | Checking Of Level & FDD Test For Subgrade Top | 123791 | 123850 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 16:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:47 | Rushikesh Gunjal | 2025-10-28 12:48 | Work already done | 2025-10-28 18:32 | Brajesh Upadhyay | work has been done | 74.7078 | 20.3647 | Inspected | RFI Approved | 59 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1680 | Checking Of Level & FDD Test For Subgrade Top | 129380 | 129693 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 16:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:47 | Rushikesh Gunjal | 2025-10-30 11:24 | Work was already done | 2025-10-30 11:29 | Brajesh Upadhyay | work has been done | 74.7508 | 20.4036 | Inspected | RFI Approved | 313 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1255 | Checking Of Level & FDD test for Subgrade Top Layer | 120400 | 121020 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-14 09:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-14 14:00 | Saurabh SE | 2025-09-14 17:16 | Work done | 2025-09-14 18:58 | Brajesh Upadhyay | work has been done | 74.6981 | 20.3402 | Inspected | RFI Approved | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1136 | Checking Of Level & FDD test for Subgrade Top | 123750 | 123850 | BHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-30 16:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-31 13:30 | Saurabh SE | 2025-09-14 17:10 | Work done | 2025-09-14 19:24 | Brajesh Upadhyay | work has been done | 74.7076 | 20.3637 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1135 | Checking Of Level & FDD Test For Subgrade Top | 139900 | 140850 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-30 16:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-31 09:30 | Saurabh SE | 2025-09-14 14:32 | Work done | 2025-09-14 19:25 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4892 | Inspected | RFI Approved | 950 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1160 | Checking Of Level & FDD Test For Subgrade Top | 140210 | 140850 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-01 18:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-02 15:00 | Saurabh SE | 2025-09-14 14:36 | Work done | 2025-09-14 19:27 | Brajesh Upadhyay | work has been done | 74.7811 | 20.4892 | Inspected | RFI Approved | 640 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1119 | Checking Of Level & FDD Test For Subgrade Top | 136380 | 137100 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-28 16:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-29 09:30 | Rushikesh Gunjal | 2025-09-05 11:10 | Check found OK | 2025-09-14 12:15 | Brajesh Upadhyay | work has been done | 74.7662 | 20.4634 | Inspected | RFI Approved | 720 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1517 | Checking Of Level & FDD Test For Subgrade Top | 124500 | 125200 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:34 | Rushikesh Gunjal | 2025-10-30 17:03 | Work was already done | 2025-10-31 07:58 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 700 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1508 | Checking Of Level & FDD Test For Subgrade Top | 133260 | 133750 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:25 | Rushikesh Gunjal | 2025-10-30 16:09 | Work was already done | 2025-10-31 07:59 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4252 | Inspected | RFI Approved | 490 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1507 | Checking Of Level & FDD Test For Subgrade Top | 132600 | 133170 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:24 | Rushikesh Gunjal | 2025-10-30 16:09 | Work was already done | 2025-10-31 07:59 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4252 | Inspected | RFI Approved | 570 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1202 | Checking Of Level & FDD Test For Subgrade Top | 140850 | 141700 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 20:30 | Rushikesh Gunjal | 2025-09-13 15:14 | Check found OK | 2025-09-14 10:58 | Brajesh Upadhyay | work has been done | 74.7792 | 20.4876 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1201 | Checking Of Level & FDD Test For Subgrade Top | 120400 | 121020 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 17:00 | Rushikesh Gunjal | 2025-09-13 16:38 | Check found satisfactory result | 2025-09-14 11:09 | Brajesh Upadhyay | work has been done | 74.696 | 20.3381 | Inspected | RFI Approved | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1199 | Checking Of Level & FDD test for Subgrade Top Layer | 140850 | 141700 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-02 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-03 16:30 | Rushikesh Gunjal | 2025-09-13 15:15 | Check found OK | 2025-09-14 11:08 | Brajesh Upadhyay | work has been done | 74.7792 | 20.4876 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1158 | Checking Of Level & FDD Test For Subgrade Top | 133170 | 133260 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-01 18:01 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-02 11:00 | Saurabh SE | 2025-09-02 11:38 | Work done | 2025-09-03 10:05 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4894 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1159 | Checking Of Level & FDD Test For Subgrade Top | 134480 | 134490 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-01 18:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-02 12:30 | Rushikesh Gunjal | 2025-09-02 11:37 | Check found OK | 2025-09-03 10:06 | Brajesh Upadhyay | work has been done | 74.7813 | 20.4894 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1520 | Checking Of Level & FDD Test For Subgrade Top | 126440 | 127000 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:37 | Rushikesh Gunjal | 2025-10-28 15:22 | Work was already done | 2025-10-28 18:42 | Brajesh Upadhyay | work has been done | 74.7327 | 20.3873 | Inspected | RFI Approved | 560 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1497 | Checking Of Level & FDD Test For Subgrade Top | 126600 | 127000 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:16 | Rushikesh Gunjal | 2025-10-28 15:19 | Work was already done | 2025-10-28 18:45 | Brajesh Upadhyay | work has been done | 74.7327 | 20.3873 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1276 | Checking Of Level & FDD test for Subgrade Top Layer | 139590 | 140090 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 16:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-09-16 16:40 | Rushikesh Gunjal | 2025-09-16 16:47 | Check found OK | 2025-09-16 17:26 | Brajesh Upadhyay | work has been done | 74.7785 | 20.4876 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1104 | Checking Of Level and FDD test for Subgrade Top | 133170 | 133270 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 17:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 12:45 | Rushikesh Gunjal | 2025-08-30 11:56 | Check found Satisfactory result | 2025-09-01 09:20 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4285 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1105 | Checking Of Level and FDD test for Subgrade Top | 134470 | 134480 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 17:42 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 14:45 | Rushikesh Gunjal | 2025-08-30 11:57 | Check found OK | 2025-09-01 09:21 | Brajesh Upadhyay | work has been done | 74.7581 | 20.4285 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1103 | Checking Of Level and FDD test for Subgrade Top | 129380 | 129800 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-27 17:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-28 09:30 | Rushikesh Gunjal | 2025-08-29 15:01 | Check and found satisfactory result | 2025-08-30 06:53 | Brajesh Upadhyay | work has been done | 74.747 | 20.3977 | Inspected | RFI Approved | 420 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1120 | Checking Of Level & FDD Test For Subgrade Top | 137870 | 138600 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-08-28 16:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-08-29 15:30 | Rushikesh Gunjal | 2025-09-11 12:25 | Check found OK | 2025-09-14 12:16 | Brajesh Upadhyay | work has been done | 74.7758 | 20.4848 | Inspected | RFI Approved | 730 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/Backdated/114:NSK-II (20A)/1 | FDD AND LEVEL CHECKING OF SG TOP LAYER | 135230 | 135750 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-09-16 17:50 | Sanjay Sharma | 2025-07-05 12:46 | Sanjay Sharma | 2025-09-16 17:50 | Work done successfully. | 2025-09-16 17:50 | Sanjay Sharma | Approved | 0 | 0 | Inspected | RFI Approved | 520 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1394 | Checking Of Level & FDD test for Subgrade Top Layer | 117030 | 117750 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 17:50 | Rushikesh Gunjal | 2025-10-14 11:48 | Check found satisfactory result and level | 2025-10-14 13:42 | Brajesh Upadhyay | work has been done | 74.6894 | 20.3287 | Inspected | RFI Approved | 720 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1376 | Checking Of Level & FDD test for Subgrade Top Layer | 119000 | 119714 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 14:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 15:00 | Rushikesh Gunjal | 2025-10-14 11:43 | Check found Satisfactory result | 2025-10-14 13:45 | Brajesh Upadhyay | work has been done | 74.6895 | 20.3286 | Inspected | RFI Approved | 714 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1379 | Checking Of Level & FDD test for Subgrade Top Layer | 119000 | 119714 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:02 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 15:30 | Rushikesh Gunjal | 2025-10-14 11:44 | Work done | 2025-10-14 13:44 | Brajesh Upadhyay | work has been done | 74.6895 | 20.3286 | Inspected | RFI Approved | 714 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1382 | Checking Of Level & FDD test for Subgrade Top Layer | 117750 | 118350 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 15:55 | Rushikesh Gunjal | 2025-10-14 11:46 | Check found Satisfactory result | 2025-10-14 13:44 | Brajesh Upadhyay | work has been done | 74.6895 | 20.3287 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1386 | Checking Of Level & FDD test for Subgrade Top Layer | 117030 | 117750 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 16:30 | Rushikesh Gunjal | 2025-10-14 11:47 | Work done | 2025-10-14 13:43 | Brajesh Upadhyay | work has been done | 74.6894 | 20.3287 | Inspected | RFI Approved | 720 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1390 | Checking Of Level & FDD test for Subgrade Top Layer | 117750 | 118350 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-13 15:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-13 17:15 | Rushikesh Gunjal | 2025-10-14 11:49 | Work done | 2025-10-14 13:43 | Brajesh Upadhyay | work has been done | 74.6894 | 20.3287 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1349 | Checking Of Level & FDD test for Subgrade Top Layer | 119000 | 119714 | BHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-08 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-09 16:00 | Rushikesh Gunjal | 2025-10-09 17:17 | Work not done |  |  |  | 74.6907 | 20.3322 | Inspected | Inspected - Rejected - Work Not Done | 714 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1353 | Checking Of Level & FDD test for Subgrade Top Layer | 118350 | 119000 | BHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-09 17:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-10 13:00 | Rushikesh Gunjal | 2025-10-13 17:32 | Check found Satisfactory result | 2025-10-13 18:26 | Brajesh Upadhyay | work has been done | 74.6895 | 20.3284 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1524 | Checking Of Level & FDD Test For Subgrade Top | 128440 | 128900 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:40 | Rushikesh Gunjal | 2025-10-28 15:41 | Work already done | 2025-10-28 18:41 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 460 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1523 | Checking Of Level & FDD Test For Subgrade Top | 128000 | 128440 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:39 | Rushikesh Gunjal | 2025-10-28 15:41 | Work was already done | 2025-10-28 18:41 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 440 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1533 | Checking Of Level & FDD Test For Subgrade Top | 133540 | 134000 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:47 | Rushikesh Gunjal | 2025-10-30 16:01 | Work was already done | 2025-10-31 07:56 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4372 | Inspected | RFI Approved | 460 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1531 | Checking Of Level & FDD Test For Subgrade Top | 132600 | 133170 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:46 | Rushikesh Gunjal | 2025-10-30 16:10 | Work was already done | 2025-10-31 07:57 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4252 | Inspected | RFI Approved | 570 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1502 | Checking Of Level & FDD Test For Subgrade Top | 129800 | 130290 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:20 | Rushikesh Gunjal | 2025-10-30 11:13 | Work was already done | 2025-10-30 11:31 | Brajesh Upadhyay | work has been done | 74.7508 | 20.4036 | Inspected | RFI Approved | 490 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1503 | Checking Of Level & FDD Test For Subgrade Top | 130290 | 130800 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:21 | Rushikesh Gunjal | 2025-10-30 11:34 | Work was already done | 2025-10-31 07:59 | Brajesh Upadhyay | work has been done | 74.7528 | 20.4086 | Inspected | RFI Approved | 510 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1506 | Checking Of Level & FDD Test For Subgrade Top | 132000 | 132600 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:23 | Rushikesh Gunjal | 2025-10-30 16:23 | Work was already done | 2025-10-31 07:59 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1510 | Checking Of Level & FDD Test For Subgrade Top | 134000 | 134480 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:27 | Rushikesh Gunjal | 2025-10-30 16:01 | Work was already done | 2025-10-31 07:58 | Brajesh Upadhyay | work has been done | 74.7587 | 20.4371 | Inspected | RFI Approved | 480 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1519 | Checking Of Level & FDD Test For Subgrade Top | 126000 | 126440 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:35 | Rushikesh Gunjal | 2025-10-28 16:02 | Work was already done | 2025-10-28 18:42 | Brajesh Upadhyay | work has been done | 74.7248 | 20.3817 | Inspected | RFI Approved | 440 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1518 | Checking Of Level & FDD Test For Subgrade Top | 125200 | 126000 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:36 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:35 | Rushikesh Gunjal | 2025-10-28 16:01 | Work was already done | 2025-10-28 18:42 | Brajesh Upadhyay | work has been done | 74.7247 | 20.3817 | Inspected | RFI Approved | 800 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1516 | Checking Of Level & FDD Test For Subgrade Top | 123850 | 124500 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:33 | Rushikesh Gunjal | 2025-10-30 17:02 | Work was already done | 2025-10-31 07:58 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1557 | Checking Of Level & FDD Test For Subgrade Top | 139590 | 140090 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-18 10:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-18 10:31 | Rushikesh Gunjal | 2025-10-27 15:22 | Work already done | 2025-10-28 08:18 | Brajesh Upadhyay | work has been done | 74.7819 | 20.4915 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1526 | Checking Of Level & FDD Test For Subgrade Top | 129800 | 130290 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:42 | Rushikesh Gunjal | 2025-10-30 11:13 | Work was already done | 2025-10-30 11:30 | Brajesh Upadhyay | work has been done | 74.7508 | 20.4036 | Inspected | RFI Approved | 490 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1534 | Checking Of Level & FDD Test For Subgrade Top | 134000 | 134470 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:48 | Rushikesh Gunjal | 2025-10-30 16:02 | Work was already done | 2025-10-31 07:56 | Brajesh Upadhyay | work has been done | 74.7586 | 20.4371 | Inspected | RFI Approved | 470 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1527 | Checking Of Level & FDD Test For Subgrade Top | 130290 | 130800 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:43 | Rushikesh Gunjal | 2025-10-30 11:36 | Work was already done | 2025-10-31 07:58 | Brajesh Upadhyay | work has been done | 74.7528 | 20.4086 | Inspected | RFI Approved | 510 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1514 | Checking Of Level & FDD Test For Subgrade Top | 122500 | 123150 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:31 | Rushikesh Gunjal | 2025-10-28 12:21 | Work was already done | 2025-10-28 18:43 | Brajesh Upadhyay | work has been done | 74.7026 | 20.3532 | Inspected | RFI Approved | 650 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1532 | Checking Of Level & FDD Test For Subgrade Top | 133270 | 133540 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:47 | Rushikesh Gunjal | 2025-10-30 16:10 | Work was already done | 2025-10-31 07:56 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4251 | Inspected | RFI Approved | 270 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1530 | Checking Of Level & FDD Test For Subgrade Top | 132000 | 132600 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:45 | Rushikesh Gunjal | 2025-10-30 16:24 | Work was already done | 2025-10-31 07:57 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1529 | Checking Of Level & FDD Test For Subgrade Top | 131450 | 132000 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:45 | Rushikesh Gunjal | 2025-10-30 16:24 | Work was already done | 2025-10-31 07:57 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1515 | Checking Of Level & FDD Test For Subgrade Top | 123150 | 123750 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:32 | Rushikesh Gunjal | 2025-10-30 16:56 | Work was already done | 2025-10-31 07:58 | Brajesh Upadhyay | work has been done | 74.7382 | 20.3911 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1512 | Checking Of Level & FDD Test For Subgrade Top | 121470 | 121800 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:30 | Rushikesh Gunjal | 2025-10-28 12:10 | Work was already done | 2025-10-28 18:43 | Brajesh Upadhyay | work has been done | 74.6995 | 20.348 | Inspected | RFI Approved | 330 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1511 | Checking Of Level & FDD Test For Subgrade Top | 121020 | 121470 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:29 | Rushikesh Gunjal | 2025-10-28 12:11 | Work was already done | 2025-10-28 18:44 | Brajesh Upadhyay | work has been done | 74.6995 | 20.348 | Inspected | RFI Approved | 450 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1509 | Checking Of Level & FDD Test For Subgrade Top | 133750 | 134000 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:26 | Rushikesh Gunjal | 2025-10-30 16:00 | Work was already done | 2025-10-31 07:59 | Brajesh Upadhyay | work has been done | 74.7587 | 20.437 | Inspected | RFI Approved | 250 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1500 | Checking Of Level & FDD Test For Subgrade Top | 128440 | 128900 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:18 | Rushikesh Gunjal | 2025-10-28 15:39 | Work already done | 2025-10-28 18:44 | Brajesh Upadhyay | work has been done | 74.7409 | 20.3931 | Inspected | RFI Approved | 460 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1498 | Checking Of Level & FDD Test For Subgrade Top | 127000 | 127850 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:16 | Rushikesh Gunjal | 2025-10-28 15:20 | Work was already done | 2025-10-28 18:45 | Brajesh Upadhyay | work has been done | 74.7327 | 20.3873 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1496 | Checking Of Level & FDD Test For Subgrade Top | 126080 | 126600 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:15 | Rushikesh Gunjal | 2025-10-28 16:01 | Work was already done | 2025-10-28 18:45 | Brajesh Upadhyay | work has been done | 74.7248 | 20.3817 | Inspected | RFI Approved | 520 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1495 | Checking Of Level & FDD Test For Subgrade Top | 125500 | 126080 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:14 | Rushikesh Gunjal | 2025-10-28 16:00 | Work already done | 2025-10-28 18:45 | Brajesh Upadhyay | work has been done | 74.7247 | 20.3817 | Inspected | RFI Approved | 580 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1494 | Checking Of Level & FDD Test For Subgrade Top | 125100 | 125500 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:12 | Rushikesh Gunjal | 2025-10-29 15:35 | Work already done | 2025-10-30 11:31 | Brajesh Upadhyay | work has been done | 74.7171 | 20.3736 | Inspected | RFI Approved | 400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1505 | Checking Of Level & FDD Test For Subgrade Top | 131450 | 132000 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:22 | Rushikesh Gunjal | 2025-10-30 16:22 | Work was already done | 2025-10-31 07:59 | Brajesh Upadhyay | work has been done | 74.754 | 20.4115 | Inspected | RFI Approved | 550 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1492 | Checking Of Level & FDD Test For Subgrade Top | 123850 | 124700 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:09 | Rushikesh Gunjal | 2025-10-30 16:54 | Work was already done | 2025-10-31 08:03 | Brajesh Upadhyay | work has been done | 74.7382 | 20.3911 | Inspected | RFI Approved | 850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1491 | Checking Of Level & FDD Test For Subgrade Top | 123150 | 123750 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:08 | Rushikesh Gunjal | 2025-10-30 17:01 | Work was already done | 2025-10-31 08:03 | Brajesh Upadhyay | work has been done | 74.7383 | 20.3912 | Inspected | RFI Approved | 600 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1488 | Checking Of Level & FDD test for Subgrade Top Layer | 121500 | 122000 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-17 12:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-17 12:04 | Rushikesh Gunjal | 2025-10-28 12:12 | Work already done | 2025-10-28 18:46 | Brajesh Upadhyay | work has been done | 74.6995 | 20.348 | Inspected | RFI Approved | 500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1674 | Checking Of Level & FDD Test For Subgrade Top | 123750 | 123781 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 16:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:42 | Rushikesh Gunjal | 2025-10-28 12:45 | Work already done | 2025-10-28 18:32 | Brajesh Upadhyay | work has been done | 74.7072 | 20.3608 | Inspected | RFI Approved | 31 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1675 | Checking Of Level & FDD Test For Subgrade Top | 123791 | 123850 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 16:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:44 | Rushikesh Gunjal | 2025-10-28 12:44 | Work already done | 2025-10-28 18:32 | Brajesh Upadhyay | work has been done | 74.7071 | 20.3607 | Inspected | RFI Approved | 59 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1676 | Checking Of Level & FDD Test For Subgrade Top | 129400 | 129693 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-10-20 16:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-10-21 16:45 | Rushikesh Gunjal | 2025-10-30 11:22 | Work was already done | 2025-10-30 11:24 | Brajesh Upadhyay | work has been done | 74.7508 | 20.4036 | Inspected | RFI Approved | 293 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1739 | Checking Of Level & FDD Test For Subgrade Top | 117000 | 117030 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-13 18:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-14 14:00 | Rushikesh Gunjal | 2025-11-15 12:00 | Work done | 2025-11-15 13:07 | Brajesh Upadhyay | work has been done | 74.6728 | 20.3179 | Inspected | RFI Approved | 30 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1730 | Checking Of Level & FDD Test For Subgrade Top | 141750 | 141800 | LHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-13 08:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-13 14:00 | Rushikesh Gunjal | 2025-11-15 13:46 | Work done | 2025-11-15 14:44 | Brajesh Upadhyay | work has been done | 74.7829 | 20.4998 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/1731 | Checking Of Level & FDD Test For Subgrade Top | 141750 | 141800 | RHS | Road | Rigid Road | Subgrade | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2025-11-13 08:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2025-11-13 15:00 | Rushikesh Gunjal | 2025-11-15 13:52 | Work done | 2025-11-15 14:09 | Brajesh Upadhyay | work has been done | 74.7829 | 20.4998 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2046 | Checking Reinforcement, Shuttering & Pouring Concrete for Drain Slab | 120380 | 120400 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-18 17:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-20 14:30 | Rushikesh Gunjal | 2026-01-19 12:20 | Work not completed |  |  |  | 74.6941 | 20.3365 | Inspected | Inspected - Rejected - Work Not Done | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2044 | Checking Reinforcement Shuttering & Pouring Concrete For Drain Slab | 120600 | 120690 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-18 17:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-19 16:00 | Kishori Lal | 2026-01-20 15:25 | Wrong RFI. |  |  |  | 74.703 | 20.3516 | Inspected | Inspected - Fail | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2047 | Checking Of Reinforcement, Shuttering For Wall Final Lift A1,A2 & mid Wall , Top Haunch with Top Slab Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-18 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-19 17:00 | Kishori Lal | 2026-01-22 13:40 | Reinforcement and formwork checked and found satisfactory. | 2026-01-22 16:12 | Brajesh Upadhyay | work has been done | 74.7074 | 20.3636 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2043 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Wall 2nd Lift A1,A2 Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-18 09:26 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-18 16:00 | Kishori Lal | 2026-01-20 15:16 | Work done. | 2026-01-21 11:11 | Brajesh Upadhyay | work has been done | 74.7076 | 20.3637 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2062 | Checking Reinforcement, shuttering and pouring concrete for R.Wall Raft A1,A2 of MNB | 123800 | 123800 | LHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-28 18:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-29 15:40 | Kishori Lal | 2026-02-02 15:25 | Work not done. |  |  |  | 74.7073 | 20.3635 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2061 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 119945 | 119970 | LHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-28 18:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-29 16:30 | Rushikesh Gunjal | 2026-01-29 18:14 | Work done | 2026-01-29 20:06 | Brajesh Upadhyay | work has been done | 74.6913 | 20.334 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2048 | Checking of Reinforcement, Shuttering & Pouring Concrete For Terminal slab A1,A2 Of BC | 133216 | 133216 | RHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-19 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-20 14:00 | Kishori Lal | 2026-01-20 12:24 | Work done. | 2026-01-21 11:03 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4287 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2067 | Checking Of Providing & Fixing of Metal Beam Crash Barrier | 118470 | 118860 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-07 17:28 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-07 18:00 | Rushikesh Gunjal | 2026-02-10 15:01 | Check and found satisfactory | 2026-02-11 13:15 | Brajesh Upadhyay | work has been done | 74.687 | 20.3238 | Inspected | RFI Approved | 390 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2039 | Checking of Reinforcement, Shuttering & Pouring Concrete for terminal Slab A1,A2 of BC | 140928 | 140928 | RHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-16 17:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-17 11:00 | Rushikesh Gunjal | 2026-01-20 11:56 | Work done | 2026-01-21 11:14 | Brajesh Upadhyay | work has been done | 74.782 | 20.4921 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2045 | Checking Of Layout Marking, Excavation & Laying PCC For Terminal Slab A1,A2 Of BC | 133216 | 133216 | RHS | Culvert | Box/Slab Culvert | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-18 17:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-19 12:00 | Kishori Lal | 2026-01-20 12:23 | Work done. | 2026-01-21 11:11 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4287 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2041 | Checking Of Reinforcement, shuttering & Pouring Concrete for Drain wall | 129600 | 129690 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-17 18:07 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-18 10:00 | Kishori Lal | 2026-01-20 12:34 | Work done. | 2026-01-21 11:13 | Brajesh Upadhyay | work has been done | 74.7481 | 20.3987 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2049 | Checking Of Level & FDD test for Earthen Shoulder 1st layer | 120400 | 121020 | LHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-20 13:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-21 14:00 | Rushikesh Gunjal | 2026-01-21 11:44 | Unsuitable material |  |  |  | 74.6979 | 20.3402 | Inspected | Inspected - Fail | 620 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2050 | Checking Of Level & FDD Test & Filling Of Earthen Shoulder Top Layer | 137850 | 138720 | RHS | Road | Rigid Road | Earth Works | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-20 14:04 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-20 14:30 | Rushikesh Gunjal | 2026-01-22 15:49 | Work done | 2026-01-22 16:12 | Brajesh Upadhyay | work has been done | 74.7735 | 20.4782 | Inspected | RFI Approved | 870 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2051 | Checking Reinforcement , Shuttering & Pouring Concrete For Drain Slab | 129600 | 129690 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-20 18:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-21 11:00 | Rushikesh Gunjal | 2026-01-22 17:18 | Work done | 2026-01-24 12:40 | Brajesh Upadhyay | work has been done | 74.7478 | 20.3983 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2052 | Checking of Pouring Concrete for Wall A1,A2 & Mid Wall Final Lift, Top Hunch & top Slab Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-21 17:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-22 14:00 | Kishori Lal | 2026-02-02 15:13 | Work done. | 2026-02-03 09:55 | Brajesh Upadhyay | work has been done | 74.7086 | 20.3641 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2053 | Checking Reinforcement, Shuttering & Pouring Concrete For Drain Slab | 120380 | 120400 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-21 17:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-22 11:00 | Kishori Lal | 2026-01-22 13:52 | Work already done. | 2026-01-22 16:11 | Brajesh Upadhyay | work has been done | 74.6941 | 20.3366 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2113 | Checking Of Layout Marking, Excavation & Laying PCC For Cut off Wall Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-26 17:57 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-27 09:30 | Rushikesh Gunjal | 2026-02-27 10:21 | Work not done |  |  |  | 74.7075 | 20.3634 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2114 | Checking of Reinforcement, Shuttering & Pouring Concrete For Cut off Wall 1st lift Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-26 17:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-27 16:00 | Rushikesh Gunjal | 2026-02-27 10:23 | Work not done |  |  |  | 74.7075 | 20.3635 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2085 | Checking of Providing & Fixing of Crash Barrier Metal Beam | 123640 | 123780 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-10 17:39 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-11 16:00 | Rushikesh Gunjal | 2026-02-21 10:04 | Check found satisfactory | 2026-02-21 13:32 | Brajesh Upadhyay | work has been done | 74.7074 | 20.3622 | Inspected | RFI Approved | 140 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2073 | Checking Reinforcement, Shuttering & Pouring Concrete For R.Wall 3rd Lift A1,A2 of MNB | 123800 | 123800 | LHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-08 18:51 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-09 10:00 | Kishori Lal | 2026-02-14 13:14 | Work done. | 2026-02-16 09:21 | Brajesh Upadhyay | work has been done | 74.7074 | 20.3637 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2077 | Checking Of Reinforcement, Shuttering & Pouring Concrete For Parapet Wall Of MNB | 123800 | 123800 | LHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-09 17:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-10 11:00 | Kishori Lal | 2026-02-14 13:16 | Work done. | 2026-02-16 09:20 | Brajesh Upadhyay | work has been done | 74.7075 | 20.3637 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2059 | Checking Of Layout Marking Excavation & Laying PCC For R.Wall A1,A2 Of MNB | 123800 | 123800 | LHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-27 17:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-28 12:00 | Kishori Lal | 2026-02-02 15:16 | Work done. | 2026-02-03 09:55 | Brajesh Upadhyay | work has been done | 74.7055 | 20.3631 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2056 | Checking Of Reinforcement, shuttering and pouring concrete for Drain Raft | 119945 | 119970 | LHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-01-24 17:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-01-25 10:00 | Kishori Lal | 2026-02-02 15:42 | Work done. | 2026-02-03 09:55 | Brajesh Upadhyay | work has been done | 74.6908 | 20.3333 | Inspected | RFI Approved | 25 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2087 | Checking Reinforcement, Shuttering & Pouring Concrete For R.Wall Raft of MNB A1, A2 | 123800 | 123800 | RHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-14 17:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-15 12:30 | Kishori Lal | 2026-02-17 17:01 | Work done. | 2026-02-19 10:02 | Brajesh Upadhyay | work has been done | 74.7079 | 20.3633 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2086 | Checking Of Layout Marking , Excavation & Laying PCC For R. Wall A1,A2 Of MNB | 123800 | 123800 | RHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-14 08:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-14 16:00 | Kishori Lal | 2026-02-14 13:20 | Work done. | 2026-02-16 09:20 | Brajesh Upadhyay | work has been done | 74.7074 | 20.3635 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2063 | Checking Of Providing & Fixing of Metal Beam Crash Barrier | 118470 | 118860 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-05 17:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-06 11:00 | Rushikesh Gunjal | 2026-02-06 18:29 | Metal Beam not fixed |  |  |  | 74.6869 | 20.3237 | Inspected | Inspected - Rejected - Work Not Done | 390 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2070 | Checking of Providing & Fixing of Crash Barrier Metal Beam | 118880 | 119170 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-08 15:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-08 17:00 | Rushikesh Gunjal | 2026-02-16 14:26 | Work done | 2026-02-17 09:07 | Brajesh Upadhyay | work has been done | 74.6899 | 20.3269 | Inspected | RFI Approved | 290 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2088 | Checking Reinforcement, shuttering and pouring concrete for R.Wall 1St Lift A1, A2 of MNB | 123800 | 123800 | RHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-16 18:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-17 10:00 | Kishori Lal | 2026-02-17 17:02 | Work done. | 2026-02-19 10:01 | Brajesh Upadhyay | work has been done | 74.7083 | 20.3634 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2116 | Checking of Reinforcement, Shuttering & Pouring Concrete For Cut off Wall Casting Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-01 09:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-01 17:00 | Rushikesh Gunjal | 2026-03-02 17:02 | Check R/f and shuttering found Satisfactory and allow for concrete pouring. | 2026-03-06 10:48 | Brajesh Upadhyay | work has been done | 74.2258 | 19.564 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2084 | Checking of Providing & Fixing of Crash Barrier Metal Beam | 140350 | 140570 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-10 17:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-11 13:00 | Rushikesh Gunjal | 2026-02-18 14:44 | Check found Satisfactory | 2026-02-19 10:02 | Brajesh Upadhyay | work has been done | 74.7796 | 20.488 | Inspected | RFI Approved | 220 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2092 | Checking Reinforcement, shuttering and pouring concrete for R.Wall Crash Barrier A1, A2 of MNB | 123800 | 123800 | LHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-19 08:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-19 14:30 | Kishori Lal | 2026-03-11 12:53 | Work done. | 2026-03-12 10:17 | Brajesh Upadhyay | work has been done | 74.7074 | 20.3635 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2090 | Checking Reinforcement, shuttering and pouring concrete for R.Wall 3rd Lift A1,A2 of MNB | 123800 | 123800 | RHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-19 08:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-19 13:30 | Kishori Lal | 2026-03-11 12:51 | Work done. | 2026-03-12 10:18 | Brajesh Upadhyay | work has been done | 74.7075 | 20.3635 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2093 | Checking Reinforcement, shuttering and pouring concrete for Parapet Wall of MNB | 123800 | 123800 | RHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-19 08:31 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-20 17:00 | Kishori Lal | 2026-03-11 12:54 | Work done. | 2026-03-12 10:17 | Brajesh Upadhyay | work has been done | 74.7074 | 20.3635 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2099 | Checking Of FDD Test For Filling Of Earthen Shoulder | 136980 | 138720 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-20 15:19 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-20 18:00 | Rushikesh Gunjal | 2026-02-21 12:13 | Check FDD test and found satisfactory result l. | 2026-02-21 13:30 | Brajesh Upadhyay | work has been done | 74.7657 | 20.461 | Inspected | RFI Approved | 1740 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2095 | Checking Of FDD Test For Filling Of Earthen Shoulder | 141700 | 141800 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-20 15:12 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-20 16:30 | Rushikesh Gunjal | 2026-02-21 12:38 | Check fdd test and found a satisfactory result | 2026-02-21 13:30 | Brajesh Upadhyay | work has been done | 74.7828 | 20.4982 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2100 | Checking Of FDD Test For Filling Of Earthen Shoulder | 129703 | 131400 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-20 15:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-20 18:30 | Rushikesh Gunjal | 2026-02-21 13:08 | Check FDD test and found a satisfactory result | 2026-02-21 13:29 | Brajesh Upadhyay | work has been done | 74.7519 | 20.406 | Inspected | RFI Approved | 1697 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2097 | Checking Of FDD Test For Filling Of Earthen Shoulder | 140120 | 141690 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-20 15:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-20 17:15 | Rushikesh Gunjal | 2026-02-21 12:26 | Check FDD test and found a satisfactory result. | 2026-02-21 13:30 | Brajesh Upadhyay | work has been done | 74.7815 | 20.4902 | Inspected | RFI Approved | 1570 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2096 | Checking Of FDD Test For Filling Of Earthen Shoulder | 128250 | 129500 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-20 15:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-20 17:00 | Rushikesh Gunjal | 2026-02-21 13:21 | Check found satisfactory | 2026-02-21 13:30 | Brajesh Upadhyay | work has been done | 74.7362 | 20.3896 | Inspected | RFI Approved | 1250 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2102 | Checking Of FDD Test For Filling Of Earthen Shoulder | 138720 | 140120 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-20 15:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-21 10:00 | Rushikesh Gunjal | 2026-02-21 12:17 | Check FDD test and found a satisfactory result. | 2026-02-21 13:29 | Brajesh Upadhyay | work has been done | 74.7746 | 20.4794 | Inspected | RFI Approved | 1400 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2104 | Checking Reinforcement, shuttering and pouring concrete for R.Wall Third Lift A1, A2 of MNB | 123800 | 123800 | RHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-21 08:48 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-21 15:00 | Kishori Lal | 2026-03-11 12:57 | Repeat RFI |  |  |  | 74.7075 | 20.3635 | Inspected | Inspected - Fail | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2082 | Checking Of Providing & Fixing of Metal Beam Crash Barrier | 123600 | 123780 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-09 17:21 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-10 16:00 | Rushikesh Gunjal | 2026-02-21 10:03 | Check found Satisfactory | 2026-02-21 13:33 | Brajesh Upadhyay | work has been done | 74.7073 | 20.3618 | Inspected | RFI Approved | 180 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2075 | Checking Of Providing & Fixing of Metal Beam Crash Barrier | 123815 | 123920 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-09 16:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-09 18:00 | Rushikesh Gunjal | 2026-02-21 10:07 | Check found Satisfactory | 2026-02-21 13:34 | Brajesh Upadhyay | work has been done | 74.7077 | 20.3647 | Inspected | RFI Approved | 105 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2079 | Checking Of Providing & Fixing of Metal Beam Crash Barrier | 133225 | 133245 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-09 17:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-10 13:00 | Rushikesh Gunjal | 2026-02-21 11:52 | Check found satisfactory | 2026-02-21 13:33 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4289 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2078 | Checking Of Providing & Fixing of Metal Beam Crash Barrier | 133190 | 133210 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-09 17:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-10 10:00 | Rushikesh Gunjal | 2026-02-21 11:53 | Work done | 2026-02-21 13:34 | Brajesh Upadhyay | work has been done | 74.7582 | 20.4289 | Inspected | RFI Approved | 20 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2071 | Checking of Providing & Fixing of Crash Barrier Metal Beam | 140840 | 140910 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-08 15:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-08 17:30 | Rushikesh Gunjal | 2026-02-21 12:29 | Check found satisfactory | 2026-02-21 13:35 | Brajesh Upadhyay | work has been done | 74.782 | 20.4917 | Inspected | RFI Approved | 70 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2072 | Checking of Providing & Fixing of Crash Barrier Metal Beam | 140940 | 141120 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-08 15:17 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-08 18:00 | Rushikesh Gunjal | 2026-02-21 12:31 | Work done and found satisfactory | 2026-02-21 13:35 | Brajesh Upadhyay | work has been done | 74.7821 | 20.4923 | Inspected | RFI Approved | 180 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2103 | Checking Of FDD Test For Filling Of Earthen Shoulder | 133220 | 134980 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-20 15:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-21 14:00 | Rushikesh Gunjal | 2026-02-21 11:50 | Check and found Satisfactory | 2026-02-21 13:28 | Brajesh Upadhyay | work has been done | 74.7585 | 20.4296 | Inspected | RFI Approved | 1760 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2101 | Checking Of FDD Test For Filling Of Earthen Shoulder | 135340 | 136980 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-20 15:22 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-20 18:40 | Rushikesh Gunjal | 2026-02-21 12:06 | Check fdd test and found satisfactory result | 2026-02-21 13:29 | Brajesh Upadhyay | work has been done | 74.7617 | 20.4526 | Inspected | RFI Approved | 1640 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2098 | Checking Of FDD Test For Filling Of Earthen Shoulder | 131400 | 133210 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-20 15:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-20 17:30 | Rushikesh Gunjal | 2026-02-21 13:05 | Check FDD test and found a satisfactory result | 2026-02-21 13:30 | Brajesh Upadhyay | work has been done | 74.7546 | 20.4136 | Inspected | RFI Approved | 1810 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2094 | Checking Of FDD Test For Filling Of Earthen Shoulder | 126750 | 128250 | RHS | Road | Rigid Road | Shoulder | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-20 15:11 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-20 16:00 | Rushikesh Gunjal | 2026-02-21 13:21 | Check found satisfactory | 2026-02-21 13:31 | Brajesh Upadhyay | work has been done | 74.7362 | 20.3896 | Inspected | RFI Approved | 1500 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2083 | Checking of Providing & Fixing of Crash Barrier Metal Beam | 123530 | 123580 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-10 17:35 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-11 10:00 | Rushikesh Gunjal | 2026-02-21 10:01 | Check found Satisfactory | 2026-02-21 13:33 | Brajesh Upadhyay | work has been done | 74.7081 | 20.3622 | Inspected | RFI Approved | 50 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2076 | Checking Of Providing & Fixing of Metal Beam Crash Barrier | 129710 | 129800 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-09 16:59 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-09 18:30 | Rushikesh Gunjal | 2026-02-21 13:11 | Check found satisfactory | 2026-02-21 13:34 | Brajesh Upadhyay | work has been done | 74.7488 | 20.4001 | Inspected | RFI Approved | 90 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2074 | Checking Of Providing & Fixing of Metal Beam Crash Barrier | 141300 | 141400 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-09 16:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-09 17:00 | Rushikesh Gunjal | 2026-02-21 12:41 | Check found satisfactory | 2026-02-21 13:34 | Brajesh Upadhyay | work has been done | 74.7831 | 20.4963 | Inspected | RFI Approved | 100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2081 | Checking Of Providing & Fixing of Metal Beam Crash Barrier | 119370 | 119430 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-09 17:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-10 14:00 | Rushikesh Gunjal | 2026-02-21 14:33 | Check found Satisfactory | 2026-02-22 17:53 | Brajesh Upadhyay | work has been done | 74.7045 | 20.3634 | Inspected | RFI Approved | 60 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2117 | Checking OF Reinforcement, Shuttering & Pouring concrete For Drain Wall | 134560 | 134640 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-05 09:44 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-05 17:00 | Rushikesh Gunjal | 2026-03-11 17:58 | Work not done |  |  |  | 74.7579 | 20.4411 | Inspected | Inspected - Rejected - Work Not Done | 80 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2115 | Checking Of Layout Marking, Excavation & Laying PCC For Cut off Wall Of MNB | 123800 | 123800 | BHS | Bridge | Minor Bridge Reconstruction | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-01 09:13 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-01 10:00 | Rushikesh Gunjal | 2026-03-02 17:00 | Work done | 2026-03-06 10:49 | Brajesh Upadhyay | work has been done | 74.2256 | 19.564 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2106 | Checking Reinforcement, shuttering and pouring concrete for Drain Raft | 129490 | 129500 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-22 18:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-23 17:00 | Rushikesh Gunjal | 2026-02-26 16:17 | Work already done | 2026-02-27 10:39 | Brajesh Upadhyay | work has been done | 74.747 | 20.3977 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2105 | Checking Of Layout Marking , Excavation & Laying PCC For Drain | 129490 | 129500 | RHS | Drain | Road Side Drain | Foundation | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-22 18:15 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-23 09:00 | Rushikesh Gunjal | 2026-02-26 16:17 | Work already done | 2026-02-27 10:39 | Brajesh Upadhyay | work has been done | 74.7471 | 20.3977 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2108 | Checking Reinforcement, shuttering and pouring concrete for R.Wall Final Lift A1, A2 of MNB | 123800 | 123800 | RHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-22 18:23 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-23 16:00 | Rushikesh Gunjal | 2026-02-24 12:27 | Work done | 2026-02-24 16:51 | Brajesh Upadhyay | WORK HAS BEEN DONE | 74.7075 | 20.3635 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2107 | Checking Of Reinforcement, Shuttering and pouring concrete For crash barrier Of MNB | 123800 | 123800 | RHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-22 18:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-23 17:00 | Rushikesh Gunjal | 2026-02-26 10:33 | Check found Satisfactory | 2026-02-27 10:39 | Brajesh Upadhyay | work has been done | 74.7074 | 20.3637 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2109 | checking of calibration of RMC Palnt | 125900 | 125900 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-23 11:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-24 11:30 | Rushikesh Gunjal | 2026-02-26 17:39 | No arrangement for calibration |  |  |  | 74.7224 | 20.377 | Inspected | Inspected - Rejected - Work Not Done | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2111 | Checking Reinforcement, shuttering and pouring concrete for Drain Wall | 129490 | 129500 | RHS | Drain | Road Side Drain | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-24 08:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-24 13:00 | Rushikesh Gunjal | 2026-02-26 16:18 | Work already done | 2026-02-27 10:39 | Brajesh Upadhyay | work has been done | 74.7471 | 20.3978 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2112 | Checking Reinforcement, shuttering and pouring concrete for Drain Slab | 129490 | 129500 | RHS | Drain | Road Side Drain | Finishing Work | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-24 08:27 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-25 12:00 | Rushikesh Gunjal | 2026-02-26 16:19 | Work already done | 2026-02-27 10:38 | Brajesh Upadhyay | work has been done | 74.7467 | 20.3975 | Inspected | RFI Approved | 10 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2110 | Checking Reinforcement, shuttering and pouring concrete for R.Wall Crash Barrier A1,A2 of MNB | 123800 | 123800 | RHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-24 08:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-24 12:30 | Rushikesh Gunjal | 2026-02-26 10:32 | Work done | 2026-02-27 10:39 | Brajesh Upadhyay | work has been done | 74.7074 | 20.3637 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2129 | Checking of Excavation of Earthen Drain | 140940 | 141740 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-24 14:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-25 14:00 | Rushikesh Gunjal | 2026-03-25 15:55 | Work done | 2026-03-26 09:19 | Brajesh Upadhyay | work has been done | 74.7829 | 20.4963 | Inspected | RFI Approved | 800 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2130 | Checking of Excavation of Earthen Drain | 121300 | 122250 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-24 14:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-25 15:00 | Rushikesh Gunjal | 2026-03-26 10:44 | Work done | 2026-03-27 10:30 | Brajesh Upadhyay | work has been done | 74.699 | 20.3454 | Inspected | RFI Approved | 950 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2091 | Checking Reinforcement, shuttering and pouring concrete for Crash Barrier of MNB | 123800 | 123800 | LHS | Bridge | Minor Bridge Reconstruction | Superstructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-19 08:25 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-19 14:00 | Kishori Lal | 2026-03-11 12:52 | Work done. | 2026-03-12 10:18 | Brajesh Upadhyay | work has been done | 74.7075 | 20.3634 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2089 | Checking Reinforcement, shuttering and pouring concrete for R.Wall 2nd Lift A1, A2 of MNB | 123800 | 123800 | RHS | Bridge | Minor Bridge Reconstruction | Substructure | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-02-17 18:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-02-18 10:00 | Kishori Lal | 2026-03-11 12:50 | Work done. | 2026-03-12 10:18 | Brajesh Upadhyay | work has been done | 74.7075 | 20.3635 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2123 | Checking Of Excavation Of Earthen Drain | 125900 | 127630 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-23 18:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-24 15:00 | Rushikesh Gunjal | 2026-03-25 15:14 | Work done | 2026-03-26 09:20 | Brajesh Upadhyay | work has been done | 74.7281 | 20.384 | Inspected | RFI Approved | 1730 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2126 | Checking Of Excavation Of Earthen Drain | 127630 | 129480 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-23 18:37 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-24 18:00 | Rushikesh Gunjal | 2026-03-27 15:39 | Work done | 2026-03-28 10:22 | Brajesh Upadhyay | work has been done | 74.732 | 20.3866 | Inspected | RFI Approved | 1850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2124 | Checking Of Development Of Minor Junction | 122256 | 122256 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-23 18:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-25 10:00 | Rushikesh Gunjal | 2026-03-24 16:35 | Check and found satisfactory Work done | 2026-03-24 20:34 | Brajesh Upadhyay | work has been done | 74.7014 | 20.3512 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2121 | Checking Of Development Of Minor Junction | 135935 | 135935 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-23 18:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-24 12:30 | Rushikesh Gunjal | 2026-03-24 15:13 | Check and found satisfactory work done | 2026-03-24 20:34 | Brajesh Upadhyay | work has been done | 74.7615 | 20.4528 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2120 | Checking Of Development Of Minor Junction | 121011 | 121011 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-23 18:24 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-24 09:00 | Rushikesh Gunjal | 2026-03-24 16:39 | Check found Satisfactory work done | 2026-03-24 20:35 | Brajesh Upadhyay | work has been done | 74.6982 | 20.3408 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2118 | Checking Of Development Of Minor Junction | 125190 | 125190 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-21 17:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-22 10:00 | Rushikesh Gunjal | 2026-03-23 16:04 | Check and found satisfactory work done | 2026-03-24 09:48 | Brajesh Upadhyay | work has been done | 74.7163 | 20.3729 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2131 | Checking of Excavation of Earthen Drain | 134820 | 134980 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-24 14:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-25 17:00 | Rushikesh Gunjal | 2026-04-01 15:27 | Work done | 2026-04-02 20:03 | Brajesh Upadhyay | work has been done | 74.7584 | 20.4444 | Inspected | RFI Approved | 160 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2127 | Checking Of Development Of Minor Junction | 138536 | 138536 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-23 18:38 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-25 17:00 | Rushikesh Gunjal | 2026-03-24 15:20 | Check found Satisfactory work done | 2026-03-24 20:33 | Brajesh Upadhyay | work has been done | 74.7724 | 20.4761 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2125 | Checking Of Development Of Minor Junction | 138768 | 138768 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-23 18:34 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-25 14:00 | Rushikesh Gunjal | 2026-03-24 15:21 | Check found Satisfactory work done | 2026-03-24 20:34 | Brajesh Upadhyay | work has been done | 74.7724 | 20.4761 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2119 | Checking Of Development Of Minor Junction | 125123 | 125123 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-22 18:08 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-23 10:00 | Rushikesh Gunjal | 2026-03-24 16:27 | Check found satisfactory work done | 2026-03-24 20:40 | Brajesh Upadhyay | work has been done | 74.7156 | 20.3728 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2133 | Checking of Excavation of Earthen Drain | 117000 | 118320 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-25 17:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-26 11:30 | Rushikesh Gunjal | 2026-03-26 10:24 | Work done | 2026-03-27 10:28 | Brajesh Upadhyay | work has been done | 74.6772 | 20.3204 | Inspected | RFI Approved | 1320 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2132 | Checking of Excavation of Earthen Drain | 118320 | 119700 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-25 17:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-26 10:00 | Rushikesh Gunjal | 2026-03-26 10:34 | Work done | 2026-03-27 10:28 | Brajesh Upadhyay | work has been done | 74.6893 | 20.3288 | Inspected | RFI Approved | 1380 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2134 | Checking of Excavation of Earthen Drain | 122250 | 123410 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-25 17:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-26 13:00 | Rushikesh Gunjal | 2026-03-26 10:48 | Work done | 2026-03-27 10:28 | Brajesh Upadhyay | work has been done | 74.704 | 20.356 | Inspected | RFI Approved | 1160 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2128 | Checking of Excavation of Earthen Drain | 117000 | 118320 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-24 14:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-25 12:30 | Rushikesh Gunjal | 2026-03-26 10:27 | Work done | 2026-03-27 10:30 | Brajesh Upadhyay | work has been done | 74.6758 | 20.3197 | Inspected | RFI Approved | 1320 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2135 | Checking of Excavation of Earthen Drain | 130890 | 132050 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-25 17:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-26 15:00 | Rushikesh Gunjal | 2026-03-27 15:45 | Work done | 2026-03-28 10:22 | Brajesh Upadhyay | work has been done | 74.7544 | 20.4133 | Inspected | RFI Approved | 1160 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2139 | Checking of Excavation of Earthen Drain | 136290 | 137300 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-26 17:32 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-27 16:00 | Rushikesh Gunjal | 2026-03-27 15:52 | Work done | 2026-03-28 10:20 | Brajesh Upadhyay | work has been done | 74.7635 | 20.4562 | Inspected | RFI Approved | 1010 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2141 | Checking of Excavation of Earthen Drain | 124800 | 125900 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-27 17:14 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-28 12:00 | Rushikesh Gunjal | 2026-03-28 10:56 | Work done | 2026-03-29 09:56 | Brajesh Upadhyay | work has done been done | 74.7104 | 20.3675 | Inspected | RFI Approved | 1100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2137 | Checking of Excavation of Earthen Drain | 138460 | 139710 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-26 16:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-27 11:30 | Rushikesh Gunjal | 2026-03-27 16:01 | Work done | 2026-03-28 10:20 | Brajesh Upadhyay | work has been done | 74.7747 | 20.481 | Inspected | RFI Approved | 1250 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2136 | Checking of Excavation of Earthen Drain | 120400 | 121300 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-26 16:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-27 10:00 | Rushikesh Gunjal | 2026-03-27 11:15 | Work done | 2026-03-28 10:20 | Brajesh Upadhyay | work has been done | 74.698 | 20.3405 | Inspected | RFI Approved | 900 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2138 | Checking of Excavation of Earthen Drain | 122250 | 123780 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-26 16:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-27 14:00 | Rushikesh Gunjal | 2026-03-28 10:51 | Work done | 2026-03-29 09:57 | Brajesh Upadhyay | work has done been done | 74.7024 | 20.3529 | Inspected | RFI Approved | 1530 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2144 | Checking of Excavation of Earthen Drain | 138460 | 139710 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-27 17:20 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-28 17:00 | Rushikesh Gunjal | 2026-03-28 12:39 | Work done | 2026-03-29 09:56 | Brajesh Upadhyay | work has done been done | 74.7754 | 20.4835 | Inspected | RFI Approved | 1250 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2142 | Checking of Excavation of Earthen Drain | 130890 | 132050 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-27 17:16 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-28 13:30 | Rushikesh Gunjal | 2026-03-28 12:55 | Work done | 2026-03-29 09:56 | Brajesh Upadhyay | work has done been done | 74.7548 | 20.4148 | Inspected | RFI Approved | 1160 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2140 | Checking of Excavation of Earthen Drain | 123850 | 124800 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-27 17:10 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-28 10:00 | Rushikesh Gunjal | 2026-03-28 15:05 | Work done | 2026-03-29 09:57 | Brajesh Upadhyay | work has done been done | 74.7117 | 20.3689 | Inspected | RFI Approved | 950 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2143 | Checking of Excavation of Earthen Drain | 118320 | 119700 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-27 17:18 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-28 15:00 | Rushikesh Gunjal | 2026-03-28 15:31 | Work done | 2026-03-29 09:56 | Brajesh Upadhyay | work has done been done | 74.6886 | 20.3249 | Inspected | RFI Approved | 1380 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2149 | Checking Of Excavation Of Earthen Drain | 120400 | 121300 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-29 16:52 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-30 17:00 | Rushikesh Gunjal | 2026-03-31 10:23 | Work done | 2026-03-31 21:15 | Brajesh Upadhyay | work has been donr | 74.6952 | 20.3376 | Inspected | RFI Approved | 900 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2145 | Checking Of Excavation Of Earthen Drain | 124800 | 125900 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-29 16:45 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-30 10:00 | Rushikesh Gunjal | 2026-03-31 10:37 | Work done | 2026-03-31 21:17 | Brajesh Upadhyay | work has been done | 74.715 | 20.3724 | Inspected | RFI Approved | 1100 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2152 | Checking of Excavation of Earthen Drain | 132050 | 133180 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-31 17:03 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-04-01 10:00 | Rushikesh Gunjal | 2026-04-01 15:20 | Work done | 2026-04-02 19:51 | Brajesh Upadhyay | work has been done | 74.7573 | 20.4193 | Inspected | RFI Approved | 1130 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2153 | Checking of Excavation of Earthen Drain | 135340 | 136290 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-31 17:05 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-04-01 12:00 | Rushikesh Gunjal | 2026-04-01 15:30 | Work done | 2026-04-02 19:50 | Brajesh Upadhyay | work has been done | 74.7611 | 20.4516 | Inspected | RFI Approved | 950 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2155 | Checking of Excavation of Earthen Drain | 129720 | 130890 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-31 17:09 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-04-01 16:00 | Rushikesh Gunjal | 2026-04-01 15:17 | Work done | 2026-04-02 19:49 | Brajesh Upadhyay | work has been done | 74.752 | 20.4061 | Inspected | RFI Approved | 1170 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2157 | Checking Of Laying Of Paver Blocks | 134980 | 135340 | LHS | Road | Rigid Road | Paver Block | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-31 18:41 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-04-01 10:00 | Rushikesh Gunjal | 2026-04-01 15:26 | Check and found satisfactory work done | 2026-04-02 19:44 | Brajesh Upadhyay | work has been dome | 74.7584 | 20.4447 | Inspected | RFI Approved | 360 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2146 | Checking Of Excavation Of Earthen Drain | 129720 | 130890 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-29 16:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-30 12:00 | Rushikesh Gunjal | 2026-04-01 15:16 | Work done | 2026-04-02 19:55 | Brajesh Upadhyay | work has been done | 74.7521 | 20.4061 | Inspected | RFI Approved | 1170 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2147 | Checking Of Excavation Of Earthen Drain | 136290 | 137300 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-29 16:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-30 13:00 | Rushikesh Gunjal | 2026-04-01 15:31 | Work done | 2026-04-02 19:54 | Brajesh Upadhyay | work has been done | 74.7612 | 20.4518 | Inspected | RFI Approved | 1010 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2156 | Checking of Reinforcement, Shuttering & pouring Concrete for Transaction Slab | 141800 | 141800 | BHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-31 17:58 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-04-01 11:00 | Rushikesh Gunjal | 2026-04-01 15:41 | Work already done | 2026-04-02 19:48 | Brajesh Upadhyay | work has been done | 74.7828 | 20.4996 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2148 | Checking Of Excavation Of Earthen Drain | 139710 | 140920 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-29 16:50 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-30 15:00 | Rushikesh Gunjal | 2026-04-01 15:43 | Work done | 2026-04-02 19:54 | Brajesh Upadhyay | work has been done | 74.7819 | 20.4915 | Inspected | RFI Approved | 1210 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2163 | Checking of Excavation of Earthen Drain | 133230 | 134500 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-04-02 10:47 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-04-03 16:00 | Rushikesh Gunjal | 2026-04-03 14:38 | Work done | 2026-04-04 09:00 | Brajesh Upadhyay | work has been done | 74.7584 | 20.4295 | Inspected | RFI Approved | 1270 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2162 | Checking of Excavation of Earthen Drain | 132050 | 133180 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-04-02 10:46 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-04-03 13:00 | Rushikesh Gunjal | 2026-04-03 14:39 | Work done | 2026-04-04 09:02 | Brajesh Upadhyay | work has been done | 74.7584 | 20.4296 | Inspected | RFI Approved | 1130 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2154 | Checking of Excavation of Earthen Drain | 125900 | 127630 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-31 17:06 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-04-01 14:00 | Rushikesh Gunjal | 2026-04-01 15:12 | Work done | 2026-04-02 19:49 | Brajesh Upadhyay | work has been done | 74.7302 | 20.3852 | Inspected | RFI Approved | 1730 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2151 | Checking Of Excavation Of Earthen Drain | 139710 | 140920 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-29 16:55 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-30 19:00 | Rushikesh Gunjal | 2026-04-01 15:36 | Work done | 2026-04-02 19:53 | Brajesh Upadhyay | work has been done | 74.7754 | 20.4841 | Inspected | RFI Approved | 1210 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2150 | Checking Of Excavation Of Earthen Drain | 127630 | 129480 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-29 16:54 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-30 18:00 | Rushikesh Gunjal | 2026-04-01 15:11 | Work done | 2026-04-02 19:54 | Brajesh Upadhyay | work has been done | 74.7303 | 20.3852 | Inspected | RFI Approved | 1850 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2159 | Checking of Excavation of Earthen Drain | 137300 | 138460 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-04-02 10:33 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-04-03 12:00 | Rushikesh Gunjal | 2026-04-03 15:58 | Work done | 2026-04-04 09:03 | Brajesh Upadhyay | work has been done | 74.7657 | 20.4618 | Inspected | RFI Approved | 1160 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2164 | Checking of Excavation of Earthen Drain | 137300 | 138460 | RHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-04-02 10:49 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-04-03 18:00 | Rushikesh Gunjal | 2026-04-05 10:06 | Work done | 2026-04-07 10:15 | Brajesh Upadhyay | work has been done | 74.766 | 20.4622 | Inspected | RFI Approved | 1160 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2158 | Checking of Excavation of Earthen Drain | 133230 | 134500 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-04-02 10:30 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-04-03 10:00 | Rushikesh Gunjal | 2026-04-03 14:37 | Work done | 2026-04-04 09:03 | Brajesh Upadhyay | work has been done | 74.7583 | 20.4296 | Inspected | RFI Approved | 1270 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2161 | Checking of Reinforcement Shuttering & Pouring Concrete For Anchor Beam | 117000 | 117000 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-04-02 10:43 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-04-03 17:00 | Rushikesh Gunjal | 2026-04-05 12:21 | Work already done | 2026-04-07 10:15 | Brajesh Upadhyay | work has been done | 74.6727 | 20.3178 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2160 | Checking of Shuttering & Laying pipe PCC For Anchor Beam | 117000 | 117000 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-04-02 10:40 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-04-03 11:00 | Rushikesh Gunjal | 2026-04-05 12:20 | Work already done | 2026-04-07 10:16 | Brajesh Upadhyay | work has been done | 74.6727 | 20.3178 | Inspected | RFI Approved | 0 | 114:NSK-II (20A)
114:NSK-II (20A) | RFI/114:NSK-II (20A)/2122 | Checking Of Excavation Of Earthen Drain | 123410 | 123780 | LHS | Road | Rigid Road | Other | CTR0050 | Shri Rajureshwar Infrastructure (75%) in JV with V.P. Sethi Construction Pvt Ltd (25%) JV | AE Group 8 | Rodic Consultants Pvt. Ltd. | 2026-03-23 18:29 | Shri Rajureshwar Infrastructure_VPSCPL JV | 2026-03-24 10:00 | Rushikesh Gunjal | 2026-04-03 16:28 | Work done | 2026-04-07 10:17 | Brajesh Upadhyay | work has been done | 74.7069 | 20.3603 | Inspected | RFI Approved | 370 | 114:NSK-II (20A)